## 01_Dashboard
CARPOOL MOBILITY PLATFORM (CMP) - IMPLEMENTATION DASHBOARD
Every figure on this sheet is a live formula over 02_Work_Items, 07_Testing and 08_Bugs_Issues. Nothing here is typed. Update the tracker and this sheet follows.
PROJECT OVERVIEW
Project | Carpool Mobility Platform |  |  |  | Sprint |  | 15-Day MVP Sprint |  | Start Date |  | TBD - no delivery horizon supplied (BAD-DEC-002)
Project Code | CMP |  |  |  | Total Features |  |  |  | Target Date |  | TBD - no release date is supportable (TR-107)
Documentation baseline | CMP-DOC-01 to CMP-DOC-20, all v0.1 Draft |  |  |  | Documents approved |  | 0 of 20 |  | Application source code |  | None existed at plan date
Plan basis | Dependency-ordered, not capacity-fitted |  |  |  | Team composition |  | Not supplied (BAD-CON-017) |  | MVP scope |  | Proposed only, not approved (BAD-DEC-020)
KEY METRICS - live counts over the 507 implementation work items
Total Work Items |  | Completed |  | Remaining |  | In Progress |  | Blocked |  | Implemented (flag) |  | Committed (flag)
Pushed (flag) |  | Tested (flag) |  | Reviewed (flag) |  | Open Bugs |  | Critical Bugs |  | High Bugs |  | Total Effort (h)
PROJECT HEALTH - percentages are of all work items, not of the 15-day subset
Health measure | Count | Of total | % |  |  |  | Interpretation
Overall completion | [6 empty] | Work items with Status = Completed
Implementation | [6 empty] | Code exists. Not the same as committed.
Commit | [6 empty] | A Git commit exists. Log it on 05_Commits.
Push | [6 empty] | The commit reached the remote. Log it on 06_Pushes.
Testing | [6 empty] | Testing completed successfully. Log cases on 07_Testing.
Review | [6 empty] | Project Owner or code review completed.
Blocked | [6 empty] | Blocked on a named decision. Cannot be worked around.
Unblocked and plannable | [6 empty] | Work that can begin once the chain is approved.
Status | Count | % of total | Bar
Not Started
In Analysis
Ready
In Progress
Implemented
Committed
Pushed
Testing
Tested
Reviewed
Completed
Blocked
Cancelled
DAILY PROGRESS - PLAN vs ACTUAL - Planned is the documented day allocation; the rest are live counts
Day | Planned | Implemented | Committed | Pushed | Tested | Completed | Remaining | Blocked | Effort (h) | Cumulative planned effort
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
Day 8
Day 9
Day 10
Day 11
Day 12
Day 13
Day 14
Day 15
Post-MVP | [9 empty] | {"formula":""}
TBD | [9 empty] | {"formula":""}
TESTING SUMMARY & BUG SUMMARY - from 07_Testing and 08_Bugs_Issues
Testing measure | Value | [5 empty] | Bug measure | Value
Total tests recorded |  | A passing suite is not readiness (TR-121). The largest risks here are undecided, not defective. CMP-DOC-18 requires a negative test for every integrity-critical requirement. |  |  |  |  | Open bugs |  | Two entries on 09_Decisions are defects in the requirement baseline rather than code bugs: FRD-GAP-006 (a driver with confirmed bookings has no way to cancel) and FRD-GAP-014 (the platform can hold money with no specified means of returning it). Neither needs engineering to resolve.
Passed | [6 empty] | Critical
Failed | [6 empty] | High
Blocked | [6 empty] | Medium
Retest Required | [6 empty] | Low
Not Tested | [6 empty] | Closed bugs
Pass Rate | [6 empty] | Bug count on work items
SCOPE SPLIT - priority, platform and work type
Priority | Items | Effort (h) |  | Platform | Items | Effort (h) |  | Work type (top) | Items | Effort (h)
P0 |  |  |  | Android |  |  |  | Backend
P1 |  |  |  | Laravel |  |  |  | Testing
P2 |  |  |  | MySQL |  |  |  | Security
|  |  |  | Filament |  |  |  | API
|  |  |  | Cross Platform |  |  |  | Admin
Documentation
UI
DevOps
FEATURE ANALYSIS - live from 03_Feature_Summary; every column is a formula
Feature | Epic | Total | Completed | Implemented | Committed | Pushed | Tested | Remaining | Blocked | Bugs | Completion % | Progress
FEAT-001 Project Foundation - Android | EPIC-01 Foundation & Architecture
FEAT-002 Project Foundation - Laravel | EPIC-01 Foundation & Architecture
FEAT-003 Project Foundation - Database | EPIC-01 Foundation & Architecture
FEAT-004 Authentication & Session | EPIC-02 Identity & Access
FEAT-005 Registration & Phone Verification | EPIC-02 Identity & Access
FEAT-006 Profile & Counterparty Disclosure | EPIC-02 Identity & Access
FEAT-007 Roles & Authorisation | EPIC-02 Identity & Access
FEAT-008 Vehicle Management | EPIC-03 Supply
FEAT-009 Ride Publishing | EPIC-03 Supply
FEAT-010 Ride Preferences | EPIC-03 Supply
FEAT-011 Ride Search & Route Matching | EPIC-04 Discovery
FEAT-012 Ride Detail & Commitment Surface | EPIC-04 Discovery
FEAT-013 Ride Request | EPIC-05 Transaction
FEAT-014 Booking & Seat Allocation | EPIC-05 Transaction
FEAT-015 Fare & Payment Initiation | EPIC-05 Transaction
FEAT-016 Payment Verification & Reconciliation | EPIC-05 Transaction
FEAT-017 Ledger | EPIC-05 Transaction
FEAT-018 Trip Execution | EPIC-06 Journey
FEAT-019 Live Position Tracking | EPIC-06 Journey
FEAT-020 Estimates & Multi-Passenger Trip | EPIC-06 Journey
FEAT-021 Trip History & Records | EPIC-06 Journey
FEAT-022 Messaging | EPIC-07 Communication
FEAT-023 Notifications | EPIC-07 Communication
FEAT-024 Emergency Contacts | EPIC-08 Safety
FEAT-025 Safety Incident Pipeline | EPIC-08 Safety
FEAT-026 Safety Centre & Safety Surface | EPIC-08 Safety
FEAT-027 Admin Foundation & Projections | EPIC-09 Operations
FEAT-028 Admin Inspection & Intervention | EPIC-09 Operations
FEAT-029 Admin Payment Reconciliation | EPIC-09 Operations
FEAT-030 Admin Safety & Support | EPIC-09 Operations
FEAT-031 Admin Operational Reporting | EPIC-09 Operations
FEAT-032 Backend Authority & Idempotency | EPIC-10 Cross-Cutting Integrity
FEAT-033 Evidential Log & Audit | EPIC-10 Cross-Cutting Integrity
FEAT-034 Degraded Operation & Configuration | EPIC-10 Cross-Cutting Integrity
FEAT-035 API Contract & Versioning | EPIC-10 Cross-Cutting Integrity
FEAT-036 Security Controls | EPIC-11 Security
FEAT-037 Verification & Test Infrastructure | EPIC-12 Quality
FEAT-038 Build, Pipeline & Environments | EPIC-13 DevOps & Release
FEAT-039 Observability & Operations | EPIC-13 DevOps & Release
HOW TO READ THIS DASHBOARD
1. Implemented, Committed, Pushed, Tested, Reviewed and Completed are SIX SEPARATE STAGES. Code existing is not a commit; a commit is not a push; a push is not a test. Set each flag independently on 02_Work_Items.
2. A work item reaches Completed only when it is implemented, committed, pushed, tested and reviewed. Nothing in this workbook sets Completed automatically - the Project Owner has final authority.
3. The Blocked count is not a delivery problem. Every blocked item names the business or technical decision that blocks it, on 09_Decisions and 10_Dependencies. None can be worked around by engineering.
4. The Day 1 to Day 15 allocation is DEPENDENCY-ORDERED, not capacity-fitted. No team size, budget or delivery horizon has been supplied (BAD-CON-017, BAD-DEC-002). Compare Effort (h) per day against real capacity before treating the plan as a commitment.
5. This register contains implementation work only. Business decisions, functional gaps, withheld areas and documentation conflicts are not work items and are never counted here - they live on 09_Decisions, 10_Dependencies and 11_Risks. A row marked Blocked is buildable work whose value or policy is not yet set, not a decision waiting to be taken.
6. Percentages are of all 507 implementation work items. They are not release readiness. Release readiness is assessed against the twelve criteria of CMP-DOC-20 section 10.1, of which one is currently met.
7. A measure with no data is reported as unavailable or as zero-with-no-tests-recorded, never as success. This mirrors FRD-FR-236, which exists because a dashboard reporting "refunds: 0" when refunds are unimplemented reads as good news.
DAILY PROGRESS CHART - planned work per day against implemented, completed and blocked

## 02_Work_Items
CMP - MASTER IMPLEMENTATION WORK ITEMS
Carpool Mobility Platform ¦ Project Code CMP ¦ Implementation work only. Every row derives from a numbered document statement. Business decisions, functional gaps, withheld areas and documentation conflicts are NOT work items - they are carried on 09_Decisions, 10_Dependencies and 11_Risks. A row marked Blocked is buildable work whose value or policy is not yet set; it names what blocks it.
PLANNING REFERENCE (derived from documentation) | [15 empty] | OWNER-MAINTAINED COLUMNS ->
Work ID | Epic | Feature | Module | Work Type | Work Description | Subtask | Platform | Layer | Requirement ID | Use Case ID | Priority | Dependency | Planned Day | Estimated Effort (h) | Assigned To | Status | Implemented | Committed | Pushed | Tested | Reviewed | Blocked | Bug Count | Commit Hash | Push Reference | Test Result | Notes | Last Updated
CMP-IMP-001 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Configuration | Create Android project skeleton (Kotlin, Jetpack Compose, single Activity) | Gradle setup; Compose BOM; single-activity host; theme scaffold; smoke build | Android | UI | MOB-001; MADR-08; ARCH-014 | - | P0 | - | Day 1 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-002 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Configuration | Create the module structure: app, presentation, domain, data, platform, core | Module creation; Gradle wiring; package skeletons; empty-module build | Android | UI | MOB-001; MOB-002; MOB-003; MOB-005 | - | P0 | - | Day 1 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-003 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | DevOps | Enforce module dependency direction at build time | Dependency-rule plugin; rule set for MOB-002/003/006; fail-on-violation; CI wiring | Android | UI | MOB-007; MOB-161; OPS-108; OPS-109; TC-037 | - | P0 | - | Day 2 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-004 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Android | Implement core provenance wrapper carrying value plus as-of marking | Provenance type; as-of instant; authoritative/cached flag; unit tests | Android | Domain | MOB-009; MADR-02; UXDR-02; API-047 | - | P0 | - | Day 1 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-005 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Android | Implement core Result type and the four-class error model | Result sealed type; InvalidRequest/BusinessRefusal/DependencyUnavailable/InternalFault; mapping tests | Android | Domain | MOB-009; MADR-10; AADR-02 | - | P0 | - | Day 1 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-006 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Configuration | Configure the compile-time dependency injection graph | DI framework setup; module bindings; app-module composition only; graph verification test | Android | UI | MADR-03; MOB-005 | - | P0 | - | Day 2 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-007 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Android | Configure injected coroutine dispatchers and structured concurrency | Dispatcher provider; no static dispatcher references; scope ownership; lint rule | Android | Domain | MADR-09; MOB-166 | - | P0 | - | Day 2 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-008 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | DevOps | Configure build variants supplying environment values at build time | Variant definitions; no env value in source; config injection; verification test | Android | UI | MOB-013; MOB-162; MOB-163; OPS-107; NFR-108 | - | P0 | - | Day 2 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-009 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Testing | Add static analysis proving absence of business logic in the client | Rule for fare/seat/state-transition computation; fail-on-violation; baseline run | Android | UI | MOB-010; MOB-011; OPS-110; SRS-REQ-125; TC-037 | - | P0 | - | Day 3 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-010 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Configuration | Declare supported Android version range and device characteristics in the build | minSdk/targetSdk declaration; device characteristic declaration; build check | Android | UI | MOB-164; OPS-111; NFR-093; NFR-094 | - | P0 | MOB-OQ-001 | TBD | 3 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - supported device range is unresolved (MOB-OQ-001, OPS-112).
CMP-IMP-011 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | DevOps | Produce a measurable client artefact size in the build | Size measurement task; report emission; record baseline | Android | UI | MOB-165; OPS-113; NFR-156 | - | P0 | - | Day 3 | 3 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Budget figure unset (OPS-114, GAP-015). Measure now so a budget can be set from observation.
CMP-IMP-012 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UI | Build the single-Activity navigation destination graph | Destination graph; one route per screen; back behaviour; deep-link entry points | Android | UI | MADR-08; MOB-020; UX-010 | - | P0 | - | Day 3 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-013 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UI | Move all user-facing and brand-bearing strings to resources | String resource files; lint against literals in code; no brand name pending BAD-DEC-023 | Android | UI | MOB-012; ARCH-027; NFR-110 | - | P0 | - | Day 3 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-014 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UX | Add accessibility hooks to the Compose surface scaffolding | Semantics properties; touch target sizing; content descriptions; focus order | Android | UI | MOB 5.3; UX-015; NFR-088 | - | P0 | - | Day 4 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - accessibility conformance standard is unchosen (MOB-OQ-002, UX 15.3).
CMP-IMP-015 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Integration | Implement client version negotiation against the platform | Version header carriage; supported-range read; unsupported detection; forced-update path | Android | Network | MOB-057; API-024; API-025; API-027 | - | P0 | - | Day 4 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-016 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UI | Build Screen 32 - Version unsupported | Compose surface; reachable without session; offers no business capability; navigation lock | Android | UI | UX-004; UX-005; API-026 | - | P0 | - | Day 4 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-017 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | Android | Implement the immutable screen-state contract and state-holder base | One state object per screen; values carry provenance; survives configuration change | Android | ViewModel | MOB-015; MOB-016; MOB-017; UXDR-05; UX-015; UX-016; UX-017 | - | P0 | - | Day 4 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-018 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UX | Implement the four designed screen conditions: loaded, loading, empty, failed | Shared condition components; no default treatments; per-condition rendering rules | Android | UI | UXDR-07; UX 5.1 | - | P0 | - | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-019 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UX | Implement the four failure treatments on the client | Invalid request; business refusal; dependency unavailable; internal fault; branch mapping | Android | UI | UXDR-03; UX 7; MADR-10; AADR-02 | - | P0 | - | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-020 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | Android Shell | UX | Implement status presentation that never relies on colour alone | Icon and text pairing; contrast check; review against UXDR-16 | Android | UI | UXDR-16; UX 15.2 | - | P0 | - | Day 5 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-021 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Create Laravel project with Interface/Application/Domain/Infrastructure namespaces | Project init; namespace roots; autoload mapping; domain-area sub-organisation; smoke boot | Laravel | Service | BE-001; BE-004; BADR-01; ARCH-014 | - | P0 | - | Day 1 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-022 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Testing | Enforce inward-only layer dependency by static analysis in the build | Architecture-test tool; Domain-references-no-framework rule; fail-on-violation | Laravel | Service | BE-002; BE-003; BE-014; BADR-18; TC-037 | - | P0 | - | Day 2 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-023 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the application service base with command and result types | Command objects in application terms; result distinguishing success from each failure class; HTTP-free invocation | Laravel | Service | BE-041; BE-042; BE-043; BE-046; BADR-03 | - | P0 | - | Day 2 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-024 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement transaction boundary ownership in application services only | Transaction manager; guard preventing begin/commit outside application layer; narrowest-scope rule | Laravel | Service | BE-047; BE-054; ARCH-032; BADR-03 | - | P0 | - | Day 3 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-025 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the idempotency registry at the application boundary | mch_idempotency_registry table; key acceptance; same-transaction write; replay semantics | Laravel | Repository | BE-045; BE-051; BADR-08; ARCH-124; DADR-13 | - | P0 | - | Day 3 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-026 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement after-commit domain event dispatch | Aggregate records events; dispatcher fires after commit; listener registration; event immutability | Laravel | Service | BE-020; BE-022; BE-039; BADR-06 | - | P0 | - | Day 4 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-027 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the seven job families with priority separation | Family declarations; no undeclared eighth; per-family queue binding; drain and pause controls | Laravel | Queue | BE-131; BE-133; BADR-07 | - | P0 | - | Day 4 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-028 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Make every job idempotent, outcome-recording and failure-visible | Safe re-execution; outcome record; failed state visible to operations; identity carried explicitly | Laravel | Queue | BE-135; BE-136; BE-137; BE-140; BE-141 | - | P0 | - | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-029 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Register scheduled work in the scheduled-generation, reconciliation and maintenance families | Scheduler bindings; frequency as configuration; single-active-scheduler assumption recorded | Laravel | Queue | BE-143; BE-145; BE-146; BE-147; BE-148 | - | P0 | - | Day 5 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-030 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the port and adapter skeleton with a capability result type | Domain port interfaces; capability result; adapter registration; unavailability signalling | Laravel | Model | BE-036; BADR-11; ARCH-061 | - | P0 | - | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-031 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the typed, versioned, cached policy configuration store | cfg_policy_values and cfg_policy_versions; typed accessors; cache; change evidenced | Laravel | Repository | BE 13.1; BADR-12; ARCH-146; DB-008 | - | P0 | - | Day 6 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-032 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the configuration-driven state machine engine | cfg_state_models; transition contracts in Domain; definitions as configuration; illegal-transition refusal | Laravel | Model | BE-038; BADR-13; ARCH-037; DB-039 | - | P0 | - | Day 6 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Six state models are undecided (BAD-DEC-015 and others). The engine is buildable; the definitions are not.
CMP-IMP-033 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement application-layer authorisation evaluated deny-by-default | Authorisation evaluated before domain invocation; single path; capability check; refusal recording | Laravel | Authorization | BE-044; BADR-14; SADR-06; ARCH-031 | - | P0 | - | Day 6 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-034 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement the four-class backend error model | Error classification; mapping to interface branches; no leakage of internal fault detail | Laravel | Service | BADR-17; BE 14.2; AADR-02 | - | P0 | - | Day 7 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-035 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Security | Bootstrap the safety surface as a separately bootable entry point | Separate entry point; minimum dependency set; independent boot verification | Laravel | Service | BADR-16; BE-191; OPS-041; AADR-11 | - | P0 | - | Day 7 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-036 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Testing | Add structural enforcement tests for the backend | ORM absent from Domain/Application/Interface; no business rule in controller, resource, job or listener; one rule one component | Laravel | Service | BE-009; BE-010; BE-011; BE-012; BE 17.2; TC-037 | - | P0 | - | Day 7 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-037 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | Backend Shell | Backend | Implement repository interfaces in Domain with the ORM behind them | Repository contracts returning domain objects; infrastructure implementations; no ORM leakage | Laravel | Repository | BE-037; BE 8.1; BADR-05 | - | P0 | - | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-038 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Create the MySQL schema on InnoDB with a full-range Unicode character set | Schema creation; InnoDB default; charset and collation; CHECK-enforcing server version verified | MySQL | Schema | DB-001; DB-009; DB-010; OPS-024; DADR-02 | - | P0 | - | Day 1 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-039 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Establish the six storage domains by table name prefix | op_, led_, ev_, proj_, mch_, cfg_ convention; migration-time domain membership check | MySQL | Schema | DB-002; DB-003; DB-014; DADR-01 | - | P0 | - | Day 1 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-040 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Implement the dual key convention: internal surrogate and external opaque identifier | BIGINT UNSIGNED AUTO_INCREMENT PK; random external id; entropy; no meaning, sequence or timestamp; internal key never exposed | MySQL | Schema | DB-021; DB-022; DB-023; DB-024; DADR-03; API-013; API-014 | - | P0 | - | Day 2 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-041 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Implement cursor paging on sort-key plus internal-id tuples | Cursor encoding; opacity; non-constructible by caller; monotonic key guarantee | MySQL | Query | DB-025; DB-026; DB-027; DADR-04; API-112 | - | P0 | - | Day 2 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-042 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Apply the type conventions: exact decimal money, instant timestamps, protected columns | DECIMAL money; no float anywhere; single time zone reference; protected and non-recoverable column marking | MySQL | Schema | DB-031; DB-033; DB-034; DB-035; DB-036; DADR-06 | - | P0 | - | Day 2 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - monetary precision is unset (DB-032), depending on scale figures not supplied (GAP-016).
CMP-IMP-043 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Security | Enforce bound parameters everywhere and forbid concatenated statements | Query construction review; static check; allow-list for sort and filter parameters | MySQL | Query | DB-038; SADR-09; SEC-119; SEC-121; BE-102 | - | P0 | - | Day 3 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-044 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Forbid geography in any table, column, index, constraint name or partition | Naming rule; migration-time check; review of all identifiers | MySQL | Schema | DB-020; DADR-14; SRS-REQ-101 | - | P0 | - | Day 3 | 3 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-045 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Establish naming, index-naming and constraint-naming conventions | Snake case; plural tables; singular columns; index names state columns; constraint names state the rule | MySQL | Schema | DB-015; DB-016; DB-017; DB-018; DB-019 | - | P0 | - | Day 3 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-046 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | DevOps | Set up the migration framework with a destructive-migration approval path | Migration tooling; ordering; recorded approval for destructive change; no migration rewrites evidence | MySQL | Migration | DB 16; DB-218; DB-219; OPS-034 | - | P0 | - | Day 4 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-047 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Security | Create the three database accounts and their grants | Application account; migration account; read account unable to alter evidence; grant inspection test | MySQL | Schema | DADR-09; OPS 11.2; TC 9 | - | P0 | - | Day 4 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-048 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Declare foreign key policy: enforced within op_, none into proj_, none from mch_ into op_ | FK declarations; prohibition checks; no cascade delete into another party evidence | MySQL | Schema | DB-012; DB-013; DB-029; DB-030 | - | P0 | - | Day 4 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-049 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Database | Record the interface version on tables whose interpretation depends on it | Version column on op_rides, op_bookings, op_payments; question answered per new table | MySQL | Schema | DB-040; DB-058; DB-063; DB-070; DADR-16 | - | P0 | - | Day 5 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-050 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | Schema Foundation | Testing | Establish the integrity constraint register and its verification | Constraint inventory; CHECK constraints; constraint-violation test per rule | MySQL | Schema | DB 15; TC 9 | - | P0 | - | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-051 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Database | Create op_users, op_user_credentials and op_sessions migrations | Table definitions; non-recoverable credential column; terminated-session retention; verification standing column with no inbound write path | MySQL | Schema | DB-041; DB-042; DB-044; DB-045 | UC-001; UC-003 | P0 | FEAT-002; FEAT-003 | Day 5 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-052 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Backend | Implement the User aggregate constructible only into a valid state | Aggregate; invariants; domain events; no framework types | Laravel | Model | BE-017; BE-019; BE-021; BE-022 | UC-001 | P0 | FEAT-002; FEAT-003 | Day 6 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-053 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | API | Implement POST /sessions to establish an authenticated session | Application service; credential check; session creation; response shape; idempotency key | Laravel | Controller | FRD-FR-014; FRD-FR-016; API 11.1; SEC 6 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 6 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-054 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Security | Refuse authentication without disclosing which credential element failed | Uniform refusal; timing consideration; refusal reason identifier; negative test | Laravel | Service | FRD-FR-015; AADR-14; SEC 5 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-055 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Backend | Admit a user holding a valid existing session without re-authentication | Session validation; expiry bound; admission path | Laravel | Service | FRD-FR-017; NFR-055 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 7 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-056 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | API | Implement POST /sessions/current/refresh within the session bound | Refresh operation; bound enforcement; refusal past bound | Laravel | Controller | NFR-055; API 11.1; SEC 6 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 7 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-057 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | API | Implement DELETE /sessions/current terminating a session and preventing reuse | Termination; recorded as terminated not removed; reuse detection; negative test | Laravel | Controller | FRD-FR-019; DB-044; NFR-054; API-103 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 7 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-058 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Backend | Route a user whose account is not phone-verified to verification rather than into the app | Verification standing check at session establishment; routing response; client handling | Laravel | Service | FRD-FR-018 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 7 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-059 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Backend | Terminate the session locally when the platform is unreachable and invalidate centrally on next contact | Local termination; deferred central invalidation; outbox entry; reconciliation | Cross Platform | Data | FRD-FR-021 | UC-003; UC-004 | P1 | FEAT-002; FEAT-003 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-060 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | UI | Build Screen 2 - Log in | Compose surface; field validation; refusal presentation; loading state; navigation on success | Android | UI | UX 4.1 Screen 2 | UC-003 | P0 | FEAT-002; FEAT-003 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-061 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Android | Implement the login state holder and client use case | Immutable state; intent handling; use case invocation; error class mapping | Android | ViewModel | MOB-015; UXDR-04; MADR-02 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 7 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-062 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Security | Implement session material storage on the device | Protected storage; no replayable material; clearing on termination; no logging of material | Android | Data | SEC 13.1; SADR-04; SADR-13; MOB 14 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-063 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Android | Clear cached business data on the device when a session ends | Cache wipe; outbox handling; verification that no business value survives | Android | Local DB | FRD-FR-020; SEC 13.3 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 8 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-064 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Integration | Implement the platform gateway session carriage | Single versioned gateway; session header; unauthenticated handling; no direct surface access | Android | Network | MADR-04; MOB-004; API 9 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-065 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | Authentication | Testing | Write authentication and session verification tests | Unit refusal uniformity; integration session lifecycle; contract branch shapes; negative reuse of terminated session | Cross Platform | Validation | TC-025; TC-029; TC-030; TC-031; FR-04 | UC-003; UC-004 | P0 | FEAT-002; FEAT-003 | Day 8 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-066 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Database | Create the op_user_verifications migration retaining attempts and outcomes | Table; per-channel attempts; outcome retention so limits are enforceable against state | MySQL | Schema | DB-043; FRD-FR-011 | UC-001; UC-002 | P0 | FEAT-004 | Day 5 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-067 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Allow a person without an account to initiate registration | Registration entry operation; no session required; rate posture | Laravel | Service | FRD-FR-001; API 9.1 | UC-001; UC-002 | P0 | FEAT-004 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-068 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Require and validate the mandatory registration details including phone number | Field requirements; validation; per-field refusal naming the unacceptable detail | Laravel | Service | FRD-FR-002; FRD-FR-003 | UC-001; UC-002 | P0 | FEAT-004 | Day 6 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-069 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Refuse registration for a phone number already on an active account and offer the login path | Uniqueness check; refusal reason identifier; login-path response | Laravel | Service | FRD-FR-004 | UC-001; UC-002 | P0 | FEAT-004 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-070 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Assign each account a unique, persistent, never-reused identifier | External opaque id generation; uniqueness constraint; no reuse guarantee; negative test | Laravel | Model | FRD-FR-005; DB-022; DB-023; DB-026 | UC-001; UC-002 | P0 | FEAT-004 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-071 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Create the account in an unverified state that does not permit participation | Initial state; participation gate; account state referencing policy configuration | Laravel | Service | FRD-FR-006; DB-045 | UC-001; UC-002 | P0 | FEAT-004 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-072 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | API | Implement POST /verifications to initiate phone verification on account creation | Verification initiation; channel dispatch through port; recorded initiation | Laravel | Controller | FRD-FR-007; API 11.1 | UC-001; UC-002 | P0 | FEAT-004 | Day 7 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-073 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | API | Implement POST /verifications/{id}/attempts to submit a demonstration of control | Attempt submission; outcome recording; account marked usable only on success | Laravel | Controller | FRD-FR-008; FRD-FR-009; API 11.1 | UC-001; UC-002 | P0 | FEAT-004 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-074 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Security | Hold phone-verified status as backend state and reject any client assertion of it | Read-only exposure; write-path prohibition; assertion attempt recorded as integrity event | Laravel | Service | FRD-FR-009; API-125; DB-041; SADR-08 | UC-001; UC-002 | P0 | FEAT-004 | Day 7 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-075 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Permit a further verification attempt within the applied limits | Retry path; attempt counting against stored state; cool-off handling | Laravel | Service | FRD-FR-010; API-126 | UC-001; UC-002 | P0 | FEAT-004 | Day 8 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-076 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Cease accepting verification attempts once the attempt limit is reached | Limit enforcement; business refusal on exhaustion; recorded exhaustion | Laravel | Service | FRD-FR-011; SEC 5.2; NFR-057 | UC-001; UC-002 | P0 | FRD-OQ-003 | TBD | 5 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - attempt limit and cool-off period are unset (FRD-OQ-003, SEC 5.2). The obligation is buildable; the value is not.
CMP-IMP-077 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Preserve entered registration details for retry when the messaging channel is unavailable | Detail preservation; dependency-unavailable branch; resume path | Laravel | Service | FRD-FR-012; FRD-FR-255 | UC-001; UC-002 | P1 | FEAT-004 | Day 8 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-078 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Backend | Leave an abandoned registration unverified and permit restart with the same number | Abandonment handling; restart path; no orphan active account | Laravel | Service | FRD-FR-013 | UC-001; UC-002 | P0 | FEAT-004 | Day 8 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-079 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Integration | Implement the SMS/OTP provider port and one adapter | Provider-neutral port; capability result; plausibility check; bounds and recording | Laravel | Notification | BE-036; BADR-11; SADR-11 | UC-001; UC-002 | P0 | FEAT-004 | TBD | 10 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - the SMS/OTP provider is unselected (README 3.2, BAD-DEP series). The port is buildable; the adapter needs a provider.
CMP-IMP-080 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | UI | Build Screen 1 - Verification | Compose surface; code entry; attempt feedback; limit-reached treatment; channel-unavailable treatment | Android | UI | UX 4.1 Screen 1 | UC-001; UC-002 | P0 | FEAT-004 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-081 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Android | Implement the registration and verification state holder and client use cases | Immutable state; intents; use cases; refusal mapping; retained details on failure | Android | ViewModel | MOB-015; UXDR-04 | UC-001; UC-002 | P0 | FEAT-004 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-082 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | Verification | Testing | Write registration and verification tests | Unit validation and uniqueness; integration attempt limits against state; negative client assertion of verified status | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-001; UC-002 | P0 | FEAT-004 | Day 9 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-083 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | API | Implement GET /profile returning the authenticated user own profile | Application service; representation; provenance marking | Laravel | Controller | FRD-FR-022; API 11.2 | UC-005; UC-007 | P0 | FEAT-004 | Day 9 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-084 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | API | Implement PATCH /profile with validation retaining the previous profile on rejection | Validation; rejection reason; previous profile retained unchanged; reflected wherever displayed | Laravel | Controller | FRD-FR-024; FRD-FR-026; API-130 | UC-005; UC-007 | P0 | FEAT-004 | Day 9 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-085 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | Backend | Require phone verification before a changed phone number takes effect | Pending phone change; verification trigger; effect only on success | Laravel | Service | FRD-FR-025 | UC-005; UC-007 | P0 | FEAT-004 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-086 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | UX | Indicate on the profile which elements are disclosed to counterparties | Disclosure indicator surface; per-element marking | Android | UI | FRD-FR-023 | UC-005; UC-007 | P0 | FRD-GAP-001; BAD-DEC-022 | TBD | 5 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - the content of the disclosure list is blocked (FRD-GAP-001, BAD-DEC-022). The indicator mechanism is buildable; the list is not.
CMP-IMP-087 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | API | Implement GET /users/{id} as a relationship-limited counterparty representation | Relationship check; field limiting; no precise home location, contact details or trip history beyond the relationship | Laravel | Controller | FRD-FR-027; API-128; API-129; SEC 7.3; UXDR-08 | UC-005; UC-007 | P0 | FEAT-004 | Day 9 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-088 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | Backend | Retrieve counterparty verification standing from backend state on every display | No caching of standing; read at request time; provenance marking | Laravel | Service | FRD-FR-027; API-128; API-157 | UC-005; UC-007 | P0 | FEAT-004 | Day 9 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-089 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | UX | Present verification standing before the user commits to travel | Standing on ride detail and commitment surface; ordering guarantee | Android | UI | FRD-FR-028; UX 9.4 | UC-005; UC-007 | P0 | FEAT-004 | Day 10 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-090 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | Backend | Present standing as unknown, not as verified or unverified, when it cannot be retrieved | Third state; dependency-unavailable treatment; negative test | Laravel | Service | FRD-FR-029; UXDR-02 | UC-005; UC-007 | P0 | FEAT-004 | Day 10 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-091 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | UI | Build Screen 3 - Profile | Compose surface; view and amend; validation feedback; disclosure indicators | Android | UI | UX 4.1 Screen 3 | UC-005; UC-007 | P0 | FEAT-004 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-092 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | UI | Build Screen 19 - Counterparty profile | Compose surface; relationship-limited fields; verification standing including unknown; absence is normal | Android | UI | UX 4.1 Screen 19; UXDR-08 | UC-007 | P0 | FEAT-004 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-093 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | UI | Build Screen 4 - Home entry point | Structural entry surface; primary navigation; single-route reachability | Android | UI | UX 4.1 Screen 4; UX-010 | - | P0 | FEAT-004 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-094 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | Profile | Testing | Write profile and disclosure tests | Unit validation retention; integration relationship limiting; negative over-disclosure to a non-qualifying party | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-005; UC-007 | P0 | FEAT-004 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-095 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Security | Determine the roles held by an actor before permitting any action | Role resolution; evaluation before domain invocation; single evaluation path | Laravel | Authorization | FRD-FR-251; BE-044; SADR-06 | UC-008; UC-080 | P0 | FEAT-002; FEAT-004 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-096 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Security | Permit an action only where a role held by the actor allows it | Capability check; deny by default; allow-list evaluation | Laravel | Authorization | FRD-FR-252; SEC 7.1 | UC-008; UC-080 | P0 | FEAT-002; FEAT-004 | Day 8 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-097 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Security | Refuse an unpermitted action without partial application and record the refusal | Atomic refusal; no partial effect; refusal recorded as an evidential record | Laravel | Authorization | FRD-FR-253; BE-053; SADR-15 | UC-008; UC-080 | P0 | FEAT-002; FEAT-004 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-098 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Security | Distinguish user roles from administrative roles and restrict each independently | Two role spaces; independent restriction; no cross-grant | Laravel | Authorization | FRD-FR-254; SEC 7.2 | UC-008; UC-080 | P0 | FEAT-002; FEAT-004 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-099 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Security | Allow a user to take the driver role subject to business eligibility | Role assumption operation; eligibility evaluation; refusal stating what is outstanding | Laravel | Authorization | FRD-FR-030; FRD-FR-031 | UC-008; UC-080 | P0 | FRD-GAP-002; BAD-DEC-005 | TBD | 6 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - driver eligibility criteria are blocked (FRD-GAP-002, BAD-DEC-005).
CMP-IMP-100 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Security | Permit a single account to hold passenger and driver roles concurrently | Concurrent role holding; role-switch surface; no data duplication | Laravel | Authorization | FRD-FR-032 | UC-008; UC-080 | P0 | FEAT-002; FEAT-004 | Day 9 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-101 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | UI | Build Screen 31 - Settings including logout and driver-role controls | Compose surface; logout; role assumption entry; notification preference entry | Android | UI | UX 4.1 Screen 31 | UC-004; UC-008 | P0 | FEAT-002; FEAT-004 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-102 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | Authorisation | Testing | Write authorisation tests | Unit deny by default; integration refusal recording; negative privilege escalation attempt | Cross Platform | Validation | TC-029; TC-030; SEC 19.1; FR-04 | UC-008; UC-080 | P0 | FEAT-002; FEAT-004 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-103 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Database | Create the op_vehicles migration with platform-written lawful capacity | Table; capacity column with no inbound write path; protected documentation reference columns; no row delete where referenced | MySQL | Schema | DB-047; DB-048; DB-049; API-132 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 8 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-104 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Backend | Implement the Vehicle aggregate | Aggregate; valid-state construction; own invariants; domain events | Laravel | Model | BE-017; BE-019; BE-021 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-105 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | API | Implement POST /vehicles to register a vehicle against a driver account | Application service; required attribute validation; per-attribute refusal; external id issue | Laravel | Controller | FRD-FR-033; FRD-FR-034; FRD-FR-035; API 11.3 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 9 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-106 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Backend | Record the lawful passenger capacity of each registered vehicle | Capacity recording; platform authority; rejection of caller-supplied capacity; negative test | Laravel | Service | FRD-FR-036; API-132; DB-047 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - the source and evidencing of lawful capacity is blocked (FRD-GAP-004, BAD-DEC-005).
CMP-IMP-107 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | API | Permit a driver to register more than one vehicle, each independently selectable | Multi-vehicle listing; GET /vehicles; selection at publication | Laravel | Controller | FRD-FR-037; API 11.3 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 10 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-108 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Backend | Refuse a vehicle registration duplicating one on another account and raise it for operator review | Duplicate detection; refusal; operator case creation | Laravel | Service | FRD-FR-038 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - whether duplicate registration is ever permitted, and on what evidence, is open (FRD-OQ-004).
CMP-IMP-109 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | API | Implement PATCH /vehicles/{id} with an active-commitment determination before applying | Active ride, booking or trip check; accept non-invalidating amendment and reflect on ride; refuse invalidating amendment naming commitments | Laravel | Controller | FRD-FR-039; FRD-FR-040; FRD-FR-041; FRD-FR-042 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 10 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - which amendments are disqualifying is open (FRD-OQ-005).
CMP-IMP-110 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | API | Implement DELETE /vehicles/{id} as a state change refusing withdrawal in active use | Withdrawal as state change not delete; refusal naming active commitments; removal from new-ride selection | Laravel | Controller | FRD-FR-043; FRD-FR-044; FRD-FR-045; API-133; DB-048 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-111 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Backend | Present the vehicle information recorded against a ride, including on completed trips | Ride-time vehicle snapshot; historical presentation; pre-commitment presentation to passenger | Laravel | Service | FRD-FR-046; FRD-FR-047; FRD-FR-048 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 11 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-112 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | UI | Build Screen 5 - Vehicles: list, add, edit, withdraw | Compose surface; list; add form; edit form; withdraw with refusal treatment; empty state | Android | UI | UX 4.1 Screen 5 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 11 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-113 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Android | Implement the vehicle state holder, client use cases and repository | Immutable state; intents; gateway calls; cache handling; refusal mapping | Android | ViewModel | MOB-015; MADR-04; MADR-05 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-114 | EPIC-03 Supply | FEAT-008 Vehicle Management | Vehicles | Testing | Write vehicle management tests | Unit capacity authority; integration active-commitment refusal; negative caller-supplied capacity; negative withdrawal in active use | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-010; UC-011; UC-012 | P0 | FEAT-007 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-115 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Database | Create op_rides and op_ride_routes migrations with a spatially indexed bounding envelope | Ride table; route geometry stored once at publication; derived envelope; spatial index; ride state via policy configuration | MySQL | Schema | DB-051; DB-052; DB-057; DB-058; DADR-08 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-116 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Database | Create the op_ride_seat_allocations narrow row with its database constraint | Narrow lockable row; seats offered held here not on op_rides; CHECK constraint; independent lockability | MySQL | Schema | DB-050; DADR-05; DB 7; ARCH-053 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-117 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Implement the Ride aggregate owning SeatAllocation within its consistency boundary | Aggregate; ownership of SeatAllocation; invariants; domain events | Laravel | Model | BE-017; BE-018; BADR-02; BADR-04 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-118 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | API | Implement POST /rides to publish a ride with origin, destination, date and departure time | Application service; required fields; idempotency key; external id issue | Laravel | Controller | FRD-FR-049; FRD-FR-050; FRD-FR-054; API 11.4 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-119 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Integration | Resolve and record the route against which passenger segments are overlapped | Mapping port call outside the transaction; geometry storage; envelope derivation | Laravel | Service | FRD-FR-051; DB-051; DB-052; BE-050; BE-052 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-120 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Refuse publication where a route cannot be resolved and state that the journey was not understood | Business refusal branch; refusal reason identifier; no partial ride created | Laravel | Service | FRD-FR-052; AADR-14 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 11 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-121 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Defer publication rather than publish without a route when the mapping service is unavailable | Dependency-unavailable branch; deferral record; resume on restore | Laravel | Service | FRD-FR-053; API-136; FRD-FR-260 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-122 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Reject a ride whose departure time has already passed | Temporal validation against platform time; refusal reason | Laravel | Service | FRD-FR-055 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-123 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Require exactly one vehicle registered to the publishing driver and route drivers with none to registration | Vehicle association; ownership check; routing response when no vehicle exists | Laravel | Service | FRD-FR-056; FRD-FR-057 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-124 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Enforce that seats offered never exceed the vehicle recorded lawful capacity | Domain invariant on Ride; refusal stating the capacity; negative test | Laravel | Model | FRD-FR-058; FRD-FR-059; BE-023; API-134 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-125 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Validate the publishing driver eligibility before accepting a ride and state the refusal reason | Eligibility evaluation; refusal reason identifier | Laravel | Service | FRD-FR-064; FRD-FR-065 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Eligibility criteria depend on BAD-DEC-005 (FRD-GAP-002); the evaluation hook is buildable.
CMP-IMP-126 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Make an accepted ride discoverable to compatible searches | Discoverability flag; projection maintenance trigger; search candidacy | Laravel | Service | FRD-FR-066 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-127 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Record the publication of a ride as an auditable event | Evidential record written in the same transaction; actor, subject, time, outcome | Laravel | Service | FRD-FR-067; FRD-FR-244; BE-049 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-128 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Allow a driver to pre-fill a new ride from a previously published ride with full re-evaluation | Pre-fill source; full re-evaluation of time, capacity and eligibility; no inherited acceptance | Laravel | Service | FRD-FR-068 | UC-014; UC-016; UC-018 | P1 | FEAT-008; FEAT-032 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-129 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | API | Implement DELETE /rides/{id} to withdraw a ride carrying no confirmed booking | Withdrawal as state change; no-confirmed-booking precondition; ride not deletable | Laravel | Controller | FRD-FR-069; API-139; DB-056 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-130 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Refuse withdrawal of a ride carrying a confirmed booking | Bare refusal; refusal reason identifier; negative test; no alternative path offered | Laravel | Service | FRD-FR-070; API-139; DB-056 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | FRD-GAP-006 - the driver has no specified way out. Do not invent one. Blocked on BAD-DEC-009.
CMP-IMP-131 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Close any pending ride request on a withdrawn ride and inform its requester | Cascade closure of pending requests; notification issue; audit record | Laravel | Service | FRD-FR-071 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-132 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | API | Implement GET /rides presenting a driver published rides from backend state | Listing; date, time, route, seats offered, seats booked, status; provenance marking | Laravel | Controller | FRD-FR-072; API 11.4 | UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-133 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | API | Implement GET /rides/{id}/seats returning authoritative seat availability | Read from the allocation record never a projection; as-of marking; never cached | Laravel | Controller | ARCH-080; API-135; API-048; ADM-037 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-134 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Backend | Invalidate stored route geometry when a ride is amended | Amendment hook; geometry invalidation; re-resolution path | Laravel | Service | API-137; DB-055; ARCH-096 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-135 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | UI | Build Screen 7 - Publish ride | Compose surface; origin/destination entry; date and time; vehicle selection; seats; validation and refusal treatment | Android | UI | UX 4.1 Screen 7 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 13 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | PARTIAL screen - it cannot state the amount payable. Blocked on BAD-DEC-003 (FRD-GAP-005).
CMP-IMP-136 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | UI | Build Screen 6 - My published rides | Compose surface; listing; status; seats offered and booked; empty state; provenance marking | Android | UI | UX 4.1 Screen 6 | UC-018 | P0 | FEAT-008; FEAT-032 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-137 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | UI | Build Screen 9 - Ride detail, driver view | Compose surface; ride detail; withdrawal control; refusal treatment when confirmed bookings exist | Android | UI | UX 4.1 Screen 9 | UC-016 | P0 | FEAT-008; FEAT-032 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-138 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Android | Implement the ride publishing state holder, client use cases and repository | Immutable state; intents; gateway calls; deferral handling; refusal mapping | Android | ViewModel | MOB-015; MADR-04; UXDR-04 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 14 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-141 | EPIC-03 Supply | FEAT-009 Ride Publishing | Ride Publishing | Testing | Write ride publishing tests | Unit capacity invariant; integration route deferral; negative withdrawal with confirmed booking; negative past departure | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-014; UC-016; UC-018 | P0 | FEAT-008; FEAT-032 | Day 14 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-142 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | Database | Create the op_ride_preferences migration storing undeclared as undeclared | Table; tri-state per preference; no permissive or restrictive default | MySQL | Schema | DB-054; FRD-FR-062 | UC-015 | P0 | FEAT-009 | Day 11 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-143 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | Backend | Present the preference set for declaration on every published ride | Air conditioning, smoking, music, luggage, pets; declaration surface in the publish flow | Laravel | Service | FRD-FR-060 | UC-015 | P0 | FEAT-009 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-144 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | Backend | Record the driver declared position on each preference | Persistence; per-preference position; audit of declaration | Laravel | Service | FRD-FR-061 | UC-015 | P0 | FEAT-009 | Day 12 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-145 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | UX | Present an undeclared preference as undeclared and infer nothing | Tri-state rendering; no inference; negative test | Android | UI | FRD-FR-062 | UC-015 | P0 | FEAT-009 | Day 12 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-146 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | UX | Display declared preferences to a passenger before any commitment is sought | Ride detail and results rendering; ordering before commitment | Android | UI | FRD-FR-063; FRD-FR-092 | UC-015 | P0 | FEAT-009 | Day 12 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-147 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | UI | Build Screen 8 - Ride preferences | Compose surface; five preferences; tri-state controls; save and validation | Android | UI | UX 4.1 Screen 8 | UC-015 | P0 | FEAT-009 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-148 | EPIC-03 Supply | FEAT-010 Ride Preferences | Ride Preferences | Testing | Write ride preference tests | Unit tri-state persistence; negative default inference; UI rendering of undeclared | Cross Platform | Validation | TC-029; TC-030 | UC-015 | P0 | FEAT-009 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-149 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | API | Implement POST /searches as a query resource returning a ranked result set | Query resource not a filtered collection; request schema; ranked response; no cached result set | Laravel | Controller | AADR-10; API-140; API-143; FRD-FR-073 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-150 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Integration | Resolve the requested travel segment from the stated origin and destination | Places or geocoding port call; segment construction; capability result on failure | Laravel | Service | FRD-FR-074 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-151 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Refuse a search where an origin or destination cannot be resolved | Business refusal; refusal reason stating the location was not understood | Laravel | Service | FRD-FR-075 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 7 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-152 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Identify published rides that are candidates for the requested date | Date candidacy query; index-supported access path | Laravel | Query | FRD-FR-076; DB 14.2 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 7 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-153 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Implement the route-overlap assessment as a domain service | Domain service not an aggregate method; expressed independently of any corridor, city or region; unit-testable without a database | Laravel | Domain | BE-034; BE-035; BE-040; ADR-03 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 8 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | TECHNICAL DECISION REQUIRED - the overlap algorithm and any minimum overlap threshold are deliberately unspecified (BAD-RULE-023, FRD-RISK-008). Route this as a named decision before implementing.
CMP-IMP-154 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Include a ride only where its route overlaps the requested segment | Overlap predicate; integrity-critical rule; negative test proving non-overlapping rides are excluded | Laravel | Domain | FRD-FR-077 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-155 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Include a ride whose route overlaps the segment even where the segment is only part of the route | Partial-segment matching; the differentiating capability; positive and negative tests | Laravel | Domain | FRD-FR-078; BAD-OPP-001 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-156 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Implement the two-phase filter: coarse spatial index then precise geometry | Spatial index coarse filter; full geometry read only for survivors; measurement of survivor count | Laravel | Query | DB-053; ARCH-081; DADR-08 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 9 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-157 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Assess pickup compatibility between the passenger origin and the ride route | Pickup relationship computation; expressible result | Laravel | Domain | FRD-FR-079 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-158 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Assess drop compatibility between the passenger destination and the ride route | Drop relationship computation; expressible result | Laravel | Domain | FRD-FR-080 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-159 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Assess whether the ride direction of travel is compatible with the requested journey | Direction predicate; reverse-direction exclusion; negative test | Laravel | Domain | FRD-FR-081 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-160 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Assess whether the ride departure time is compatible with the requested travel time | Time window predicate; window value as configuration | Laravel | Domain | FRD-FR-082 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-161 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Exclude from bookable results any ride with fewer available seats than requested | Seat predicate in the candidate filter; explicit statement of the exclusion; negative test | Laravel | Domain | FRD-FR-083; GAP-020 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | GAP-020 - no downstream statement carries this exclusion into the coarse filter. Record the criterion explicitly rather than inheriting it from a decision record prose.
CMP-IMP-162 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Evaluate seat availability from backend state on every search, never from a cached count | Authoritative read per search; no projection read; as-of marking; negative test | Laravel | Service | FRD-FR-084; ADM-037; API-135 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-163 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Present a ride as compatible only where every compatibility assessment is satisfied | Composite predicate; short-circuit ordering; test matrix across all six assessments | Laravel | Domain | FRD-FR-085 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-164 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Rank compatible rides on a basis the platform can express to the passenger | Ranking function; expressibility constraint; stable ordering | Laravel | Domain | FRD-FR-086 | UC-019; UC-020; UC-021 | P1 | FEAT-009 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-165 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Express, for each result, the degree of route overlap with the requested segment | Overlap degree computation; journey-terms expression; no unexplained score | Laravel | Service | FRD-FR-087; UXDR-09; API-142 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-166 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | UX | Express the pickup and drop relationship in terms the passenger can act on | Actionable phrasing; no raw distances without meaning; content review | Laravel | Service | FRD-FR-088; NFR-085; UXDR-09 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 11 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-167 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Re-evaluate results in full when a search is repeated | No result-set caching; full re-run; negative test against a stale result set | Laravel | Service | FRD-FR-093; API-143 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 11 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-168 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | Return a successful empty result rather than a refusal when no candidate matches | Empty result semantics; distinct from refusal; measurement of zero-result searches | Laravel | Service | API-144; ARCH-081; FRD-FR-235 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 11 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Behaviour on an empty result set - whether alternatives are offered and which - is withheld (BAD-OQ-007, UC-022). Return empty; offer nothing.
CMP-IMP-169 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Backend | State that search is unavailable rather than return an unmatched or unranked result set | Dependency-unavailable branch when mapping is unavailable; capability withdrawal; negative test | Laravel | Service | FRD-FR-096; FRD-FR-256; FRD-FR-259 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 11 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-170 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | UI | Build Screen 10 - Search | Compose surface; origin and destination entry; date; seats; validation; unresolvable-location treatment | Android | UI | UX 4.1 Screen 10 | UC-019 | P0 | FEAT-009 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-171 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | UI | Build Screen 11 - Results | Compose surface; result cards; match quality; empty, loading and failed states; unavailable-search treatment | Android | UI | UX 4.1 Screen 11; UX 10 | UC-020 | P0 | FEAT-009 | Day 12 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-172 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Android | Implement the search state holder, client use cases and repository | Immutable state; intents; gateway calls; no client-side filtering or ranking; refusal mapping | Android | ViewModel | MOB-015; MOB-010; MADR-04 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 12 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-173 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | Search & Matching | Testing | Write search and matching tests | Unit overlap predicate matrix; integration two-phase filter; negative non-overlapping inclusion; negative cached availability | Cross Platform | Validation | TC-029; TC-030; FR-04; FR-06 | UC-019; UC-020; UC-021 | P0 | FEAT-009 | Day 12 | 16 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-174 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | Backend | Present, for each result, the fare, departure time and number of available seats | Result representation fields; as-of marking on each business value | Laravel | Service | FRD-FR-089; AADR-09 | UC-021 | P0 | FEAT-011 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-175 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | Backend | Present, for each result, the driver information and verification indicators required for a trust decision | Trust field set; relationship-limited; no more than the decision requires | Laravel | Service | FRD-FR-090; API-141; API-049 | UC-021 | P0 | FEAT-011 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-176 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | Backend | Present, for each result, the vehicle information recorded against the ride | Vehicle snapshot fields; pre-commitment presentation | Laravel | Service | FRD-FR-091; FRD-FR-047 | UC-021 | P0 | FEAT-011 | Day 12 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-177 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | Backend | Re-check availability when a passenger proceeds from a result | Authoritative re-read; inform when no longer bookable; return to results | Laravel | Service | FRD-FR-094 | UC-021 | P0 | FEAT-011 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-178 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | Backend | Inform a passenger and return them to results where a ride is withdrawn while viewing | Withdrawal detection; message; navigation back to results | Laravel | Service | FRD-FR-095 | UC-021 | P0 | FEAT-011 | Day 13 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-179 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | API | Implement GET /rides/{id} as a relationship-limited ride representation | Relationship-varying representation; disclosure limits; as-of markings | Laravel | Controller | API 11.4; AADR-08; API-051 | UC-021 | P0 | FEAT-011 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-180 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | UI | Build Screen 12 - Ride detail, passenger view | Compose surface; ride, driver, vehicle, preferences; verification standing; seat availability with provenance | Android | UI | UX 4.1 Screen 12 | UC-021 | P0 | FEAT-011 | Day 13 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-181 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | UI | Build Screen 13 - Commitment surface | Compose surface; single gated commitment point; everything the passenger must see before committing; refusal at commitment; refresh failure treatment | Android | UI | UX 4.1 Screen 13; UXDR-06; UX 9 | UC-021 | P0 | FEAT-011 | Day 13 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | PARTIAL screen - it cannot state whether a request requires driver acceptance (BAD-DEC-007) nor the fare composition (BAD-DEC-003).
CMP-IMP-182 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | UX | Apply disclosure rules at the commitment surface | What each party sees at commitment; relationship-based disclosure | Android | UI | UX 9.4; UXDR-08 | UC-021 | P0 | FRD-GAP-008; BAD-DEC-022 | TBD | 5 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - the precision of counterparty location disclosed before a booking exists is blocked (FRD-GAP-008, BAD-DEC-022).
CMP-IMP-183 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | Ride Detail | Testing | Write ride detail and commitment tests | Integration availability re-check; negative withdrawn-ride handling; contract representation shape | Cross Platform | Validation | TC-030; TC-031 | UC-021 | P0 | FEAT-011 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-184 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Database | Create the op_ride_requests migration with state referencing policy configuration | Table; request state via cfg_ not a database ENUM; requester and seats requested; hold expiry column left unused | MySQL | Schema | DB-061; DB-062; DB-039 | UC-023 | P0 | FEAT-012 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-185 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Backend | Implement the RideRequest aggregate | Aggregate; valid-state construction; own invariants; domain events | Laravel | Model | BE-017; BE-019; BE-021 | UC-023 | P0 | FEAT-012 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-186 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | API | Implement POST /ride-requests to request a stated number of seats on a ride | Application service; idempotency key; request record against the ride; external id issue | Laravel | Controller | FRD-FR-097; FRD-FR-100; API 11.6 | UC-023 | P0 | FEAT-012 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-187 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Backend | Re-confirm seat availability from backend state at the moment a request is made | Authoritative read at request time; no cached count; negative test | Laravel | Service | FRD-FR-098 | UC-023 | P0 | FEAT-012 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-188 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Backend | Decline a request where seats are no longer available, state why, and consume no seat | Business refusal; no seat consumption; verification that allocation is unchanged | Laravel | Service | FRD-FR-099 | UC-023 | P0 | FEAT-012 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-189 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Backend | Present the requesting passenger verification standing to the driver | Standing read at display time; driver-facing representation | Laravel | Service | FRD-FR-101; API-146 | UC-023 | P0 | FEAT-012 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-190 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Backend | Refuse a request from a passenger who is not eligible to request and state the reason | Eligibility evaluation; refusal reason identifier | Laravel | Service | FRD-FR-102 | UC-023 | P0 | FEAT-012 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-191 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Backend | Inform both the passenger and the driver of the outcome of a ride request | Notification issue to both parties; category assignment; record | Laravel | Service | FRD-FR-103; FRD-FR-197 | UC-023 | P0 | FEAT-012 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-192 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | API | Implement GET /ride-requests for own requests and requests on own rides | Two-perspective listing; cursor paging; relationship-limited representation | Laravel | Controller | API 11.6 | UC-023 | P0 | FEAT-012 | Day 14 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-193 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | API | Implement DELETE /ride-requests/{id} to allow a passenger to withdraw a request | Withdrawal; state change; notification to driver; audit record | Laravel | Controller | API 11.6 | UC-023 | P0 | FEAT-012 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-194 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | UI | Build Screen 14 - Request seats | Compose surface; seat count; confirmation; refusal treatment; outcome presentation | Android | UI | UX 4.1 Screen 14 | UC-023 | P0 | FEAT-012 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | PARTIAL screen - it cannot state whether a request requires driver acceptance (BAD-DEC-007, FRD-GAP-009).
CMP-IMP-195 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | UI | Build the requests-on-ride view within Screen 9 | Compose section; requester standing; accept and decline entry points; empty state | Android | UI | UX 4.1 Screen 9 | UC-023 | P0 | FEAT-012 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Accept and decline controls depend on BAD-DEC-007. Build the listing; withhold controls the platform cannot honour (FRD-FR-195, UX-006).
CMP-IMP-199 | EPIC-05 Transaction | FEAT-013 Ride Request | Ride Requests | Testing | Write ride request tests | Unit eligibility refusal; integration availability re-confirmation; negative seat consumption on decline | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-023 | P0 | FEAT-012 | Day 15 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-200 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Database | Create the op_bookings migration carrying the platform-computed fare and payment reference | Table; fare column with no caller-supplied write path; payment reference making the confirmation rule checkable; state via policy configuration; interface version column | MySQL | Schema | DB-059; DB-060; DB-061; DB-063 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-201 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Implement the Booking aggregate with the confirmed-requires-verified-payment invariant | Aggregate; invariant in Domain; not reachable for override; negative test | Laravel | Model | BE-025; BE-012; BAD-RULE-028; FRD-FR-106 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 14 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-202 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Implement the SeatAllocation invariant that confirmed seats never exceed seats offered | Invariant on the allocation record; database CHECK constraint as second line; negative test | Laravel | Model | BE-024; FRD-FR-107; DB 7; BAD-RULE-027 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 14 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-203 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Implement pessimistic row locking on the allocation record plus the database constraint | SELECT FOR UPDATE on the narrow row; constraint backstop; deadlock handling; lock scope narrowest possible | Laravel | Repository | BADR-04; DADR-05; BE-054; ARCH-053 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 14 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-204 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | API | Implement POST /bookings creating a booking in pending state | Application service; pending creation; never reported confirmed until payment verified; idempotency key | Laravel | Controller | API-148; FRD-FR-105; AADR-07 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-205 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Determine seat availability solely from platform state and reject any client-supplied seat count | Client value rejection; whole-request rejection; integrity event recorded; negative test | Laravel | Service | FRD-FR-104; FRD-FR-238; FRD-FR-239; FRD-FR-240 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-206 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Confirm a booking only where seats remain available at the moment of confirmation | Confirmation-time re-check under lock; refusal branch; negative test under concurrency | Laravel | Service | FRD-FR-105; API-149; BE-056 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-207 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Confirm a booking only where payment status is verified | Payment status precondition; no confirmation on pending or failed; negative test | Laravel | Service | FRD-FR-106; BE-025; API-145 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-208 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Refuse confirmation where seats became unavailable and initiate the return of any value taken | Refusal; seat release; initiation record for the return of value | Laravel | Service | FRD-FR-108; PAY 13.2 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | The return of value itself is BLOCKED (FRD-GAP-014, GAP-009, BAD-DEC-010). Record the initiation; do not invent the refund.
CMP-IMP-209 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Do not confirm, and release any held seats, where payment is not verified | Seat release path; allocation restoration; audit record | Laravel | Service | FRD-FR-109 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-210 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Security | Reject any client assertion that a booking is confirmed | Assertion rejection; whole-request refusal; integrity event; negative test | Laravel | Service | FRD-FR-110; FRD-FR-238 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-211 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Allocate the requested seats to a confirmed booking | Allocation write under lock; totals maintained; invariant re-checked | Laravel | Service | FRD-FR-111 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-212 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Commit seat allocation, booking confirmation, ledger entry and payment status change in one transaction | Single transaction scope; no provider call inside; evidential record in the same commit; partial-effect impossibility test | Laravel | Service | BE-048; BE-049; BE-050; BE-053; SRS-REQ-040; SRS-REQ-041 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-213 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Record the confirmation of a booking as an auditable event | Evidential record; actor, subject, time, outcome; same-transaction write | Laravel | Service | FRD-FR-112; FRD-FR-244; FRD-FR-245 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-214 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Inform both the passenger and the driver when a booking is confirmed | Notification issue to both; booking category; record | Laravel | Service | FRD-FR-113; FRD-FR-197 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-215 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | API | Implement GET /bookings presenting bookings from backend state | Listing with ride, seats, status, payment status and associated trip; cursor paging; as-of markings | Laravel | Controller | FRD-FR-114; API 11.7 | UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-216 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Android | Mark bookings shown from device-held data as cached and non-authoritative | Cache provenance treatment; booking and payment status never presented as authoritative from cache | Android | Data | FRD-FR-115; UXDR-02; UX 6 | UC-025; UC-029 | P1 | FEAT-013; FEAT-016 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-217 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Backend | Record every cancellation with the responsible party and the reason | Cancellation record; party and reason; no monetary effect recorded | Laravel | Service | FRD-FR-116; DB-064 | UC-025; UC-029 | P1 | FEAT-013; FEAT-016 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Build the record now; the consequence is undecided (FRD-GAP-012, BAD-DEC-009). Recording costs nothing and makes the eventual policy enforceable retrospectively (FRD-ASM-004).
CMP-IMP-218 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | UI | Build Screen 17 - My bookings and Screen 18 - Booking detail | Compose surfaces; listing; detail; pending state; provenance marking; empty state | Android | UI | UX 4.1 Screens 17, 18 | UC-029 | P1 | FEAT-013; FEAT-016 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-219 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | UI | Build Screen 8 state - Booking pending | Pending presentation; submission state on the affected object; no success claim while pending | Android | UI | UXDR-14; UX 11 | UC-025; UC-029 | P1 | FEAT-013; FEAT-016 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-220 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Testing | Write concurrency tests proving overbooking is impossible under genuine parallelism | Parallel confirmation attempts; allocation invariant assertion; database constraint assertion; repeat runs | Cross Platform | Validation | TADR-08; TC 12.1; BE-024; NFR-028 | UC-025; UC-029 | P0 | FEAT-013; FEAT-016 | Day 15 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-221 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | Bookings | Testing | Write booking integrity tests | Negative confirmation without verified payment; negative client-asserted confirmation; integration single-transaction atomicity | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-025; UC-029 | P1 | FEAT-013; FEAT-016 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-222 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Calculate the amount payable under platform authority alone | Fare computation inside the Domain; never accepted from an inbound value; negative test | Laravel | Domain | FRD-FR-117; BE-032; ARCH-083; BAD-RULE-034 | UC-030; UC-031 | P0 | FEAT-014 | Day 9 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-223 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Security | Reject any client-supplied amount payable | Whole-request rejection; integrity event recorded; negative test | Laravel | Service | FRD-FR-118; API-150; FRD-FR-238; FRD-FR-239 | UC-030; UC-031 | P0 | FEAT-014 | Day 9 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-224 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Present the total amount payable to the passenger before any payment is initiated | Amount presentation on the commitment surface; as-of marking; ordering guarantee | Laravel | Service | FRD-FR-119; UX 9.1 | UC-030; UC-031 | P0 | FEAT-014 | Day 10 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-225 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Do not initiate a payment for an amount the passenger has not been shown | Shown-amount binding; refusal when unbound; negative test | Laravel | Service | FRD-FR-120 | UC-030; UC-031 | P0 | FEAT-014 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-226 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Re-present the total and require the passenger to see it where the amount changes | Change detection between display and payment; forced re-display; no silent substitution | Laravel | Service | FRD-FR-121 | UC-030; UC-031 | P0 | FEAT-014 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-227 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Freeze the fare before the handoff | Fare freeze at initiation; frozen value carried into verification; no recomputation mid-flow | Laravel | Service | PADR-01; PAY 5 | UC-030; UC-031 | P0 | FEAT-014 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-228 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | API | Implement POST /bookings/{id}/payments to initiate payment for the established amount | Application service; idempotency key; provider port call outside the transaction; payment record creation | Laravel | Controller | FRD-FR-122; API 11.8; BE-050; BE-052 | UC-030; UC-031 | P0 | FEAT-014 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-229 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Implement the UPI handoff on the client | UPI intent construction; handoff to the payment application; return handling; no instrument surface | Android | Data | FRD-FR-123; PADR-02; MOB 8.3 | UC-030; UC-031 | P0 | FEAT-014 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-230 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Security | Discard the response returned by the client-side UPI application | Response discarded not distrusted; never treated as evidence; negative test asserting no state change from it | Laravel | Service | FRD-FR-124; PADR-03; API-154; BAD-RULE-032 | UC-030; UC-031 | P0 | FEAT-014 | Day 11 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-231 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Security | Ensure no payment instrument surface exists anywhere in the system | No instrument field on any screen, endpoint, column or log; static check; schema inspection | Cross Platform | Validation | PADR-08; DB-037; DB-068; SEC 12; API-053 | UC-030; UC-031 | P0 | FEAT-014 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-232 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Payment | Refuse to start a payment the platform cannot verify when the ecosystem is unavailable | Dependency-unavailable branch; refusal not optimistic start; negative test | Laravel | Service | FRD-FR-137; PADR-12; FRD-FR-259 | UC-030; UC-031 | P0 | FEAT-014 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-233 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | UI | Build Screen 15 - Payment handoff | Compose surface; amount presentation; handoff trigger; return path; always returns to pending | Android | UI | UX 4.1 Screen 15; UXDR-10; UX 11.1 | UC-031 | P0 | FEAT-014 | Day 12 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-235 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | Payment Initiation | Testing | Write fare and initiation tests | Negative client-supplied amount; negative payment for an unshown amount; integration fare freeze; contract branch shapes | Cross Platform | Validation | TC-029; TC-030; TC-031; FR-04 | UC-030; UC-031 | P0 | FEAT-014 | Day 12 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-236 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Database | Create op_payments and op_payment_attempts migrations with a three-value CHECK constraint | Tables; verified/failed/pending CHECK; no inbound write path from the interface; attempt rows never updated to hide a prior attempt; provider reference stored | MySQL | Schema | DB-065; DB-066; DB-067; DB-069; DB-070 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-237 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Implement the Payment aggregate permitting exactly three states and no fourth | Aggregate; three states; no sub-states; leaving pending only by verification or recorded reconciliation; negative test | Laravel | Domain | BE-026; BE-027; PADR-07; SRS-REQ-155; SRS-REQ-156 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 12 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-238 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Initiate independent verification of every payment attempt including abandoned ones | Verification job enqueued unconditionally; abandonment covered; no dependence on passenger return | Laravel | Queue | FRD-FR-125; FRD-FR-126; PADR-04 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 12 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-239 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Implement the payment-verification job family | Job family binding; retry with configured backoff; idempotent execution; failed state visible | Laravel | Queue | BE-131; BE-135; BE-137; BE-139 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 12 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-240 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Determine payment status solely from platform verification | Status derivation from own verification only; provider-reported outcome not authoritative; negative test | Laravel | Service | FRD-FR-127; FRD-FR-128; PADR-04 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-241 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Set payment status to failed on established failure and release any held seats | Failed transition; seat release; allocation restoration; audit record | Laravel | Service | FRD-FR-129 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-242 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Set payment status to pending and route for reconciliation where the outcome cannot be established | Pending transition; reconciliation queue entry; never assume in either direction | Laravel | Service | FRD-FR-130; FRD-FR-131; FRD-FR-258; PADR-06 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-243 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Re-attempt verification of a pending payment on platform initiative | Scheduled reconciliation job; re-verification; no timeout resolution; pending never times out | Laravel | Queue | FRD-FR-132; BE-145; PADR-06 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-244 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Record every payment attempt and its verified outcome | Attempt rows; outcome recording; append-only attempt history; inspection view | Laravel | Service | FRD-FR-134; DB-067 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-245 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Inform the passenger of the verified outcome and never of the outcome reported by the UPI application | Outcome messaging; provider outcome suppressed; negative test | Laravel | Service | FRD-FR-135; API-156 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 13 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-246 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | UX | Inform a passenger that a payment is being confirmed and report no success while pending | Pending presentation; no success claim; UXDR-10 conformance | Android | UI | FRD-FR-136; UXDR-10 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-247 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Integration | Implement the provider-neutral payment port and one adapter | Port contract in Domain; capability result semantics; plausibility check; bounds and recording of provider calls | Laravel | Service | PADR-10; BE-036; PAY 9; SADR-11 | UC-031; UC-032; UC-033 | P0 | BAD-DEP-004 | TBD | 12 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - the PSP is unselected (BAD-DEP-004). The port is buildable; the adapter needs a provider. Seven selection gates are stated in PAY 14.1.
CMP-IMP-248 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Security | Implement the provider callback surface as a trigger that enqueues verification and nothing else | Callback endpoint; enqueue only; never treated as verification; signature handling; negative test | Laravel | Controller | PADR-09; AADR-12; API 13 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 14 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-249 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Security | Ensure payment status is never settable through the interface | Field absent from every schema; write-path prohibition; static and contract check | Laravel | Service | API-153; DB-066; AADR-06; BAD-RULE-033 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-250 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Payment | Ensure payment verification outcomes are never cached | No-cache rule at gateway and client; authoritative read every time; negative test | Laravel | Service | API-157; ARCH-126 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-251 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | UI | Build Screen 16 - Payment status | Compose surface; verified, failed and pending treatments; no success claim while pending; retry entry point | Android | UI | UX 4.1 Screen 16 | UC-032 | P0 | FEAT-015; FEAT-017 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-252 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | Payment Verification | Testing | Write payment integrity tests | Negative provider response accepted as evidence; negative pending resolved by assumption; negative status set through the interface; integration verification without passenger return | Cross Platform | Validation | TC-029; TC-030; FR-03; FR-04; PAY 16 | UC-031; UC-032; UC-033 | P0 | FEAT-015; FEAT-017 | Day 14 | 16 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-253 | EPIC-05 Transaction | FEAT-017 Ledger | Ledger | Backend | Create the led_ledger_entries append-only migration | Table in led_ domain; append-only enforcement; no update path; exact decimal money | MySQL | Schema | DB-005; DB 8; DADR-07; DB-031 | UC-032 | P0 | FEAT-003 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-254 | EPIC-05 Transaction | FEAT-017 Ledger | Ledger | Payment | Record a ledger entry for every movement of value | Entry per movement attributable to payer, booking and event; written in the booking transaction | Laravel | Service | FRD-FR-133; BE-048; ARCH-112 | UC-032 | P0 | FEAT-003 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-255 | EPIC-05 Transaction | FEAT-017 Ledger | Ledger | Payment | Produce balanced entries immediately on every verified payment | Double-entry in effect; balance assertion at write time; negative test on unbalanced write | Laravel | Service | PADR-11; DADR-07 | UC-032 | P0 | FEAT-003 | Day 13 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-256 | EPIC-05 Transaction | FEAT-017 Ledger | Ledger | Backend | Compute balances rather than store them | No stored balance column; computation query; index support | MySQL | Query | DADR-06; DB-031 | UC-032 | P0 | FEAT-003 | Day 13 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-257 | EPIC-05 Transaction | FEAT-017 Ledger | Ledger | Payment | Surface a discrepancy where a ledger does not reconcile rather than present a concealing balance | Reconciliation check; discrepancy surfacing; routing to the reconciliation queue | Laravel | Service | FRD-FR-222; FRD-FR-223 | UC-032 | P0 | FEAT-003 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-259 | EPIC-05 Transaction | FEAT-017 Ledger | Ledger | Testing | Write ledger tests | Unit balance computation; integration same-transaction entry; negative unbalanced entry; negative update of an entry | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-032 | P0 | FEAT-003 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-260 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Database | Create op_trips and op_trip_participants migrations capturing values not references alone | Tables; captured participants, route as travelled, fare and payment outcome; booking references making the start rule checkable; state via policy configuration | MySQL | Schema | DB-071; DB-072; DB-075; DADR-11 | UC-038; UC-042 | P0 | FEAT-014 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-261 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Implement the Trip aggregate with the start-requires-confirmed-booking invariant | Aggregate; invariant in Domain; not reachable for override; negative test | Laravel | Domain | BE-028; BE-012; SRS-REQ-159; FRD-FR-142 | UC-038; UC-042 | P0 | FEAT-014 | Day 15 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-262 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | API | Implement POST /trips/{id}/start allowing a driver to begin a trip | Application service; idempotency key; confirmed-booking precondition; trip creation and start time record | Laravel | Controller | FRD-FR-141; FRD-FR-143; API-159; API 11.9 | UC-038; UC-042 | P0 | FEAT-014 | Day 15 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-263 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Refuse to begin a trip against a ride with no confirmed booking | Business refusal; refusal reason; negative test | Laravel | Service | FRD-FR-142; BE-028 | UC-038; UC-042 | P0 | FEAT-014 | Day 15 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-264 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Record every trip state transition with the time at which it occurred | Transition log; evidential record; inspection view | Laravel | Service | FRD-FR-144; FRD-FR-244 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-265 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Make the current trip state visible to every participant | Participant-scoped state read; as-of marking; client rendering | Laravel | Service | FRD-FR-145 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-266 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Notify booked passengers when a trip begins | Notification issue; trip category; record | Laravel | Service | FRD-FR-146; FRD-FR-197 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-267 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Record the actual start time of a trip against its scheduled departure time | Both instants recorded; variance derivable; inspection view | Laravel | Service | FRD-FR-147 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-268 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | API | Implement POST /trips/{id}/completion closing a trip and recording each booking outcome independently | Completion service; per-booking outcome; captured values written | Laravel | Controller | FRD-FR-165; FRD-FR-166; API 11.9 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-269 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Backend | Do not report a trip as complete where its record cannot be written | Write-then-report ordering; failure branch; reconciliation raise; negative test | Laravel | Service | FRD-FR-167; FRD-FR-248; FRD-FR-249 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-270 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | UI | Build Screen 22 - Active trip, driver view | Compose surface; trip state; start and complete controls; next point; position age visible | Android | UI | UX 4.1 Screen 22; UX-009 | UC-042 | P0 | FEAT-014 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-273 | EPIC-06 Journey | FEAT-018 Trip Execution | Trips | Testing | Write trip execution tests | Negative start without confirmed booking; integration completion capture; negative completion reported without a written record | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-038; UC-042 | P0 | FEAT-014 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-274 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | Database | Create the op_trip_positions migration carrying two distinct instants | Separate table for independent removal; instant of acquisition distinct from instant of receipt; index for latest-position access | MySQL | Schema | DB-073; DB-074; GADR-03 | UC-039 | P0 | FEAT-018 | Day 15 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-275 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Implement the trip-bound foreground location service on the client | Foreground service bound to the trip; disclosure notification; start and stop with the trip; no user-level tracking | Android | Data | MADR-07; GADR-01; GADR-04; GPS 5.1 | UC-039 | P0 | FEAT-018 | Post-MVP | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-276 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | Android | Implement location permission coordination | Permission request flow; rationale; denial handling; degraded operation without permission | Android | UI | MOB 8.2; FRD-FR-152 | UC-039 | P0 | FEAT-018 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-277 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Obtain the vehicle position during an active trip and report it | Position acquisition; POST /trips/{id}/positions; reported by the vehicle not every participant; batching under intermittent connectivity | Cross Platform | Service | FRD-FR-148; ARCH-093; GADR-02 | UC-039 | P0 | FEAT-018 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-278 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | Configuration | Take the position reporting cadence from platform-delivered configuration | Cadence from GET /configuration; client never chooses; adjustable without a client release | Cross Platform | Service | GADR-06; API-162; MOB-135; OPS-118 | UC-039 | P0 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-279 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Validate and accept reported positions | Acceptance rules; participant, trip and time scoping; rejection of out-of-scope reports | Cross Platform | Service | GPS 6.2; GADR-11 | UC-039 | P0 | FEAT-018 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-280 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | API | Implement GET /trips/{id}/positions/latest scoped to participants of the active trip | Participant-scoped read; time-scoped access; as-of marking | Laravel | Controller | FRD-FR-149; GADR-11; API 11.9 | UC-039 | P0 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-281 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Never present a previously known position as the current position | Staleness bound per position against a delivered bound; expiry treatment; negative test | Cross Platform | Service | FRD-FR-150; API-161; GADR-05 | UC-039 | P0 | FEAT-018 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-282 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | UX | Indicate that position is unavailable and when it was last known | Unavailable treatment; last-known instant shown; no extrapolation | Android | UI | FRD-FR-151; GADR-07 | UC-039 | P0 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Open question - what the passenger sees when the driver becomes unreachable mid-trip is unresolved (FRD-OQ-009).
CMP-IMP-283 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Permit a trip to begin indicating that tracking is unavailable | Tracking as enhancement not precondition; start path without position; indication to participants | Cross Platform | Service | FRD-FR-152; GADR-08 | UC-039 | P0 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-284 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Continue to report position without map context where the mapping service is unavailable | Degraded presentation; position path unaffected; dependency-unavailable marking | Cross Platform | Service | FRD-FR-153; GADR-13 | UC-039 | P1 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-285 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | GPS | Cease position tracking when a trip ends | Service stop; foreground notification removal; verification that no position is acquired after end | Cross Platform | Service | FRD-FR-154 | UC-039 | P0 | FEAT-018 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-286 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | UI | Build Screen 21 - Active trip, passenger view with position age always visible | Compose surface; map or position; age of position; unavailable treatment; safety centre reachable | Android | UI | UX 4.1 Screen 21; UXDR-11; UX-009; UX-011 | UC-039; UC-040 | P0 | FEAT-018 | Post-MVP | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-287 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | Security | Apply position privacy scoping and retention marking | Participant, trip and time scoping; separate table for independent removal; retention marking | Laravel | Service | GPS 10; DB-073; DB-179 | UC-039 | P0 | BAD-DEC-021 | TBD | 8 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - position retention period is unset (BAD-DEC-021, FRD-RISK-007). Location history accumulates without bound until it is set.
CMP-IMP-288 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS Tracking | Testing | Write live tracking tests | Negative stale position presented as current; integration cadence from configuration; negative position acquired after trip end; participant scoping | Cross Platform | Validation | TC-029; TC-030; FR-04; GPS 14 | UC-039 | P0 | FEAT-018 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-289 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Compute an estimated time of arrival at each participant next relevant point | ETA computation; per-participant next point; mapping port call; update on progress | Laravel | Service | FRD-FR-155; FRD-FR-157 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-290 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Compute the remaining distance to each participant next relevant point | Distance computation; per-participant; update on progress | Laravel | Service | FRD-FR-156; FRD-FR-157 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-291 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | State that no estimate is available rather than present a stale or default value | No-estimate treatment; no extrapolation; negative test against a default value | Laravel | Service | FRD-FR-158; GADR-07 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-292 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Present a driver with the estimate to their next pickup or drop rather than their own destination | Driver-perspective estimate; next-point selection | Laravel | Service | FRD-FR-159; GADR-10 | UC-040; UC-044 | P1 | FEAT-019 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | BLOCKED in part - pickup and drop sequencing on a multi-passenger trip is undecided (GAP-017, GPS 12.4). FRD-FR-159 is unimplementable for a multi-passenger trip until it is decided.
CMP-IMP-293 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Associate every confirmed booking on a ride with the same trip | One trip per ride; booking association; participant records | Laravel | Service | FRD-FR-161 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-294 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Track each booking pickup and drop independently on a multi-passenger trip | Per-booking journey state; independent progression; GADR-09 conformance | Laravel | Service | FRD-FR-162; GADR-09 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-295 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | UX | Present each passenger with the trip from the perspective of their own pickup and drop points | Per-passenger view composition; no disclosure of other passengers beyond the relationship | Android | UI | FRD-FR-163; UXDR-08 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-296 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Ensure one passenger cancellation or absence does not invalidate another booking on the same trip | Independence invariant; negative test with a cancelled co-passenger | Laravel | Domain | FRD-FR-164 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-297 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | UI | Build Screen 23 - Multi-passenger trip | Compose surface; per-booking journeys; own perspective; co-traveller disclosure limits | Android | UI | UX 4.1 Screen 23 | UC-044 | P0 | FEAT-019 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-298 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | GPS | Provide current speed, current landmark and the next navigation instruction during an active trip | Telemetry fields; navigation instruction source; presentation | Laravel | Service | FRD-FR-160 | UC-040; UC-044 | P2 | FEAT-019 | Post-MVP | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Release R2 by FRD-FR-160. Open question whether the deferral is correct (FRD-OQ-007).
CMP-IMP-299 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | Trip Estimates | Testing | Write estimate and multi-passenger tests | Negative stale or default estimate; integration per-booking independence; negative co-passenger cancellation effect | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-040; UC-044 | P0 | FEAT-019 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-300 | EPIC-06 Journey | FEAT-021 Trip History & Records | Trip History | API | Implement GET /trips presenting a user completed trips | Listing with date, route, counterparties, fare paid or earned, and outcome; cursor paging | Laravel | Controller | FRD-FR-168; API 11.9 | UC-043 | P1 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-301 | EPIC-06 Journey | FEAT-021 Trip History & Records | Trip History | Backend | Record, for every completed trip, its participants, route travelled, associated payment and outcome | Captured values written at completion; immutability; inspection view | Laravel | Service | FRD-FR-166; DB-072; NFR-126 | UC-043 | P0 | FEAT-018 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-302 | EPIC-06 Journey | FEAT-021 Trip History & Records | Trip History | Backend | Show a completed trip vehicle as it was recorded at the time of travel | Historical vehicle snapshot; no live vehicle read | Laravel | Service | FRD-FR-048 | UC-043 | P1 | FEAT-018 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-303 | EPIC-06 Journey | FEAT-021 Trip History & Records | Trip History | UI | Build Screen 20 - Trip history | Compose surface; listing; detail entry; empty state; provenance marking | Android | UI | UX 4.1 Screen 20 | UC-043 | P1 | FEAT-018 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-304 | EPIC-06 Journey | FEAT-021 Trip History & Records | Trip History | Testing | Write trip history tests | Integration captured values; negative live-read substitution for a captured value | Cross Platform | Validation | TC-029; TC-030 | UC-043 | P1 | FEAT-018 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-305 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Database | Create conversation and message tables with membership derived from the ride relationship | Tables; derived membership never granted; every message recorded; no read-state column | MySQL | Schema | NADR-02; NADR-03; NADR-06; FRD-FR-170; FRD-FR-172 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-306 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | API | Allow a driver and a passenger with a qualifying relationship to exchange messages | POST /conversations/{id}/messages; relationship check; message record | Laravel | Controller | FRD-FR-169; API 11.10 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-307 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Chat | Never deliver a message to a party with no qualifying relationship to the ride | Delivery guard; negative test with a non-qualifying party | Laravel | Service | FRD-FR-170 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-308 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Chat | Decline to open a conversation where the relationship does not permit messaging | Business refusal; refusal reason identifier | Laravel | Service | FRD-FR-171 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-309 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Chat | Retain a message and deliver it when the recipient next connects | Retention on delivery failure; delivery on reconnect; no loss | Laravel | Service | FRD-FR-173; NADR-09 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-310 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Chat | Never report a message as read to its sender | No read state leaves the platform; absent from every representation; negative test | Laravel | Service | FRD-FR-174; NADR-06 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-311 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Chat | Queue messages rather than discard them where the messaging service is unavailable | Queue on dependency unavailability; drain on restore | Laravel | Queue | FRD-FR-175; FRD-FR-260 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-312 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Chat | Support messaging between the participants of a multi-passenger trip | Multi-party conversation; membership derivation; disclosure limits | Laravel | Service | FRD-FR-176; NOTIF 5.6 | UC-045; UC-046; UC-047 | P2 | FEAT-014 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-313 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | API | Implement GET /conversations and GET /conversations/{id}/messages | Listings; cursor paging; relationship-limited representation | Laravel | Controller | API 11.10 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-314 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Android | Present previously retrieved messages when the device has no connectivity | Presentation cache read; offline retrieval; no fabrication of newer content | Android | Local DB | FRD-FR-177; MADR-05 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-315 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | UX | Indicate that a conversation shown without connectivity may not be current | Cached provenance treatment; as-of marking; UXDR-02 conformance | Android | UI | FRD-FR-178; UXDR-02 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-316 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Android | Implement the durable outbox so an offline-composed message is never shown as delivered | Outbox store separate from cache; idempotent durable submission; submission state on the affected object; never delivered until the platform accepts | Android | Local DB | FRD-FR-179; MADR-05; MADR-06; UXDR-14; NADR-04 | UC-045; UC-046; UC-047 | P0 | FEAT-014 | Post-MVP | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-317 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Notification | Alert a recipient to a message disclosing no more than the conversation itself would | Message-arrival notification; content limits; NOTIF 10.3 conformance | Laravel | Notification | FRD-FR-180; NOTIF 10.3 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-318 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | UI | Build Screen 24 - Conversations and Screen 25 - Messages | Compose surfaces; conversation list; message thread; offline treatment; send with outbox state; empty states | Android | UI | UX 4.1 Screens 24, 25 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-320 | EPIC-07 Communication | FEAT-022 Messaging | Messaging | Testing | Write messaging tests | Negative delivery to a non-qualifying party; negative read-state exposure; integration offline outbox submission; queue on unavailability | Cross Platform | Validation | TC-029; TC-030; FR-04; NOTIF 13 | UC-045; UC-046; UC-047 | P1 | FEAT-014 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-321 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Database | Create notification, preference and device registration tables | Tables; category immutable at issue; addressee and time; delivery target registration | MySQL | Schema | FRD-FR-203; NADR-13; API 11.11 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-322 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Issue a notification to each affected user on ride, booking, payment, trip, chat, reward, safety and system events | Event listeners; issue per event per affected user; one notification per event per user | Laravel | Notification | FRD-FR-197; NADR-10; NOTIF-081 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-323 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Identify the category of every notification at issue and make it immutable | Eight-category set; assignment at issue; no ninth without changing the preference surface | Laravel | Notification | FRD-FR-198; NOTIF-081; NADR-13 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-324 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Determine the users affected by an event before issuing notifications | Affected-user determination at issue not at delivery; participant resolution | Laravel | Notification | FRD-FR-199; NADR-08 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-325 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Apply a user notification preferences to non-essential categories at issue | Preference evaluation at issue against the preferences at that moment; no retroactive effect | Laravel | Notification | FRD-FR-200; NOTIF-089; NOTIF-090 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-326 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Deliver safety-category and payment-category notifications irrespective of preferences | Mandatory delivery; zero safety notifications suppressed; negative test | Laravel | Notification | FRD-FR-201; NOTIF-084; NOTIF-088; NFR-076 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-327 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | UX | Keep mandatory categories absent from the preference surface entirely | Not shown disabled, locked or explained; preference surface lists only controllable categories; negative test | Android | UI | FRD-FR-202; NOTIF-085; NOTIF-086; NOTIF-087; NADR-07 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-328 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Record every notification issued with its category, addressee and time | Record write; suppressed notifications still recorded and still in history | Laravel | Notification | FRD-FR-203; NOTIF-094; NOTIF-095 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-329 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Retain a notification in the application where its delivery fails | In-application record authoritative; delivery best-effort; negative test on loss | Laravel | Notification | FRD-FR-204; NADR-09 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-330 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Queue notifications where the messaging service is unavailable | Queue on dependency unavailability; drain on restore; notification job family | Laravel | Queue | FRD-FR-205; FRD-FR-260; BE-131 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-331 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Record and make available in the application a notification for a user with no reachable device | No-device path; in-application availability; no silent drop | Laravel | Notification | FRD-FR-206 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-332 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | API | Implement GET /notifications presenting history with category and time | Listing; cursor paging; acknowledgement operation | Laravel | Controller | FRD-FR-207; API 11.11 | UC-062; UC-063; UC-064 | P1 | FEAT-002 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-333 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | State that the subject of a notification is no longer accessible rather than fail silently | Subject resolution at open; explicit message; negative test on silent failure | Laravel | Notification | FRD-FR-208 | UC-062; UC-063; UC-064 | P1 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-334 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Integration | Implement the provider-neutral delivery port and one adapter | Port contract; capability result; bounds and recording; adapter for the selected provider | Laravel | Notification | NADR-12; BE-036; NOTIF 9 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-335 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | API | Implement device registration through PUT and DELETE /devices/current | Registration; deregistration; token rotation; no business value carried | Laravel | Controller | API 11.11 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-336 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Security | Ensure a notification carries no business value | Content limits; no fare, seat count, payment status or balance in a notification; negative test | Laravel | Notification | NADR-05; UXDR-12; NOTIF 10.1 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-337 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | UX | Make safety notifications visually distinct from every other category | Distinct treatment; not colour alone; review against NOTIF-093 | Android | UI | NOTIF-093; UX-160; UXDR-16 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-338 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Integration | Implement Firebase Cloud Messaging handling and deep links on the client | FCM integration; foreground and background handling; deep link routing to the notification subject | Android | Data | MOB 8.4; README 3 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-339 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | UI | Build Screen 26 - Notifications and Screen 27 - Notification preferences | Compose surfaces; history with category and time; preference toggles for controllable categories only; empty states | Android | UI | UX 4.1 Screens 26, 27 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-340 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Notification | Issue no notification in the reward category | Category exists but produces nothing; guard; negative test | Laravel | Notification | NOTIF-082 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 3 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | The reward category exists in FRD-FR-197 but no reward behaviour is specified (BAD-DEC-013). Do not issue in it.
CMP-IMP-341 | EPIC-07 Communication | FEAT-023 Notifications | Notifications | Testing | Write notification tests | Negative suppression of a safety notification; negative mandatory category on the preference surface; integration delivery failure retention; negative business value in content | Cross Platform | Validation | TC-029; TC-030; FR-04; NOTIF 13 | UC-062; UC-063; UC-064 | P0 | FEAT-002 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-342 | EPIC-08 Safety | FEAT-024 Emergency Contacts | Emergency Contacts | Database | Create the op_user_emergency_contacts migration | Table; protected contact columns; per-user nomination | MySQL | Schema | DB 6.2; DB-035 | UC-048 | P0 | FEAT-006 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-343 | EPIC-08 Safety | FEAT-024 Emergency Contacts | Emergency Contacts | API | Allow a user to nominate one or more emergency contacts | GET and PUT /profile/emergency-contacts; nomination; record against the user | Laravel | Controller | FRD-FR-181; FRD-FR-184; API 11.2 | UC-048 | P0 | FEAT-006 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-344 | EPIC-08 Safety | FEAT-024 Emergency Contacts | Emergency Contacts | API | Allow a user to amend or remove a nominated emergency contact | PUT and DELETE operations; state change; audit record | Laravel | Controller | FRD-FR-182; API 11.2 | UC-048 | P0 | FEAT-006 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-345 | EPIC-08 Safety | FEAT-024 Emergency Contacts | Emergency Contacts | Backend | Validate emergency contact details and state why a contact is unusable | Validation; reason identifier; API-131 conformance | Laravel | Service | FRD-FR-183; API-131 | UC-048 | P0 | FEAT-006 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-346 | EPIC-08 Safety | FEAT-024 Emergency Contacts | Emergency Contacts | UI | Build Screen 29 - Emergency contacts | Compose surface; list, add, amend, remove; unusable-contact treatment; empty state | Android | UI | UX 4.1 Screen 29 | UC-048 | P0 | FEAT-006 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-347 | EPIC-08 Safety | FEAT-024 Emergency Contacts | Emergency Contacts | Testing | Write emergency contact tests | Unit validation reasons; integration nomination and removal; negative unusable contact accepted | Cross Platform | Validation | TC-029; TC-030 | UC-048 | P0 | FEAT-006 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-348 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Database | Create op_safety_incidents and op_safety_actions migrations insertable with partial context | Tables; no validation failure on a non-essential column can lose a signal; missing context recorded as missing and distinguishable from absent in fact | MySQL | Schema | DB-077; DB-078; FRD-FR-187 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-349 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Implement the SafetyIncident aggregate with the close-requires-outcome invariant | Aggregate; invariant in Domain; no close by timeout; negative test | Laravel | Domain | BE-029; FRD-FR-227; FRD-FR-228; SRS-REQ-160 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-350 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Record every safety signal received as a safety incident | Intake service; unconditional record; negative test proving no signal is discarded | Laravel | Service | FRD-FR-185; FRD-FR-188 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-351 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Capture the raising user, trip, location at the time, vehicle and co-travellers with each incident | Context capture; partial capture tolerated; each element independently optional | Laravel | Service | FRD-FR-186; FRD-FR-187 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-352 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Place every safety incident in the safety operator queue | proj_safety_queue entry; maintained by the safety job family; never delayed by other work | Laravel | Queue | FRD-FR-189; ADM-044; BE-132 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-353 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Retain and retry an incident that cannot immediately reach the operator queue | Retry with backoff; no discard; failed safety job raises an operational condition immediately | Laravel | Queue | FRD-FR-190; BE-138; NFR-030 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-354 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Record a safety incident raised outside an active trip with no trip context | Trip-less intake path; context marked absent in fact | Laravel | Service | FRD-FR-191 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-355 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Record the actions taken in response to a safety incident and its outcome | Action records; outcome record; retention for post-incident review | Laravel | Service | FRD-FR-192; FRD-FR-229 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-356 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Security | Record every safety incident and every action upon it as an auditable event | Evidential records; actor, subject, time, outcome; same-transaction write | Laravel | Service | FRD-FR-193; FRD-FR-244 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-357 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | DevOps | Isolate the safety job family so it shares no capacity with any other family | Dedicated worker binding; no shared queue; deployment separation verified | Laravel | Queue | BE-132; OPS-040; BD-04 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-358 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | Safety Pipeline | Testing | Write safety pipeline tests | Negative signal discarded; negative incident closed without an outcome; negative close by timeout; integration partial-context insert; safety family isolation | Cross Platform | Validation | TC-029; TC-030; FR-04; FR-05 | UC-051 | P0 | FEAT-002; FEAT-033 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-359 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | Security | Implement the safety surface on its own path prefix | /safety/v1 routing; separate adapter set; minimum dependency set | Laravel | Controller | AADR-11; API 12; BADR-16 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-360 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | DevOps | Route the safety prefix independently with no shared rate limit, quota or throttle | Edge routing; no general-prefix policy applied; no refusal for a reason the application would not refuse for | Laravel | Controller | OPS-045; OPS-046; OPS-047; SEC-180; API-172 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-361 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | DevOps | Make the safety unit deployable and restartable without restarting the application unit | Independent deployment unit; restart verification; boot with minimum dependencies | Cross Platform | Controller | OPS-037; OPS-041; BE-191 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-362 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | UX | Present safety information and every available safety control from a single place | Safety centre composition; single point of access | Android | UI | FRD-FR-194; FRD-FR-196 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-363 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | Security | Never present a safety control the platform cannot honour | Control availability derived from platform capability; negative test asserting no unhonourable control is rendered | Android | UI | FRD-FR-195; UX-006; UXDR-13; MOB-150 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-364 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | UX | Make the safety centre reachable from every screen during an active trip | Global reachability during a trip; navigation entry; verification across screens | Android | UI | UX-011; NFR-092 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-365 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | UI | Build Screen 28 - Safety centre | Compose surface; safety information; available controls only; emergency contacts entry; rules entry | Android | UI | UX 4.1 Screen 28; UX 13.1 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-366 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | UI | Build Screen 30 - Rules of participation | Compose surface; versioned policy text from configuration; no insurance claim of any kind | Android | UI | UX 4.1 Screen 30; SRS-REQ-179 | UC-083 | P0 | FEAT-025 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-367 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | Security | Enforce the insurance prohibition on every user-facing surface | Content review of every surface; static check for insurance terminology; no statement or implication of cover | Cross Platform | Validation | FRD 8.5 prohibition; BRD-REQ-187; BAD-RISK-006; NFR-137 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-372 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | Safety Surface | Testing | Write safety surface tests | Negative unhonourable control rendered; negative safety prefix refused by an edge policy; integration independent restart; reachability during a trip | Cross Platform | Validation | TC-029; TC-030; FR-05 | UC-054; UC-083 | P0 | FEAT-025 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-373 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Install and bootstrap the Filament administrative surface within the application unit | Filament install; panel configuration; reachable only over stated routes; never bypassing the application unit | Filament | Resource | BADR-15; OPS-050; ADM 4 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-374 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Bind every resource to an application service for writes and a projection for reads | No Eloquent model binding; resource base class; service invocation; projection reader | Filament | Resource | ADMR-01; ADM-017; ADM-018; BADR-15 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-375 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Database | Create the nine projection tables in the proj_ domain | proj_admin_rides, bookings, trips, users, payments; proj_reconciliation_queue; proj_safety_queue; proj_support_cases; proj_operational_measures | MySQL | Schema | ADM-033; DB-006; DB-139 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-376 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Maintain each projection by a listener responding to domain events | Listeners per projection; synchronous or job maintenance recorded per projection; maintenance instant on each row | Laravel | Repository | ADM-034; ADM-039; ADM-043; BE-119; BE-124 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-377 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Make every projection rebuildable in full by truncate and replay | Rebuild command; replay from authoritative state; executable without interrupting write traffic | Laravel | Repository | ADM-035; ADM-042; BE-120; BE-126 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-378 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Ensure no projection is an input to a business decision | Read-path separation; static check; negative test | Filament | Resource | ADM-036; BE-121; DB-130 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-379 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Ensure seat availability is never read from a projection, including by an operator | Authoritative read enforced at every seat display; negative test in the admin surface | Filament | Resource | ADM-037; ARCH-056; DB-131 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-380 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Present each listing projection maintenance instant and mark it stale past its bound | Maintenance instant on every listing; staleness treatment; distinct operational condition on maintenance failure | Filament | Resource | ADM-046; ADM-047; ADM-050; UX-042; UX-044 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Projection staleness bounds are configuration and their values are unset (ADM-049).
CMP-IMP-381 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Ensure an operator never acts on a listing value where the action requires a current value | Action path forced through the detail view service read; negative test | Filament | Resource | ADM-048; ADM-038 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-382 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Security | Implement cursor paging and fixed allow-list filtering and sorting on every listing | Cursor paging; allow-list parameters never constructed from input; projection-supported parameters only | Filament | Resource | ADM-023; ADM-024; ADM-025; SEC-121 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-383 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Present a count only where the projection can produce it, and report unavailable never zero | Count availability check; unavailable reporting; negative test against a zero substitution | Filament | Resource | ADM-026; ADM-027; API-118; API-119 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-384 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Give each resource validation identical to a client request | Shared validation; no admin-only relaxation; negative test | Filament | Resource | ADM-029; ARCH-132; API-042 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-385 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Implement bulk operations as explicit bulk application services, atomic per record | Bulk service; no iteration of a single-record service in the resource; per-record outcome recorded | Filament | Resource | ADM-030; ADM-031; BE-053 | UC-070 | P2 | FEAT-002; FEAT-033 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-386 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Admin | Implement export as an application service operation under the same authorisation and evidencing as a read | Export service; authorisation; evidential record | Filament | Resource | ADM-032; ADMR-08 | UC-070 | P2 | FEAT-002; FEAT-033 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-387 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Security | Implement the twelve-capability administrative role mechanism | Capability set; role composition from capabilities; roles as versioned policy configuration; deny by default | Filament | Resource | ADM-163; ADM-164; ADM-170; ADMR-12 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | BLOCKED for deployment - the administrative surface cannot be deployed until at least one role exists (ADM-168). The role set is undecided (ADM-166, BAD-DEC-006).
CMP-IMP-388 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | UX | Tell operators plainly that their actions, refusals and inspections are recorded | Surface notice; placement; content review | Filament | Resource | ADM-165; SEC-206; ADMR-06 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 3 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-389 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | Admin Foundation | Testing | Write admin foundation tests | Negative ORM binding in a resource; negative projection read for seat availability; integration rebuild by replay; negative count reported as zero | Cross Platform | Validation | TC-029; TC-030; ADM 16 | UC-070 | P1 | FEAT-002; FEAT-033 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-390 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Allow an operator to locate a ride, ride request, booking or trip | Listing search over projections; single-projection reads; no cross-projection join | Filament | Resource | FRD-FR-209; ADM-020; ADM 7.1 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-391 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Present a located record with its parties, seats, status, state history, payment, messages and safety incidents | One composing application service operation; not assembled from several service calls in the resource | Filament | Page | FRD-FR-210; ADM-021; ADM-022 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-392 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Ensure inspecting a record does not alter it | Read-only guarantee; negative test asserting no state change from inspection | Filament | Resource | FRD-FR-211; ADM 7.3 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-393 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Record an operator inspection of a record as an auditable event | Evidential record on read; operator identity; subject | Filament | Resource | FRD-FR-212; ADMR-08; ADM 14.1 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Open question - whether inspection should be audited or only state changes, and the audit volume consequence, is unresolved (FRD-OQ-006).
CMP-IMP-394 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Security | Refuse operator access where the role does not permit it and record the refusal | Authorisation check; refusal record as fully as an application; negative test | Filament | Resource | FRD-FR-213; ADMR-06; SEC-065 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-395 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Security | Present only the fields the operator role entitles them to | Field-level entitlement; message content and position history as separate capabilities | Filament | Resource | ADM-028; ADM-164; SEC-067 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-396 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Allow an operator to apply an intervention to a booking or trip, stating the intervention and its reason | Intervention action invoking the same application service; reason required; operator identity carried into the service | Filament | Resource | FRD-FR-214; ADMR-04; ADMR-07; ADM 8.1 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-397 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Refuse an operator intervention that would allow confirmed seats to exceed seats offered | Same invariant path as a client request; capability never exemption; negative test | Filament | Resource | FRD-FR-215; ADMR-05; ADM 8.3; BE-024 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-398 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Refuse an operator intervention that would set payment status other than through verification or reconciliation | Status write prohibition for operators; negative test | Filament | Resource | FRD-FR-216; ADMR-05; BE-026 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-399 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Record every refused operator intervention as an auditable event | Refusal record; reason; operator identity | Filament | Resource | FRD-FR-217; ADMR-06 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-400 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Record an applied intervention with the identity of the operator who applied it | Operator attribution; evidential record; inspection view | Filament | Resource | FRD-FR-218; FRD-FR-246; ADM-165 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-401 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Admin | Inform the parties affected by an applied intervention | Notification issue to affected parties; category assignment | Filament | Resource | FRD-FR-219; FRD-FR-197 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-402 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | Admin Case Handling | Testing | Write admin inspection and intervention tests | Negative invariant bypass by an operator; negative payment status set by an operator; integration refusal recording; negative alteration by inspection | Cross Platform | Validation | TC-029; TC-030; FR-04; ADM 16 | UC-070; UC-071 | P1 | FEAT-027 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-403 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Admin | Present pending payments to operators as a managed queue | proj_reconciliation_queue resource; ordering; staleness marking; provenance on payment status | Filament | Resource | FRD-FR-138; ADM-038; ADM 9.1 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-404 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Admin | Allow an operator to record a determination against a pending payment and apply it to status and ledger | Determination action; recorded basis; status transition through reconciliation only; ledger entry | Filament | Resource | FRD-FR-139; PADR-13; ADM 9.2 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-405 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Admin | Retain a payment in the queue with the investigation recorded where the outcome still cannot be established | Retention in queue; investigation record; no forced resolution | Filament | Resource | FRD-FR-140 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-406 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Admin | Allow an operator to locate a payment, refund or settlement record | Payment listing and search; refund and settlement records absent by decision | Filament | Resource | FRD-FR-220; ADM 9 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | No refund or settlement record exists - both are withheld (GAP-009, BAD-RULE-036, ADM-105).
CMP-IMP-407 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Admin | Present a located payment with its amount, method, verification history, status and ledger entries | Composed detail service; attempt history; ledger entries; as-of markings | Filament | Page | FRD-FR-221 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-408 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Admin | Surface a ledger discrepancy rather than present a computed balance that conceals it | Reconciliation check on display; discrepancy presentation; routing to the queue | Filament | Resource | FRD-FR-222; FRD-FR-223 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-409 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | Reconciliation | Testing | Write reconciliation tests | Negative status set outside verification or reconciliation; integration determination applied to ledger; negative concealed discrepancy | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-033; UC-072 | P0 | FEAT-027; FEAT-016 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-410 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Present safety incidents to a safety responder as a queue | proj_safety_queue resource; isolated from other administrative work; ordering | Filament | Resource | FRD-FR-224; ADMR-13; ADM-044 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-411 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Present a safety incident with its full captured context and the related trip, parties and records | Composed detail service; missing context shown as missing; position history under its own capability | Filament | Page | FRD-FR-225; ADM-164 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-412 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Allow a safety responder to record an assessment, each action taken and an outcome | Assessment; action log; outcome record | Filament | Resource | FRD-FR-226; ADM 10 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-413 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Prevent a safety incident being closed without a recorded outcome | Close guard; ADMR-09 conformance; negative test | Filament | Resource | FRD-FR-227; BE-029; ADMR-09 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-414 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Prevent a safety incident being closed by timeout | No timeout closure path; negative test | Filament | Resource | FRD-FR-228 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-415 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Retain a closed safety incident for post-incident review | Retention; review access; no deletion path | Filament | Resource | FRD-FR-229 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-416 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Database | Create op_operator_cases and op_operator_actions migrations | Tables; durable record of every operator action | MySQL | Schema | DB 6.9; NFR-125 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-417 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Implement the OperatorCase aggregate with the close-requires-outcome invariant | Aggregate; invariant; closure as unresolved permitted; negative test | Laravel | Domain | BE-030; FRD-FR-233 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-418 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Allow a support agent to record a support case and its subject | Case creation; subject; listing via proj_support_cases | Filament | Resource | FRD-FR-230 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-419 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Give a support agent access to the trip, payment, message and prior-case records relevant to their case | Case-scoped access; capability-gated message content; reputation records absent by decision | Filament | Resource | FRD-FR-231; ADM-127 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Reputation records within a support case are withheld (BAD-DEC-012, ADM-127).
CMP-IMP-420 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Record each step an agent takes on a support case | Step log; operator attribution; evidential record | Filament | Resource | FRD-FR-232; FRD-FR-246 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-421 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Admin | Prevent a support case being closed without a recorded outcome, permitting closure as unresolved | Close guard; unresolved outcome allowed; negative test | Filament | Resource | FRD-FR-233; ADMR-09 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-422 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | Safety & Support Ops | Testing | Write safety and support operations tests | Negative incident closed without outcome; negative close by timeout; integration case step recording; capability gating of message content | Cross Platform | Validation | TC-029; TC-030; FR-04; FR-05 | UC-073; UC-075 | P0 | FEAT-027; FEAT-025 | Post-MVP | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-423 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | Reporting | Admin | Derive every reported measure from platform records | proj_operational_measures maintenance; no external or estimated input | Filament | Widget | FRD-FR-234; ADM 12 | UC-076 | P1 | FEAT-027 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-424 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | Reporting | Admin | Segment the zero-result search measure by corridor and time band | Segmentation dimensions; no geography in any key or partition; measure computation | Filament | Widget | FRD-FR-235; DB-020; DADR-14 | UC-076 | P1 | FEAT-027 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-425 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | Reporting | Admin | Report a measure as unavailable rather than as zero where the behaviour it measures is not implemented | Unavailable reporting; explicit list of unimplemented measures; negative test | Filament | Widget | FRD-FR-236; ADM-027; ADMR-10 | UC-076 | P1 | FEAT-027 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | FRD-FR-236 prevents a specific damaging defect - a dashboard reporting refunds zero when refunds are unimplemented reads as good news.
CMP-IMP-426 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | Reporting | Admin | Make proj_operational_measures rebuildable independently of the other eight projections | Independent rebuild command; replay; no coupling | Filament | Widget | ADM-045; ADM-035 | UC-076 | P1 | FEAT-027 | Post-MVP | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-427 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | Reporting | Testing | Write reporting tests | Negative unimplemented measure reported as zero; integration segmentation; rebuild independence | Cross Platform | Validation | TC-029; TC-030 | UC-076 | P1 | FEAT-027 | Post-MVP | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-429 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Backend | Determine every value affecting shared business state from platform authoritative state | Authority rule applied across all services; no derivation from client input; static review | Laravel | Service | FRD-FR-237; SRS-REQ-176; ARCH-016 | UC-078 | P0 | FEAT-002 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-430 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Security | Reject any client-supplied value purporting to determine an authoritative business value | Rejection of seat availability, booking status, payment status, fare, wallet balance, reward accrual, verification status; schema absence; negative test per field | Laravel | Service | FRD-FR-238; AADR-06; API-037 | UC-078 | P0 | FEAT-002 | Day 5 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-431 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Security | Reject a request carrying such a value in its entirety and never partially apply it | Whole-request rejection; no partial effect; negative test | Laravel | Service | FRD-FR-239; BE-053 | UC-078 | P0 | FEAT-002 | Day 6 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-432 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Security | Record an attempt to assert an authoritative value as an auditable integrity event | Security event as an evidential record; assertion attempt capture; alerting hook | Laravel | Service | FRD-FR-240; SADR-08; SADR-15 | UC-078 | P0 | FEAT-002 | Day 6 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-433 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Backend | Return the platform own determination as the authoritative result of every such request | Response always carries the platform value; as-of marking; contract test | Laravel | Service | FRD-FR-241; AADR-09 | UC-078 | P0 | FEAT-002 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-434 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Backend | Permit a client to retain returned values for presentation only | Presentation cache contract; no business decision from cached values; client static check | Cross Platform | Data | FRD-FR-242; MOB-010; MADR-05 | UC-078 | P0 | FEAT-002 | Day 6 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-435 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Backend | Resolve any client and platform state disagreement in favour of the platform and correct the client | Correction response; client application of the correction; refresh or discard semantics | Cross Platform | Data | FRD-FR-243; SRS-REQ-176 | UC-078 | P0 | FEAT-002 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Open question - whether correction requires the client to discard its cache or merely refresh is unresolved (FRD-OQ-010).
CMP-IMP-436 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | API | Require an idempotency key on every state-changing operation | Mandatory key at the interface; rejection without one; replay semantics; contract test | Laravel | Controller | AADR-04; API-057; BE-045 | UC-078 | P0 | FEAT-002 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-437 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | Backend Authority | Testing | Write backend authority tests | Negative client assertion per authoritative field; integration whole-request rejection; integration idempotent replay | Cross Platform | Validation | TC-029; TC-030; TC-031; FR-04 | UC-078 | P0 | FEAT-002 | Day 8 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-438 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Database | Create the ev_evidential_records append-only chained migration | Table in ev_ domain; chain column; written only by the evidential writer; physical non-updatability | MySQL | Schema | DB-004; DB 9.1; DB 9.3; DADR-09 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 6 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-439 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Implement one evidential writer as the only path into ev_ | Single writer component; append-only; dedicated database account; no other write path | Laravel | Repository | BADR-09; BE-105; DB-004 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 8 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-440 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Database | Enforce append-only at the database level | Trigger or grant-based enforcement; no UPDATE or DELETE grant; constraint test | MySQL | Schema | DB 9.2; DB 9.3; DADR-09 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-441 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Security | Implement the keyed evidential chain with the key held outside the database | Chain construction; keying; key custody outside the database; verification routine | Laravel | Repository | SADR-07; SEC 10; SEC 10.1 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 9 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-442 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Record every ride, request, booking, payment, trip, safety incident and operator action as an auditable event | Event coverage matrix; per-aggregate emission; coverage test | Laravel | Repository | FRD-FR-244 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 9 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-443 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Record what occurred, when, its subject and the party responsible with each event | Record content; operator named where an operator acted; content test | Laravel | Repository | FRD-FR-245; FRD-FR-246; BE-107 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 9 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-444 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Retain records durably and prevent silent alteration or deletion | Durability; alteration detection through the chain; negative test on tamper | Laravel | Repository | FRD-FR-247 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-445 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Do not report an action as complete where its auditable record cannot be written | Write-then-report ordering across every service; failure branch; negative test | Laravel | Repository | FRD-FR-248; BE-049 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-446 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Raise for reconciliation any action that took effect but whose record could not be written | Reconciliation raise; queue entry; operator visibility | Laravel | Queue | FRD-FR-249 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-447 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Admin | Make auditable records available to operators for inspection | Two audit views; operator access under capability; demonstration of how a matter was handled | Filament | Page | FRD-FR-250; ADM 14.3 | UC-079 | P1 | FEAT-002; FEAT-003 | Post-MVP | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-448 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Backend | Run evidential chain verification as scheduled reconciliation | Scheduled job; chain walk; discrepancy raise | Laravel | Queue | BE-146; BE-115 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 10 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-450 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | Evidential Log | Testing | Write evidential log tests | Negative record update or delete; negative action reported complete without a record; integration chain verification; tamper detection | Cross Platform | Validation | TC-029; TC-030; FR-04 | UC-079 | P0 | FEAT-002; FEAT-003 | Day 10 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-451 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Backend | Detect the unavailability of a supporting service and determine which capabilities are affected | Port health signalling; capability mapping; state propagation | Laravel | Service | FRD-FR-255 | UC-081 | P0 | FEAT-032 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-452 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Backend | Withdraw or mark an affected capability rather than present it as working | Capability withdrawal; marking; negative test asserting no capability is presented as working while unavailable | Cross Platform | Service | FRD-FR-256; UX-006 | UC-081 | P0 | FEAT-032 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-453 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | UX | Inform the affected actor what is unavailable and what remains available | Dependency-unavailable treatment; actionable message; client rendering | Android | UI | FRD-FR-257; UXDR-03; UX 7.4 | UC-081 | P0 | FEAT-032 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-454 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Backend | Never resolve an unknown outcome by assumption in either direction while a service is unavailable | No optimistic or pessimistic resolution; pending semantics; negative test | Laravel | Service | FRD-FR-258; PADR-06 | UC-081 | P0 | FEAT-032 | Day 12 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-455 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Backend | Withdraw a capability entirely rather than degrade it where degrading would compromise an absolute rule | Absolute-rule guard; withdrawal decision table; negative test | Laravel | Service | FRD-FR-259 | UC-081 | P0 | FEAT-032 | Day 12 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-456 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Backend | Resume normal behaviour and process deferred work when a service is restored | Restore detection; deferred work drain; ordering guarantees | Laravel | Queue | FRD-FR-260 | UC-081 | P0 | FEAT-032 | Day 12 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-457 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | API | Implement GET /configuration delivering platform configuration to the client | Configuration resource; delivered values per API 14.2; version marking; cache semantics | Laravel | Controller | AADR-13; API 14; API 14.1 | UC-081 | P0 | FEAT-032 | Day 12 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-458 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Configuration | Consume delivered configuration on the client for cadence and staleness bounds | Configuration read at start and refresh; no client-chosen values; adjustable without a client release | Android | Data | MOB 12.1; MOB-135; OPS-118; API-162 | UC-081 | P0 | FEAT-032 | Day 12 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-459 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | API | Implement GET /health distinguishing platform health from dependency health | Health resource; per-dependency reporting; not conflated with readiness | Laravel | Controller | BE-203; API 11.13; OPS 12.3 | UC-081 | P0 | FEAT-032 | Day 12 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-460 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | Degradation | Testing | Write degraded operation tests | Induced failure per dependency; negative capability presented as working; negative assumption resolution; integration restore and drain | Cross Platform | Validation | TADR-09; TC 12.2; TC-030; FR-04 | UC-081 | P0 | FEAT-032 | Day 13 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-461 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Implement URI path versioning supporting version N and N minus 1 | /api/v1 routing; dual-version support; deprecation posture | Laravel | Controller | AADR-03; API 5 | - | P0 | FEAT-002 | Day 4 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-462 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Implement GET /versions reporting the supported version range | Version resource; reachable without a session; client negotiation input | Laravel | Controller | API-027; API 11.13; API 9.1 | - | P0 | FEAT-002 | Day 4 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-463 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Implement the four error branches with four distinct shapes | Invalid request; business refusal; dependency unavailable; internal fault; classification rules; contract tests | Laravel | Controller | AADR-02; API 8; API 8.6 | - | P0 | FEAT-002 | Day 4 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-464 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Identify refusal reasons rather than return free text | Reason identifier registry; no free-text reason; client mapping to content | Laravel | Controller | AADR-14; API-014; UX 14 | - | P0 | FEAT-002 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-465 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Carry an as-of marking on every business value in every representation | Provenance envelope; as-of instant; contract test across resources | Laravel | Controller | AADR-09; API-047; UXDR-02 | - | P0 | FEAT-002 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-466 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Vary representation by relationship rather than by role alone | Relationship resolution; per-relationship field sets; disclosure limits | Laravel | Controller | AADR-08; API 6.3; API-051 | - | P0 | FEAT-002 | Day 5 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-467 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Serve JSON only with one representation per resource | Content negotiation refusal for other types; single representation rule | Laravel | Controller | AADR-05; API 6.1 | - | P0 | FEAT-002 | Day 5 | 4 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-468 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | Security | Keep authoritative fields absent from every request schema | Schema audit; absence rather than ignore-on-input; contract test per resource | Laravel | Controller | AADR-06; API-037; FRD-FR-238 | - | P0 | FEAT-002 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-469 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Model intents as resources rather than as verbs on a resource | Intent sub-resources; acceptance, cancellation, verification, completion, start; naming consistency | Laravel | Controller | AADR-07; API 4 | - | P0 | FEAT-002 | Day 6 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-470 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | API | Implement collections with cursor paging and allow-listed filtering | Cursor contract; opaque cursors; filter allow-list; page size as configuration | Laravel | Controller | API 10; API-112; API-113; DADR-04 | - | P0 | FEAT-002 | Day 6 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | No limit, window or page size value is stated anywhere in CMP-DOC-10 (API 0.8.4). Values are configuration and unset.
CMP-IMP-471 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API Contract | Testing | Write API contract tests asserting shape and not business behaviour | Branch shapes; schema acceptance; response markings; no business assertion | Cross Platform | Validation | TADR-10; TC-031; API 19 | - | P0 | FEAT-002 | Day 6 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-472 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Establish and enforce the four trust boundaries | TB-1 client to platform; TB-2 operator to platform; TB-3 provider to platform; TB-4 platform to persistence; positional defence not perimeter | Laravel | Validation | SEC 4; SADR-01 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 9 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-473 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Implement session bounds, refresh limits and non-replayable session material | Absolute and idle bounds; refresh within the bound; nothing replayable in any store | Laravel | Authentication | SEC 6; SADR-04; NFR-054; NFR-055 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 9 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Bound values are configuration and unset pending BAD-DEC-018.
CMP-IMP-474 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Store authentication credentials in non-recoverable form | Non-recoverable scheme; algorithm selection per SEC 14.2; never on op_users | Laravel | Authentication | SEC 5.3; DB-036; DB-042 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 9 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-475 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Implement attempt bounding on authentication and verification | Attempt counting against state; lockout posture; recorded exhaustion | Laravel | Authentication | SEC 5.2; FRD-FR-011; NFR-057 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - limits and cool-off periods are unset (FRD-OQ-003).
CMP-IMP-476 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Implement per-column protection at rest for identity evidence and payment-related data | Column-level protection; key custody; no whole-database substitution | MySQL | Schema | SADR-05; SEC 8; DB-035 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 10 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-477 | EPIC-11 Security | FEAT-036 Security Controls | Security | DevOps | Implement protection in transit end to end | Transport termination point; end-to-end property; recorded rather than assumed | Laravel | Network | SEC 9; SEC-091; SEC-101; OPS-048 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 10 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Decision Required - protocol versions and cipher selection depend on the unselected hosting provider (OPS-049, BAD-DEP-009).
CMP-IMP-478 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Prevent injection by construction across every data path | Bound values only; no concatenated statements; allow-listed sort and filter; static check | Laravel | Validation | SADR-09; DB-038; SEC 11; SEC-119; SEC-121 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 10 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-479 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Ensure no payment credential is ever received by any component | No instrument field anywhere; provider response bodies containing one never stored; schema and log inspection | Cross Platform | Validation | SADR-10; SEC 12; DB-037; DB-068 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 11 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-480 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Implement the client-side security posture: the device holds nothing worth stealing | Session material; identity evidence; cache and outbox contents; logging and transport discipline; device integrity posture | Android | Data | SADR-13; SEC 13; SEC 13.1; SEC 13.3; SEC 13.4 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 11 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-481 | EPIC-11 Security | FEAT-036 Security Controls | Security | DevOps | Supply secrets at deploy time and never in an artefact | Secret inventory; injection at start; no secret in repository or build log; signing key custody | Laravel | Validation | SADR-14; SEC 14.1; SEC-163; SEC-165; OPS-098; OPS-116 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 11 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-482 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Record security events as evidential records | Event set; assertion attempts; authorisation refusals; chain inclusion | Laravel | Validation | SADR-15; SEC 17.1; FRD-FR-240 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 11 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-483 | EPIC-11 Security | FEAT-036 Security Controls | Security | Security | Implement the abuse and automated-access posture with bounds held as configuration | Rate limiting on the general prefix only; quotas; tuning values as configuration; safety prefix exempt | Laravel | Validation | SEC 15; API 15; SEC-180; OPS-046 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 12 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | All tuning values are unset (API 15.3, SEC 15).
CMP-IMP-484 | EPIC-11 Security | FEAT-036 Security Controls | Security | Testing | Implement an executable check for every checkable security property | Automated check set per SEC 19.1; build integration; four unmechanised properties recorded separately | Cross Platform | Validation | SADR-16; SEC 19.1; SEC 19.4; SEC-230 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 12 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-486 | EPIC-11 Security | FEAT-036 Security Controls | Security | Testing | Write security verification tests | Injection attempts; over-disclosure; session reuse; privilege escalation; secret presence in artefact; instrument surface presence | Cross Platform | Validation | SEC 19; TC 10; FR-04 | UC-080 | P0 | FEAT-002; FEAT-003 | Day 13 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-487 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Wire the six verification levels so that a failure at an earlier level stops the later ones | Level 1 static; 2 unit and domain; 3 integration and service; 4 contract; 5 system behaviour; 6 manual review; ordered execution | Cross Platform | Validation | TC-025; TC-028; TADR-05 | - | P0 | FEAT-001; FEAT-002 | Day 3 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-488 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Documentation | Build the consolidated verification obligation register with owning levels | 99 obligations; one owning level each; secondary verification recorded; change control | Cross Platform | Validation | TC 4; TC-026; TC-027; TADR-01; TADR-02; TADR-14 | - | P0 | FEAT-001; FEAT-002 | Day 3 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-489 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Documentation | Complete the integrity-critical mapping TC-017 | Map every one of the 1,412 integrity-critical statements to an owning obligation; report the residue | Cross Platform | Validation | TC-017; TC 4.3; TR criterion 6 | - | P0 | FEAT-001; FEAT-002 | Day 4 | 24 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Release readiness criterion 6 (TR 10.1) - not started. This is analysis work, not construction, and it gates gate 4.
CMP-IMP-490 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | DevOps | Implement the thirteen structural rules at gate 1 with no suppression path for the eight non-suppressible | Rule implementation; fail not warn; eight rules with no suppression path in pipeline configuration | Cross Platform | Validation | TC-037; TC-038; TC-021; OPS-092; OPS-093 | - | P0 | FEAT-001; FEAT-002 | Day 4 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-491 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish domain test infrastructure running without a database, framework or network | Test harness; isolation verification; fast feedback | Cross Platform | Validation | TC-029; BE-040; MOB-153 | - | P0 | FEAT-001; FEAT-002 | Day 4 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-492 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish integration test infrastructure against a real database | Real MySQL instance; CHECK-enforcing version; no in-memory substitute; fixture strategy | Cross Platform | Validation | TC-030; TADR-08; DB-085; OPS-024 | - | P0 | FEAT-001; FEAT-002 | Day 5 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-493 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish contract test infrastructure asserting shape and not behaviour | Schema assertions; branch shape assertions; prohibition on business assertions | Cross Platform | Validation | TC-031; TADR-10 | - | P0 | FEAT-001; FEAT-002 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-494 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish database constraint testing | Constraint violation attempts; grant inspection; schema inspection | Cross Platform | Validation | TC 9; TC 6.2; DB 15 | - | P0 | FEAT-001; FEAT-002 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-495 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish concurrency testing under genuine parallelism | Parallel execution harness; repeat runs; allocation and idempotency assertions | Cross Platform | Validation | TADR-08; TC 12.1 | - | P0 | FEAT-001; FEAT-002 | Day 6 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-496 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish induced-failure testing with hooks absent from the production artefact | Failure injection at ports; hook removal verified by static analysis; per-dependency scenarios | Cross Platform | Validation | TADR-09; TC 12.2; TC-155; OPS-099 | - | P0 | FEAT-001; FEAT-002 | Day 6 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-497 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Establish client testing infrastructure | State holder tests; Compose surface tests; gateway substitution; outbox tests | Android | Validation | TC 11; MOB 15 | - | P0 | FEAT-001; FEAT-002 | Day 6 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-498 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Testing | Require a negative test for every integrity-critical requirement | Coverage measured against the integrity-critical set; positive and negative pair per marked requirement; gap report | Cross Platform | Validation | FR-04; TADR-04; TC 4.3 | - | P0 | FEAT-001; FEAT-002 | Day 7 | 16 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-499 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | UX | Establish accessibility verification as a specified procedure with a recorded outcome | Walkthrough procedure; recorded outcome; not an instruction to look | Cross Platform | Validation | TC 13; TC-032; TADR-12 | - | P0 | MOB-OQ-002 | Day 7 | 8 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | Decision Required - the accessibility conformance standard is unchosen (MOB-OQ-002, NFR-088, UX 15.3).
CMP-IMP-500 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | DevOps | Generate test data only; never copy production personal data into any environment | Generator; shape without volume; prohibition check | Cross Platform | Validation | TC 16; OPS-022; TC-203; TC-206 | - | P0 | FEAT-001; FEAT-002 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-501 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Documentation | Implement the coverage and verification report shape | Report per TC 15.2; no coverage percentage as a gate; untested-because-undecided set carried | Cross Platform | Validation | TC 15; TC-012; TC-020; TR-111; TR-119 | - | P0 | FEAT-001; FEAT-002 | Day 8 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-502 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | Verification | Documentation | Publish the untested-because-undecided set with every readiness statement | Set maintenance; attachment rule; misrepresentation prohibition | Cross Platform | Validation | TC 14.3; TR-119; TR-120; TRDR-11 | - | P0 | FEAT-001; FEAT-002 | Day 8 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-503 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Define the four environments with distinct secrets and no production data outside production | Development, test, staging, production; own configuration each; CHECK-enforcing database everywhere; reconstructible from recorded configuration | Cross Platform | Migration | OPS 5.1; OPS-021; OPS-022; OPS-024; OPS-025; OPS-028 | - | P0 | FEAT-037 | Day 2 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Environment sizing is register decision 9 and is unresolved (OPS-027). Staging cannot be shaped like production in volume until GAP-016 is resolved (OPS-026).
CMP-IMP-504 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Implement the four-gate pipeline running every level below each gate | Gate 1 commit; gate 2 merge; gate 3 pre-release; gate 4 release; no bypass path; no emergency path | Cross Platform | Migration | OPS-089; OPS-090; OPS-105; OPS 9.1; TC 6.3 | - | P0 | FEAT-037 | Day 3 | 16 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-505 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Require every non-suppressible obligation to pass at gate 4 with no exception | 25 non-suppressible obligations wired into gate 4; no suppression path | Cross Platform | Migration | OPS-091; TC-021; TC-200; TR-110 | - | P0 | FEAT-037 | Day 4 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-506 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Build one artefact per unit per commit and promote it unchanged | Per-unit build; bit-for-bit promotion; artefact identity recorded; reproducible from commit | Cross Platform | Migration | OPS-029; OPS-030; OPS-097; OPS-100; OPS-101 | - | P0 | FEAT-037 | Day 4 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-507 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Ensure an artefact contains no environment value, endpoint or secret | Artefact inspection check; build-time verification; failure-induction hooks absent | Cross Platform | Migration | OPS-098; OPS-099; NFR-108; SEC-163 | - | P0 | FEAT-037 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-508 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Record each promotion with artefact identity, gate results and authorising person | Promotion record; rollback as promotion of a previously passing artefact not a rebuild | Cross Platform | Migration | OPS-032; OPS-033; NFR-119 | - | P0 | FEAT-037 | Day 5 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-509 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Handle migrations in deployment without rolling them back on rollback | Migration execution; destructive migration recorded approval; no migration rewrites an evidential record; failed migration is a failed deployment | Cross Platform | Migration | OPS-034; OPS-104; DB-218; DB-219 | - | P0 | FEAT-037 | Day 6 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-510 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Define and deploy the five deployment units | Application; safety surface; general worker; safety worker; scheduler; each independently deployable and restartable | Cross Platform | Migration | OPS-037; ARCH-143 | - | P0 | FEAT-037 | Day 6 | 14 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-511 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Ensure the application unit holds no session state in instance memory | Stateless verification; interchangeable instances; horizontal scale readiness | Cross Platform | Migration | OPS-038; ARCH-138; ARCH-139 | - | P0 | FEAT-037 | Day 7 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-512 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Ensure exactly one scheduler instance is active | Single-active enforcement; duplicate triggering prevention; failover posture | Cross Platform | Migration | OPS-039; ARCH-140 | - | P0 | FEAT-037 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-513 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Make each job family independently drainable and pausable in deployment | Per-family controls; drain procedure; pause procedure | Cross Platform | Migration | OPS-043; BE-133 | - | P0 | FEAT-037 | Day 7 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-514 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | Security | Implement the secret store with rotation and compromise procedures | Store reachable only from the units; injection at start; rotation procedure; compromise procedure | Cross Platform | Migration | OPS 8; OPS-116; SEC 14.1; SADR-14 | - | P0 | FEAT-037 | Day 8 | 12 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Custody for six unselected suppliers is stated as a property, not a product (OPS 8.2).
CMP-IMP-515 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Implement client build, signing and distribution verification | Signing key in the store never in a repository or build log; distribution-platform technical requirements verified in the build | Android | Migration | OPS-107; OPS-115; OPS-116; MOB-168 | - | P0 | FEAT-037 | Day 8 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested | Distribution platform obligations beyond the technical are BAD-DEP-008 and are not specified (OPS-120).
CMP-IMP-516 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Ensure a client release does not require a platform release and vice versa | Independent release verification; version negotiation coverage | Cross Platform | Migration | OPS-117; MOB-131; SRS-REQ-011 | - | P0 | FEAT-037 | Day 8 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-517 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | DevOps | Implement backup and the restore-versus-retention procedure | Backup regime; restore procedure; retention re-applied before a restore is complete | Cross Platform | Migration | OPS 11.3; OPS 11.4; DDR-12 | - | P0 | BAD-DEC-021 | TBD | 12 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | BLOCKED - the restore reconciliation procedure cannot be completed until retention periods exist (BAD-DEC-021, OPS 15.2). Release readiness criterion 9.
CMP-IMP-519 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | Delivery Pipeline | Testing | Verify the pipeline gates themselves | Gate bypass attempt; suppression path search; promotion skipping attempt; emergency path search | Cross Platform | Migration | OPS-031; OPS-090; OPS-105; TC-053; TC-054 | - | P0 | FEAT-037 | Day 9 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-520 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | Observability | DevOps | Instrument the eighteen measurement points required from first release | Instrumentation; reporting; no threshold set; instrument first threshold later | Cross Platform | Service | OPS 12.2; OPS-119; DDR-11; TR criterion 11 | - | P1 | FEAT-038 | Day 13 | 16 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-521 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | Observability | DevOps | Instrument the nine mobile measurement points | Battery, data, memory and start-up measurement; reporting; baseline capture | Android | Service | MOB 13.1; OPS-119; GAP-015 | - | P1 | FEAT-038 | Day 13 | 10 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-522 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | Observability | Integration | Integrate crash reporting, performance monitoring and analytics on the client | Firebase Crashlytics, Performance Monitoring and Analytics wiring; no personal data in events | Android | Service | README 3; NFR series | - | P1 | FEAT-038 | Day 14 | 8 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-523 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | Observability | DevOps | Distinguish platform health from dependency health in operational reporting | Separate signals; no conflation; operational dashboard inputs | Cross Platform | Service | OPS 12.3; BE-203 | - | P1 | FEAT-038 | Day 14 | 6 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-524 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | Observability | DevOps | Record the artefact identity in every operational log line | Identity injection; log format; correlation with the deployment record | Cross Platform | Service | OPS-100; BE-199 | - | P1 | FEAT-038 | Day 14 | 5 |  | Not Started | No | No | No | No | No | No | 0 | TBD | TBD | Not Tested
CMP-IMP-525 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | Observability | Security | Establish the incident response structure and break-glass access | Response structure; break-glass authorisation and recording; no operator path around the application | Cross Platform | Service | OPS 14; OPS-092 break-glass; DDR-13; OPS-050 | - | P1 | SEC-OQ-07 | TBD | 12 |  | Blocked | No | No | No | No | No | Yes | 0 | TBD | TBD | Not Tested | BLOCKED - incident response ownership is unanswered since CMP-DOC-13 (SEC-OQ-07). Release readiness criteria 9 and 10.

## 03_Feature_Summary
CMP - FEATURE SUMMARY
Entirely formula-driven from 02_Work_Items. Do not type counts into this sheet - they will be wrong the moment the tracker changes.
Feature ID | Feature | Epic | Total Work Items | Not Started | In Progress | Implemented | Committed | Pushed | Testing | Tested | Reviewed | Completed | Blocked | Other Statuses | Bugs | Completion %
FEAT-001 | FEAT-001 Project Foundation - Android | EPIC-01 Foundation & Architecture
FEAT-002 | FEAT-002 Project Foundation - Laravel | EPIC-01 Foundation & Architecture
FEAT-003 | FEAT-003 Project Foundation - Database | EPIC-01 Foundation & Architecture
FEAT-004 | FEAT-004 Authentication & Session | EPIC-02 Identity & Access
FEAT-005 | FEAT-005 Registration & Phone Verification | EPIC-02 Identity & Access
FEAT-006 | FEAT-006 Profile & Counterparty Disclosure | EPIC-02 Identity & Access
FEAT-007 | FEAT-007 Roles & Authorisation | EPIC-02 Identity & Access
FEAT-008 | FEAT-008 Vehicle Management | EPIC-03 Supply
FEAT-009 | FEAT-009 Ride Publishing | EPIC-03 Supply
FEAT-010 | FEAT-010 Ride Preferences | EPIC-03 Supply
FEAT-011 | FEAT-011 Ride Search & Route Matching | EPIC-04 Discovery
FEAT-012 | FEAT-012 Ride Detail & Commitment Surface | EPIC-04 Discovery
FEAT-013 | FEAT-013 Ride Request | EPIC-05 Transaction
FEAT-014 | FEAT-014 Booking & Seat Allocation | EPIC-05 Transaction
FEAT-015 | FEAT-015 Fare & Payment Initiation | EPIC-05 Transaction
FEAT-016 | FEAT-016 Payment Verification & Reconciliation | EPIC-05 Transaction
FEAT-017 | FEAT-017 Ledger | EPIC-05 Transaction
FEAT-018 | FEAT-018 Trip Execution | EPIC-06 Journey
FEAT-019 | FEAT-019 Live Position Tracking | EPIC-06 Journey
FEAT-020 | FEAT-020 Estimates & Multi-Passenger Trip | EPIC-06 Journey
FEAT-021 | FEAT-021 Trip History & Records | EPIC-06 Journey
FEAT-022 | FEAT-022 Messaging | EPIC-07 Communication
FEAT-023 | FEAT-023 Notifications | EPIC-07 Communication
FEAT-024 | FEAT-024 Emergency Contacts | EPIC-08 Safety
FEAT-025 | FEAT-025 Safety Incident Pipeline | EPIC-08 Safety
FEAT-026 | FEAT-026 Safety Centre & Safety Surface | EPIC-08 Safety
FEAT-027 | FEAT-027 Admin Foundation & Projections | EPIC-09 Operations
FEAT-028 | FEAT-028 Admin Inspection & Intervention | EPIC-09 Operations
FEAT-029 | FEAT-029 Admin Payment Reconciliation | EPIC-09 Operations
FEAT-030 | FEAT-030 Admin Safety & Support | EPIC-09 Operations
FEAT-031 | FEAT-031 Admin Operational Reporting | EPIC-09 Operations
FEAT-032 | FEAT-032 Backend Authority & Idempotency | EPIC-10 Cross-Cutting Integrity
FEAT-033 | FEAT-033 Evidential Log & Audit | EPIC-10 Cross-Cutting Integrity
FEAT-034 | FEAT-034 Degraded Operation & Configuration | EPIC-10 Cross-Cutting Integrity
FEAT-035 | FEAT-035 API Contract & Versioning | EPIC-10 Cross-Cutting Integrity
FEAT-036 | FEAT-036 Security Controls | EPIC-11 Security
FEAT-037 | FEAT-037 Verification & Test Infrastructure | EPIC-12 Quality
FEAT-038 | FEAT-038 Build, Pipeline & Environments | EPIC-13 DevOps & Release
FEAT-039 | FEAT-039 Observability & Operations | EPIC-13 DevOps & Release
TOTAL | All features

## 04_Daily_Progress
CMP - DAILY PROGRESS
Pre-seeded with the Day 1 to Day 15 plan derived from documentation sequencing. Day allocation is DEPENDENCY-ORDERED, not capacity-fitted - see 01_Dashboard, Project Health.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Date | Day | Work ID | Feature | Work Description | Started | Completed | Status | Commit | Push | Test | Review | Blocker | Notes
| Day 1 | CMP-IMP-001 | FEAT-001 Project Foundation - Android | Create Android project skeleton (Kotlin, Jetpack Compose, single Activity) | No | No | Not Started | TBD | No | Not Tested | No
| Day 1 | CMP-IMP-002 | FEAT-001 Project Foundation - Android | Create the module structure: app, presentation, domain, data, platform, core | No | No | Not Started | TBD | No | Not Tested | No
| Day 1 | CMP-IMP-004 | FEAT-001 Project Foundation - Android | Implement core provenance wrapper carrying value plus as-of marking | No | No | Not Started | TBD | No | Not Tested | No
| Day 1 | CMP-IMP-005 | FEAT-001 Project Foundation - Android | Implement core Result type and the four-class error model | No | No | Not Started | TBD | No | Not Tested | No
| Day 1 | CMP-IMP-021 | FEAT-002 Project Foundation - Laravel | Create Laravel project with Interface/Application/Domain/Infrastructure namespaces | No | No | Not Started | TBD | No | Not Tested | No
| Day 1 | CMP-IMP-038 | FEAT-003 Project Foundation - Database | Create the MySQL schema on InnoDB with a full-range Unicode character set | No | No | Not Started | TBD | No | Not Tested | No
| Day 1 | CMP-IMP-039 | FEAT-003 Project Foundation - Database | Establish the six storage domains by table name prefix | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-003 | FEAT-001 Project Foundation - Android | Enforce module dependency direction at build time | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-006 | FEAT-001 Project Foundation - Android | Configure the compile-time dependency injection graph | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-007 | FEAT-001 Project Foundation - Android | Configure injected coroutine dispatchers and structured concurrency | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-008 | FEAT-001 Project Foundation - Android | Configure build variants supplying environment values at build time | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-022 | FEAT-002 Project Foundation - Laravel | Enforce inward-only layer dependency by static analysis in the build | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-023 | FEAT-002 Project Foundation - Laravel | Implement the application service base with command and result types | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-040 | FEAT-003 Project Foundation - Database | Implement the dual key convention: internal surrogate and external opaque identifier | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-041 | FEAT-003 Project Foundation - Database | Implement cursor paging on sort-key plus internal-id tuples | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-042 | FEAT-003 Project Foundation - Database | Apply the type conventions: exact decimal money, instant timestamps, protected columns | No | No | Not Started | TBD | No | Not Tested | No
| Day 2 | CMP-IMP-503 | FEAT-038 Build, Pipeline & Environments | Define the four environments with distinct secrets and no production data outside production | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-009 | FEAT-001 Project Foundation - Android | Add static analysis proving absence of business logic in the client | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-011 | FEAT-001 Project Foundation - Android | Produce a measurable client artefact size in the build | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-012 | FEAT-001 Project Foundation - Android | Build the single-Activity navigation destination graph | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-013 | FEAT-001 Project Foundation - Android | Move all user-facing and brand-bearing strings to resources | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-024 | FEAT-002 Project Foundation - Laravel | Implement transaction boundary ownership in application services only | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-025 | FEAT-002 Project Foundation - Laravel | Implement the idempotency registry at the application boundary | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-043 | FEAT-003 Project Foundation - Database | Enforce bound parameters everywhere and forbid concatenated statements | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-044 | FEAT-003 Project Foundation - Database | Forbid geography in any table, column, index, constraint name or partition | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-045 | FEAT-003 Project Foundation - Database | Establish naming, index-naming and constraint-naming conventions | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-487 | FEAT-037 Verification & Test Infrastructure | Wire the six verification levels so that a failure at an earlier level stops the later ones | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-488 | FEAT-037 Verification & Test Infrastructure | Build the consolidated verification obligation register with owning levels | No | No | Not Started | TBD | No | Not Tested | No
| Day 3 | CMP-IMP-504 | FEAT-038 Build, Pipeline & Environments | Implement the four-gate pipeline running every level below each gate | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-014 | FEAT-001 Project Foundation - Android | Add accessibility hooks to the Compose surface scaffolding | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-015 | FEAT-001 Project Foundation - Android | Implement client version negotiation against the platform | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-016 | FEAT-001 Project Foundation - Android | Build Screen 32 - Version unsupported | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-017 | FEAT-001 Project Foundation - Android | Implement the immutable screen-state contract and state-holder base | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-026 | FEAT-002 Project Foundation - Laravel | Implement after-commit domain event dispatch | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-027 | FEAT-002 Project Foundation - Laravel | Implement the seven job families with priority separation | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-046 | FEAT-003 Project Foundation - Database | Set up the migration framework with a destructive-migration approval path | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-047 | FEAT-003 Project Foundation - Database | Create the three database accounts and their grants | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-048 | FEAT-003 Project Foundation - Database | Declare foreign key policy: enforced within op_, none into proj_, none from mch_ into op_ | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-461 | FEAT-035 API Contract & Versioning | Implement URI path versioning supporting version N and N minus 1 | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-462 | FEAT-035 API Contract & Versioning | Implement GET /versions reporting the supported version range | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-463 | FEAT-035 API Contract & Versioning | Implement the four error branches with four distinct shapes | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-489 | FEAT-037 Verification & Test Infrastructure | Complete the integrity-critical mapping TC-017 | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-490 | FEAT-037 Verification & Test Infrastructure | Implement the thirteen structural rules at gate 1 with no suppression path for the eight non-suppressible | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-491 | FEAT-037 Verification & Test Infrastructure | Establish domain test infrastructure running without a database, framework or network | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-505 | FEAT-038 Build, Pipeline & Environments | Require every non-suppressible obligation to pass at gate 4 with no exception | No | No | Not Started | TBD | No | Not Tested | No
| Day 4 | CMP-IMP-506 | FEAT-038 Build, Pipeline & Environments | Build one artefact per unit per commit and promote it unchanged | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-018 | FEAT-001 Project Foundation - Android | Implement the four designed screen conditions: loaded, loading, empty, failed | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-019 | FEAT-001 Project Foundation - Android | Implement the four failure treatments on the client | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-020 | FEAT-001 Project Foundation - Android | Implement status presentation that never relies on colour alone | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-028 | FEAT-002 Project Foundation - Laravel | Make every job idempotent, outcome-recording and failure-visible | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-029 | FEAT-002 Project Foundation - Laravel | Register scheduled work in the scheduled-generation, reconciliation and maintenance families | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-030 | FEAT-002 Project Foundation - Laravel | Implement the port and adapter skeleton with a capability result type | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-049 | FEAT-003 Project Foundation - Database | Record the interface version on tables whose interpretation depends on it | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-050 | FEAT-003 Project Foundation - Database | Establish the integrity constraint register and its verification | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-051 | FEAT-004 Authentication & Session | Create op_users, op_user_credentials and op_sessions migrations | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-066 | FEAT-005 Registration & Phone Verification | Create the op_user_verifications migration retaining attempts and outcomes | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-429 | FEAT-032 Backend Authority & Idempotency | Determine every value affecting shared business state from platform authoritative state | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-430 | FEAT-032 Backend Authority & Idempotency | Reject any client-supplied value purporting to determine an authoritative business value | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-464 | FEAT-035 API Contract & Versioning | Identify refusal reasons rather than return free text | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-465 | FEAT-035 API Contract & Versioning | Carry an as-of marking on every business value in every representation | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-466 | FEAT-035 API Contract & Versioning | Vary representation by relationship rather than by role alone | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-467 | FEAT-035 API Contract & Versioning | Serve JSON only with one representation per resource | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-468 | FEAT-035 API Contract & Versioning | Keep authoritative fields absent from every request schema | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-492 | FEAT-037 Verification & Test Infrastructure | Establish integration test infrastructure against a real database | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-493 | FEAT-037 Verification & Test Infrastructure | Establish contract test infrastructure asserting shape and not behaviour | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-494 | FEAT-037 Verification & Test Infrastructure | Establish database constraint testing | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-507 | FEAT-038 Build, Pipeline & Environments | Ensure an artefact contains no environment value, endpoint or secret | No | No | Not Started | TBD | No | Not Tested | No
| Day 5 | CMP-IMP-508 | FEAT-038 Build, Pipeline & Environments | Record each promotion with artefact identity, gate results and authorising person | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-031 | FEAT-002 Project Foundation - Laravel | Implement the typed, versioned, cached policy configuration store | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-032 | FEAT-002 Project Foundation - Laravel | Implement the configuration-driven state machine engine | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-033 | FEAT-002 Project Foundation - Laravel | Implement application-layer authorisation evaluated deny-by-default | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-052 | FEAT-004 Authentication & Session | Implement the User aggregate constructible only into a valid state | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-053 | FEAT-004 Authentication & Session | Implement POST /sessions to establish an authenticated session | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-054 | FEAT-004 Authentication & Session | Refuse authentication without disclosing which credential element failed | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-067 | FEAT-005 Registration & Phone Verification | Allow a person without an account to initiate registration | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-068 | FEAT-005 Registration & Phone Verification | Require and validate the mandatory registration details including phone number | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-069 | FEAT-005 Registration & Phone Verification | Refuse registration for a phone number already on an active account and offer the login path | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-070 | FEAT-005 Registration & Phone Verification | Assign each account a unique, persistent, never-reused identifier | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-071 | FEAT-005 Registration & Phone Verification | Create the account in an unverified state that does not permit participation | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-431 | FEAT-032 Backend Authority & Idempotency | Reject a request carrying such a value in its entirety and never partially apply it | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-432 | FEAT-032 Backend Authority & Idempotency | Record an attempt to assert an authoritative value as an auditable integrity event | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-433 | FEAT-032 Backend Authority & Idempotency | Return the platform own determination as the authoritative result of every such request | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-434 | FEAT-032 Backend Authority & Idempotency | Permit a client to retain returned values for presentation only | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-438 | FEAT-033 Evidential Log & Audit | Create the ev_evidential_records append-only chained migration | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-469 | FEAT-035 API Contract & Versioning | Model intents as resources rather than as verbs on a resource | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-470 | FEAT-035 API Contract & Versioning | Implement collections with cursor paging and allow-listed filtering | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-471 | FEAT-035 API Contract & Versioning | Write API contract tests asserting shape and not business behaviour | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-495 | FEAT-037 Verification & Test Infrastructure | Establish concurrency testing under genuine parallelism | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-496 | FEAT-037 Verification & Test Infrastructure | Establish induced-failure testing with hooks absent from the production artefact | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-497 | FEAT-037 Verification & Test Infrastructure | Establish client testing infrastructure | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-509 | FEAT-038 Build, Pipeline & Environments | Handle migrations in deployment without rolling them back on rollback | No | No | Not Started | TBD | No | Not Tested | No
| Day 6 | CMP-IMP-510 | FEAT-038 Build, Pipeline & Environments | Define and deploy the five deployment units | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-034 | FEAT-002 Project Foundation - Laravel | Implement the four-class backend error model | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-035 | FEAT-002 Project Foundation - Laravel | Bootstrap the safety surface as a separately bootable entry point | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-036 | FEAT-002 Project Foundation - Laravel | Add structural enforcement tests for the backend | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-037 | FEAT-002 Project Foundation - Laravel | Implement repository interfaces in Domain with the ORM behind them | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-055 | FEAT-004 Authentication & Session | Admit a user holding a valid existing session without re-authentication | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-056 | FEAT-004 Authentication & Session | Implement POST /sessions/current/refresh within the session bound | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-057 | FEAT-004 Authentication & Session | Implement DELETE /sessions/current terminating a session and preventing reuse | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-058 | FEAT-004 Authentication & Session | Route a user whose account is not phone-verified to verification rather than into the app | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-060 | FEAT-004 Authentication & Session | Build Screen 2 - Log in | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-061 | FEAT-004 Authentication & Session | Implement the login state holder and client use case | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-064 | FEAT-004 Authentication & Session | Implement the platform gateway session carriage | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-072 | FEAT-005 Registration & Phone Verification | Implement POST /verifications to initiate phone verification on account creation | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-073 | FEAT-005 Registration & Phone Verification | Implement POST /verifications/{id}/attempts to submit a demonstration of control | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-074 | FEAT-005 Registration & Phone Verification | Hold phone-verified status as backend state and reject any client assertion of it | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-149 | FEAT-011 Ride Search & Route Matching | Implement POST /searches as a query resource returning a ranked result set | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-150 | FEAT-011 Ride Search & Route Matching | Resolve the requested travel segment from the stated origin and destination | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-151 | FEAT-011 Ride Search & Route Matching | Refuse a search where an origin or destination cannot be resolved | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-152 | FEAT-011 Ride Search & Route Matching | Identify published rides that are candidates for the requested date | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-435 | FEAT-032 Backend Authority & Idempotency | Resolve any client and platform state disagreement in favour of the platform and correct the client | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-436 | FEAT-032 Backend Authority & Idempotency | Require an idempotency key on every state-changing operation | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-498 | FEAT-037 Verification & Test Infrastructure | Require a negative test for every integrity-critical requirement | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-499 | FEAT-037 Verification & Test Infrastructure | Establish accessibility verification as a specified procedure with a recorded outcome | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-500 | FEAT-037 Verification & Test Infrastructure | Generate test data only; never copy production personal data into any environment | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-511 | FEAT-038 Build, Pipeline & Environments | Ensure the application unit holds no session state in instance memory | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-512 | FEAT-038 Build, Pipeline & Environments | Ensure exactly one scheduler instance is active | No | No | Not Started | TBD | No | Not Tested | No
| Day 7 | CMP-IMP-513 | FEAT-038 Build, Pipeline & Environments | Make each job family independently drainable and pausable in deployment | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-059 | FEAT-004 Authentication & Session | Terminate the session locally when the platform is unreachable and invalidate centrally on next contact | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-062 | FEAT-004 Authentication & Session | Implement session material storage on the device | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-063 | FEAT-004 Authentication & Session | Clear cached business data on the device when a session ends | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-065 | FEAT-004 Authentication & Session | Write authentication and session verification tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-075 | FEAT-005 Registration & Phone Verification | Permit a further verification attempt within the applied limits | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-077 | FEAT-005 Registration & Phone Verification | Preserve entered registration details for retry when the messaging channel is unavailable | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-078 | FEAT-005 Registration & Phone Verification | Leave an abandoned registration unverified and permit restart with the same number | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-080 | FEAT-005 Registration & Phone Verification | Build Screen 1 - Verification | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-081 | FEAT-005 Registration & Phone Verification | Implement the registration and verification state holder and client use cases | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-095 | FEAT-007 Roles & Authorisation | Determine the roles held by an actor before permitting any action | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-096 | FEAT-007 Roles & Authorisation | Permit an action only where a role held by the actor allows it | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-103 | FEAT-008 Vehicle Management | Create the op_vehicles migration with platform-written lawful capacity | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-153 | FEAT-011 Ride Search & Route Matching | Implement the route-overlap assessment as a domain service | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-154 | FEAT-011 Ride Search & Route Matching | Include a ride only where its route overlaps the requested segment | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-155 | FEAT-011 Ride Search & Route Matching | Include a ride whose route overlaps the segment even where the segment is only part of the route | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-437 | FEAT-032 Backend Authority & Idempotency | Write backend authority tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-439 | FEAT-033 Evidential Log & Audit | Implement one evidential writer as the only path into ev_ | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-440 | FEAT-033 Evidential Log & Audit | Enforce append-only at the database level | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-501 | FEAT-037 Verification & Test Infrastructure | Implement the coverage and verification report shape | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-502 | FEAT-037 Verification & Test Infrastructure | Publish the untested-because-undecided set with every readiness statement | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-514 | FEAT-038 Build, Pipeline & Environments | Implement the secret store with rotation and compromise procedures | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-515 | FEAT-038 Build, Pipeline & Environments | Implement client build, signing and distribution verification | No | No | Not Started | TBD | No | Not Tested | No
| Day 8 | CMP-IMP-516 | FEAT-038 Build, Pipeline & Environments | Ensure a client release does not require a platform release and vice versa | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-082 | FEAT-005 Registration & Phone Verification | Write registration and verification tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-083 | FEAT-006 Profile & Counterparty Disclosure | Implement GET /profile returning the authenticated user own profile | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-084 | FEAT-006 Profile & Counterparty Disclosure | Implement PATCH /profile with validation retaining the previous profile on rejection | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-085 | FEAT-006 Profile & Counterparty Disclosure | Require phone verification before a changed phone number takes effect | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-087 | FEAT-006 Profile & Counterparty Disclosure | Implement GET /users/{id} as a relationship-limited counterparty representation | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-088 | FEAT-006 Profile & Counterparty Disclosure | Retrieve counterparty verification standing from backend state on every display | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-097 | FEAT-007 Roles & Authorisation | Refuse an unpermitted action without partial application and record the refusal | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-098 | FEAT-007 Roles & Authorisation | Distinguish user roles from administrative roles and restrict each independently | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-100 | FEAT-007 Roles & Authorisation | Permit a single account to hold passenger and driver roles concurrently | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-104 | FEAT-008 Vehicle Management | Implement the Vehicle aggregate | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-105 | FEAT-008 Vehicle Management | Implement POST /vehicles to register a vehicle against a driver account | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-106 | FEAT-008 Vehicle Management | Record the lawful passenger capacity of each registered vehicle | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-156 | FEAT-011 Ride Search & Route Matching | Implement the two-phase filter: coarse spatial index then precise geometry | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-157 | FEAT-011 Ride Search & Route Matching | Assess pickup compatibility between the passenger origin and the ride route | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-158 | FEAT-011 Ride Search & Route Matching | Assess drop compatibility between the passenger destination and the ride route | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-159 | FEAT-011 Ride Search & Route Matching | Assess whether the ride direction of travel is compatible with the requested journey | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-160 | FEAT-011 Ride Search & Route Matching | Assess whether the ride departure time is compatible with the requested travel time | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-222 | FEAT-015 Fare & Payment Initiation | Calculate the amount payable under platform authority alone | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-223 | FEAT-015 Fare & Payment Initiation | Reject any client-supplied amount payable | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-441 | FEAT-033 Evidential Log & Audit | Implement the keyed evidential chain with the key held outside the database | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-442 | FEAT-033 Evidential Log & Audit | Record every ride, request, booking, payment, trip, safety incident and operator action as an auditable event | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-443 | FEAT-033 Evidential Log & Audit | Record what occurred, when, its subject and the party responsible with each event | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-472 | FEAT-036 Security Controls | Establish and enforce the four trust boundaries | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-473 | FEAT-036 Security Controls | Implement session bounds, refresh limits and non-replayable session material | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-474 | FEAT-036 Security Controls | Store authentication credentials in non-recoverable form | No | No | Not Started | TBD | No | Not Tested | No
| Day 9 | CMP-IMP-519 | FEAT-038 Build, Pipeline & Environments | Verify the pipeline gates themselves | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-089 | FEAT-006 Profile & Counterparty Disclosure | Present verification standing before the user commits to travel | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-090 | FEAT-006 Profile & Counterparty Disclosure | Present standing as unknown, not as verified or unverified, when it cannot be retrieved | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-091 | FEAT-006 Profile & Counterparty Disclosure | Build Screen 3 - Profile | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-092 | FEAT-006 Profile & Counterparty Disclosure | Build Screen 19 - Counterparty profile | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-093 | FEAT-006 Profile & Counterparty Disclosure | Build Screen 4 - Home entry point | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-094 | FEAT-006 Profile & Counterparty Disclosure | Write profile and disclosure tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-101 | FEAT-007 Roles & Authorisation | Build Screen 31 - Settings including logout and driver-role controls | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-102 | FEAT-007 Roles & Authorisation | Write authorisation tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-107 | FEAT-008 Vehicle Management | Permit a driver to register more than one vehicle, each independently selectable | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-108 | FEAT-008 Vehicle Management | Refuse a vehicle registration duplicating one on another account and raise it for operator review | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-109 | FEAT-008 Vehicle Management | Implement PATCH /vehicles/{id} with an active-commitment determination before applying | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-110 | FEAT-008 Vehicle Management | Implement DELETE /vehicles/{id} as a state change refusing withdrawal in active use | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-115 | FEAT-009 Ride Publishing | Create op_rides and op_ride_routes migrations with a spatially indexed bounding envelope | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-116 | FEAT-009 Ride Publishing | Create the op_ride_seat_allocations narrow row with its database constraint | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-161 | FEAT-011 Ride Search & Route Matching | Exclude from bookable results any ride with fewer available seats than requested | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-162 | FEAT-011 Ride Search & Route Matching | Evaluate seat availability from backend state on every search, never from a cached count | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-163 | FEAT-011 Ride Search & Route Matching | Present a ride as compatible only where every compatibility assessment is satisfied | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-164 | FEAT-011 Ride Search & Route Matching | Rank compatible rides on a basis the platform can express to the passenger | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-165 | FEAT-011 Ride Search & Route Matching | Express, for each result, the degree of route overlap with the requested segment | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-224 | FEAT-015 Fare & Payment Initiation | Present the total amount payable to the passenger before any payment is initiated | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-225 | FEAT-015 Fare & Payment Initiation | Do not initiate a payment for an amount the passenger has not been shown | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-226 | FEAT-015 Fare & Payment Initiation | Re-present the total and require the passenger to see it where the amount changes | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-227 | FEAT-015 Fare & Payment Initiation | Freeze the fare before the handoff | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-444 | FEAT-033 Evidential Log & Audit | Retain records durably and prevent silent alteration or deletion | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-445 | FEAT-033 Evidential Log & Audit | Do not report an action as complete where its auditable record cannot be written | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-446 | FEAT-033 Evidential Log & Audit | Raise for reconciliation any action that took effect but whose record could not be written | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-448 | FEAT-033 Evidential Log & Audit | Run evidential chain verification as scheduled reconciliation | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-450 | FEAT-033 Evidential Log & Audit | Write evidential log tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-475 | FEAT-036 Security Controls | Implement attempt bounding on authentication and verification | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-476 | FEAT-036 Security Controls | Implement per-column protection at rest for identity evidence and payment-related data | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-477 | FEAT-036 Security Controls | Implement protection in transit end to end | No | No | Not Started | TBD | No | Not Tested | No
| Day 10 | CMP-IMP-478 | FEAT-036 Security Controls | Prevent injection by construction across every data path | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-111 | FEAT-008 Vehicle Management | Present the vehicle information recorded against a ride, including on completed trips | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-112 | FEAT-008 Vehicle Management | Build Screen 5 - Vehicles: list, add, edit, withdraw | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-113 | FEAT-008 Vehicle Management | Implement the vehicle state holder, client use cases and repository | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-114 | FEAT-008 Vehicle Management | Write vehicle management tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-117 | FEAT-009 Ride Publishing | Implement the Ride aggregate owning SeatAllocation within its consistency boundary | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-118 | FEAT-009 Ride Publishing | Implement POST /rides to publish a ride with origin, destination, date and departure time | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-119 | FEAT-009 Ride Publishing | Resolve and record the route against which passenger segments are overlapped | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-120 | FEAT-009 Ride Publishing | Refuse publication where a route cannot be resolved and state that the journey was not understood | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-142 | FEAT-010 Ride Preferences | Create the op_ride_preferences migration storing undeclared as undeclared | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-166 | FEAT-011 Ride Search & Route Matching | Express the pickup and drop relationship in terms the passenger can act on | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-167 | FEAT-011 Ride Search & Route Matching | Re-evaluate results in full when a search is repeated | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-168 | FEAT-011 Ride Search & Route Matching | Return a successful empty result rather than a refusal when no candidate matches | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-169 | FEAT-011 Ride Search & Route Matching | State that search is unavailable rather than return an unmatched or unranked result set | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-170 | FEAT-011 Ride Search & Route Matching | Build Screen 10 - Search | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-228 | FEAT-015 Fare & Payment Initiation | Implement POST /bookings/{id}/payments to initiate payment for the established amount | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-229 | FEAT-015 Fare & Payment Initiation | Implement the UPI handoff on the client | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-230 | FEAT-015 Fare & Payment Initiation | Discard the response returned by the client-side UPI application | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-231 | FEAT-015 Fare & Payment Initiation | Ensure no payment instrument surface exists anywhere in the system | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-236 | FEAT-016 Payment Verification & Reconciliation | Create op_payments and op_payment_attempts migrations with a three-value CHECK constraint | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-451 | FEAT-034 Degraded Operation & Configuration | Detect the unavailability of a supporting service and determine which capabilities are affected | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-452 | FEAT-034 Degraded Operation & Configuration | Withdraw or mark an affected capability rather than present it as working | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-479 | FEAT-036 Security Controls | Ensure no payment credential is ever received by any component | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-480 | FEAT-036 Security Controls | Implement the client-side security posture: the device holds nothing worth stealing | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-481 | FEAT-036 Security Controls | Supply secrets at deploy time and never in an artefact | No | No | Not Started | TBD | No | Not Tested | No
| Day 11 | CMP-IMP-482 | FEAT-036 Security Controls | Record security events as evidential records | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-121 | FEAT-009 Ride Publishing | Defer publication rather than publish without a route when the mapping service is unavailable | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-122 | FEAT-009 Ride Publishing | Reject a ride whose departure time has already passed | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-123 | FEAT-009 Ride Publishing | Require exactly one vehicle registered to the publishing driver and route drivers with none to registration | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-124 | FEAT-009 Ride Publishing | Enforce that seats offered never exceed the vehicle recorded lawful capacity | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-125 | FEAT-009 Ride Publishing | Validate the publishing driver eligibility before accepting a ride and state the refusal reason | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-126 | FEAT-009 Ride Publishing | Make an accepted ride discoverable to compatible searches | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-127 | FEAT-009 Ride Publishing | Record the publication of a ride as an auditable event | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-143 | FEAT-010 Ride Preferences | Present the preference set for declaration on every published ride | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-144 | FEAT-010 Ride Preferences | Record the driver declared position on each preference | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-145 | FEAT-010 Ride Preferences | Present an undeclared preference as undeclared and infer nothing | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-146 | FEAT-010 Ride Preferences | Display declared preferences to a passenger before any commitment is sought | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-147 | FEAT-010 Ride Preferences | Build Screen 8 - Ride preferences | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-148 | FEAT-010 Ride Preferences | Write ride preference tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-171 | FEAT-011 Ride Search & Route Matching | Build Screen 11 - Results | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-172 | FEAT-011 Ride Search & Route Matching | Implement the search state holder, client use cases and repository | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-173 | FEAT-011 Ride Search & Route Matching | Write search and matching tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-174 | FEAT-012 Ride Detail & Commitment Surface | Present, for each result, the fare, departure time and number of available seats | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-175 | FEAT-012 Ride Detail & Commitment Surface | Present, for each result, the driver information and verification indicators required for a trust decision | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-176 | FEAT-012 Ride Detail & Commitment Surface | Present, for each result, the vehicle information recorded against the ride | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-177 | FEAT-012 Ride Detail & Commitment Surface | Re-check availability when a passenger proceeds from a result | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-179 | FEAT-012 Ride Detail & Commitment Surface | Implement GET /rides/{id} as a relationship-limited ride representation | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-184 | FEAT-013 Ride Request | Create the op_ride_requests migration with state referencing policy configuration | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-232 | FEAT-015 Fare & Payment Initiation | Refuse to start a payment the platform cannot verify when the ecosystem is unavailable | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-233 | FEAT-015 Fare & Payment Initiation | Build Screen 15 - Payment handoff | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-235 | FEAT-015 Fare & Payment Initiation | Write fare and initiation tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-237 | FEAT-016 Payment Verification & Reconciliation | Implement the Payment aggregate permitting exactly three states and no fourth | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-238 | FEAT-016 Payment Verification & Reconciliation | Initiate independent verification of every payment attempt including abandoned ones | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-239 | FEAT-016 Payment Verification & Reconciliation | Implement the payment-verification job family | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-253 | FEAT-017 Ledger | Create the led_ledger_entries append-only migration | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-453 | FEAT-034 Degraded Operation & Configuration | Inform the affected actor what is unavailable and what remains available | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-454 | FEAT-034 Degraded Operation & Configuration | Never resolve an unknown outcome by assumption in either direction while a service is unavailable | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-455 | FEAT-034 Degraded Operation & Configuration | Withdraw a capability entirely rather than degrade it where degrading would compromise an absolute rule | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-456 | FEAT-034 Degraded Operation & Configuration | Resume normal behaviour and process deferred work when a service is restored | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-457 | FEAT-034 Degraded Operation & Configuration | Implement GET /configuration delivering platform configuration to the client | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-458 | FEAT-034 Degraded Operation & Configuration | Consume delivered configuration on the client for cadence and staleness bounds | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-459 | FEAT-034 Degraded Operation & Configuration | Implement GET /health distinguishing platform health from dependency health | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-483 | FEAT-036 Security Controls | Implement the abuse and automated-access posture with bounds held as configuration | No | No | Not Started | TBD | No | Not Tested | No
| Day 12 | CMP-IMP-484 | FEAT-036 Security Controls | Implement an executable check for every checkable security property | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-128 | FEAT-009 Ride Publishing | Allow a driver to pre-fill a new ride from a previously published ride with full re-evaluation | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-129 | FEAT-009 Ride Publishing | Implement DELETE /rides/{id} to withdraw a ride carrying no confirmed booking | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-130 | FEAT-009 Ride Publishing | Refuse withdrawal of a ride carrying a confirmed booking | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-131 | FEAT-009 Ride Publishing | Close any pending ride request on a withdrawn ride and inform its requester | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-132 | FEAT-009 Ride Publishing | Implement GET /rides presenting a driver published rides from backend state | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-133 | FEAT-009 Ride Publishing | Implement GET /rides/{id}/seats returning authoritative seat availability | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-134 | FEAT-009 Ride Publishing | Invalidate stored route geometry when a ride is amended | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-135 | FEAT-009 Ride Publishing | Build Screen 7 - Publish ride | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-178 | FEAT-012 Ride Detail & Commitment Surface | Inform a passenger and return them to results where a ride is withdrawn while viewing | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-180 | FEAT-012 Ride Detail & Commitment Surface | Build Screen 12 - Ride detail, passenger view | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-181 | FEAT-012 Ride Detail & Commitment Surface | Build Screen 13 - Commitment surface | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-183 | FEAT-012 Ride Detail & Commitment Surface | Write ride detail and commitment tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-185 | FEAT-013 Ride Request | Implement the RideRequest aggregate | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-186 | FEAT-013 Ride Request | Implement POST /ride-requests to request a stated number of seats on a ride | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-187 | FEAT-013 Ride Request | Re-confirm seat availability from backend state at the moment a request is made | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-188 | FEAT-013 Ride Request | Decline a request where seats are no longer available, state why, and consume no seat | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-200 | FEAT-014 Booking & Seat Allocation | Create the op_bookings migration carrying the platform-computed fare and payment reference | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-240 | FEAT-016 Payment Verification & Reconciliation | Determine payment status solely from platform verification | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-241 | FEAT-016 Payment Verification & Reconciliation | Set payment status to failed on established failure and release any held seats | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-242 | FEAT-016 Payment Verification & Reconciliation | Set payment status to pending and route for reconciliation where the outcome cannot be established | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-243 | FEAT-016 Payment Verification & Reconciliation | Re-attempt verification of a pending payment on platform initiative | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-244 | FEAT-016 Payment Verification & Reconciliation | Record every payment attempt and its verified outcome | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-245 | FEAT-016 Payment Verification & Reconciliation | Inform the passenger of the verified outcome and never of the outcome reported by the UPI application | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-254 | FEAT-017 Ledger | Record a ledger entry for every movement of value | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-255 | FEAT-017 Ledger | Produce balanced entries immediately on every verified payment | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-256 | FEAT-017 Ledger | Compute balances rather than store them | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-460 | FEAT-034 Degraded Operation & Configuration | Write degraded operation tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-486 | FEAT-036 Security Controls | Write security verification tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-520 | FEAT-039 Observability & Operations | Instrument the eighteen measurement points required from first release | No | No | Not Started | TBD | No | Not Tested | No
| Day 13 | CMP-IMP-521 | FEAT-039 Observability & Operations | Instrument the nine mobile measurement points | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-136 | FEAT-009 Ride Publishing | Build Screen 6 - My published rides | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-137 | FEAT-009 Ride Publishing | Build Screen 9 - Ride detail, driver view | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-138 | FEAT-009 Ride Publishing | Implement the ride publishing state holder, client use cases and repository | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-141 | FEAT-009 Ride Publishing | Write ride publishing tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-189 | FEAT-013 Ride Request | Present the requesting passenger verification standing to the driver | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-190 | FEAT-013 Ride Request | Refuse a request from a passenger who is not eligible to request and state the reason | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-191 | FEAT-013 Ride Request | Inform both the passenger and the driver of the outcome of a ride request | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-192 | FEAT-013 Ride Request | Implement GET /ride-requests for own requests and requests on own rides | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-193 | FEAT-013 Ride Request | Implement DELETE /ride-requests/{id} to allow a passenger to withdraw a request | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-194 | FEAT-013 Ride Request | Build Screen 14 - Request seats | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-201 | FEAT-014 Booking & Seat Allocation | Implement the Booking aggregate with the confirmed-requires-verified-payment invariant | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-202 | FEAT-014 Booking & Seat Allocation | Implement the SeatAllocation invariant that confirmed seats never exceed seats offered | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-203 | FEAT-014 Booking & Seat Allocation | Implement pessimistic row locking on the allocation record plus the database constraint | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-204 | FEAT-014 Booking & Seat Allocation | Implement POST /bookings creating a booking in pending state | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-246 | FEAT-016 Payment Verification & Reconciliation | Inform a passenger that a payment is being confirmed and report no success while pending | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-248 | FEAT-016 Payment Verification & Reconciliation | Implement the provider callback surface as a trigger that enqueues verification and nothing else | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-249 | FEAT-016 Payment Verification & Reconciliation | Ensure payment status is never settable through the interface | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-250 | FEAT-016 Payment Verification & Reconciliation | Ensure payment verification outcomes are never cached | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-251 | FEAT-016 Payment Verification & Reconciliation | Build Screen 16 - Payment status | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-252 | FEAT-016 Payment Verification & Reconciliation | Write payment integrity tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-257 | FEAT-017 Ledger | Surface a discrepancy where a ledger does not reconcile rather than present a concealing balance | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-259 | FEAT-017 Ledger | Write ledger tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-260 | FEAT-018 Trip Execution | Create op_trips and op_trip_participants migrations capturing values not references alone | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-522 | FEAT-039 Observability & Operations | Integrate crash reporting, performance monitoring and analytics on the client | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-523 | FEAT-039 Observability & Operations | Distinguish platform health from dependency health in operational reporting | No | No | Not Started | TBD | No | Not Tested | No
| Day 14 | CMP-IMP-524 | FEAT-039 Observability & Operations | Record the artefact identity in every operational log line | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-195 | FEAT-013 Ride Request | Build the requests-on-ride view within Screen 9 | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-199 | FEAT-013 Ride Request | Write ride request tests | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-205 | FEAT-014 Booking & Seat Allocation | Determine seat availability solely from platform state and reject any client-supplied seat count | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-206 | FEAT-014 Booking & Seat Allocation | Confirm a booking only where seats remain available at the moment of confirmation | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-207 | FEAT-014 Booking & Seat Allocation | Confirm a booking only where payment status is verified | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-208 | FEAT-014 Booking & Seat Allocation | Refuse confirmation where seats became unavailable and initiate the return of any value taken | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-209 | FEAT-014 Booking & Seat Allocation | Do not confirm, and release any held seats, where payment is not verified | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-210 | FEAT-014 Booking & Seat Allocation | Reject any client assertion that a booking is confirmed | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-211 | FEAT-014 Booking & Seat Allocation | Allocate the requested seats to a confirmed booking | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-212 | FEAT-014 Booking & Seat Allocation | Commit seat allocation, booking confirmation, ledger entry and payment status change in one transaction | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-213 | FEAT-014 Booking & Seat Allocation | Record the confirmation of a booking as an auditable event | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-214 | FEAT-014 Booking & Seat Allocation | Inform both the passenger and the driver when a booking is confirmed | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-215 | FEAT-014 Booking & Seat Allocation | Implement GET /bookings presenting bookings from backend state | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-220 | FEAT-014 Booking & Seat Allocation | Write concurrency tests proving overbooking is impossible under genuine parallelism | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-261 | FEAT-018 Trip Execution | Implement the Trip aggregate with the start-requires-confirmed-booking invariant | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-262 | FEAT-018 Trip Execution | Implement POST /trips/{id}/start allowing a driver to begin a trip | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-263 | FEAT-018 Trip Execution | Refuse to begin a trip against a ride with no confirmed booking | No | No | Not Started | TBD | No | Not Tested | No
| Day 15 | CMP-IMP-274 | FEAT-019 Live Position Tracking | Create the op_trip_positions migration carrying two distinct instants | No | No | Not Started | TBD | No | Not Tested | No

## 05_Commits
CMP - COMMITS
No commit hash is invented. Record TBD until a real commit exists. One row per commit.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Commit ID | Date | Day | Work ID | Feature | Commit Hash | Commit Message | Branch | Author | Files Changed | Status | Notes

## 06_Pushes
CMP - PUSHES
A commit is not a push. Record the push separately so the two stages cannot be confused.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Push ID | Date | Day | Work ID | Commit Hash | Branch | Remote | Push Status | Push Date | Notes

## 07_Testing
CMP - TESTING
CMP-DOC-18 requires a negative test for every integrity-critical requirement (FR-04). Record positive and negative cases as separate rows.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Test ID | Date | Day | Work ID | Feature | Test Type | Environment | Test Description | Expected Result | Actual Result | Result | Bug ID | Tester | Notes

## 08_Bugs_Issues
CMP - BUGS ISSUES
A defect in the requirement baseline is not a code bug. Two are already recorded on 09_Decisions - FRD-GAP-006 and FRD-GAP-014.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Bug ID | Date | Work ID | Feature | Severity | Priority | Description | Steps to Reproduce | Expected | Actual | Status | Assigned To | Fixed | Commit Hash | Retested | Notes

## 09_Decisions
CMP - DECISIONS
Seeded from the 24 business decisions of CMP-DOC-01 and the critical functional gaps of CMP-DOC-04. Nothing here has been decided by the documentation - all 24 are open.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Decision ID | Date | Area | Question | Decision | Reason | Impact | Owner | Status | Related Requirement | Related Work ID
BAD-DEC-001 |  | Legal | Obtain a qualified legal opinion on the operating model, including the effect of platform-set fares and platform fees on how the service is characterised. |  |  | Fare and fee design, launch, BAD-DEC-003, 004, 013 | Project Owner | Open | BAD-DEC-001; BAD-RISK-001 | -
BAD-DEC-002 |  | Product | Commission validation research with real commuters and set a delivery horizon. |  |  | Requirement confidence; roadmap dates | Product Owner | Open | BAD-DEC-002; BAD-CON-017 | -
BAD-DEC-003 |  | Payment | Fare model: who sets the fare, any platform constraint, per-seat versus per-booking, and whether a platform fee exists and on what basis. |  |  | FRD-GAP-005 and FRD-GAP-013 - Screen 7 cannot state the amount payable; payment composition unspecifiable | Project Owner | Open | FRD-GAP-005; FRD-GAP-013; BAD-RULE-035 | CMP-IMP-222
BAD-DEC-004 |  | Payment | Driver settlement: how and when drivers receive funds. |  |  | FRD-GAP-015 - no settlement, earnings, payout or withdrawal view exists | Project Owner | Open | FRD-GAP-015; BAD-RULE-036; ADM-105 | -
BAD-DEC-005 |  | Trust | Verification policy: levels, evidence accepted per level, and what each level permits for users and vehicles. |  |  | FRD-GAP-002, 004, 023 - no operator can set a verification standing (ADM-195) | Project Owner | Open | FRD-GAP-002; FRD-GAP-004; FRD-GAP-023 | -
BAD-DEC-006 |  | Operations | Permitted user account states and transitions, and the administrative role set. |  |  | FRD-GAP-003, 024 - the admin surface cannot deploy until one role exists (ADM-168); a safety responder cannot act on an account (ADM-196) | Project Owner | Open | FRD-GAP-003; FRD-GAP-024; ADM-166; ADM-168 | -
BAD-DEC-007 |  | Booking | Booking model: does a request require driver acceptance; are seats held during payment and for how long; is payment taken at booking or on completion. |  |  | FRD-GAP-009, 010, 011 - the transition from interest to committed paid booking. The narrow waist of the product. | Project Owner | Open | FRD-GAP-009; FRD-GAP-010; FRD-GAP-011 | -
BAD-DEC-008 |  | Product | Recurring commute rules: generation horizon, pause semantics, holiday handling, verified-peer auto-acceptance. |  |  | Whole area carries zero functional requirements; no API resource, table or screen (API-138) | Product Owner | Open | CMP-DOC-04 9.2; API-138 | -
BAD-DEC-009 |  | Booking | Cancellation rules: windows, permitted parties, penalties, no-show treatment. |  |  | LIVE DEFECT - FRD-GAP-006: a driver with confirmed bookings has no specified way to cancel. Also FRD-GAP-012, 017, 027. | Project Owner | Open | FRD-GAP-006; FRD-GAP-012; GAP-008 | -
BAD-DEC-010 |  | Payment | Refund policy and entitlement. |  |  | LIVE DEFECT - FRD-GAP-014: the platform can hold a passenger money with no specified means of returning it. | Project Owner | Open | FRD-GAP-014; GAP-009 | -
BAD-DEC-011 |  | Safety | Safety response protocol: what happens on SOS, who acts, in what time, with what authority, and whether emergency contacts are notified automatically. |  |  | LAUNCH GATE - FRD-GAP-020. SOS must not ship (BAD-RISK-005). FRD-FR-195 keeps the control out testably. | Trust & Safety | Open | FRD-GAP-020; BAD-RISK-005 | -
BAD-DEC-012 |  | Product | Rating and review rules: scale, who may rate whom, visibility, and whether ratings affect access or ranking. |  |  | Zero functional requirements. Every trip completed before this produces no reputation, unrecoverably (FRD-RISK-004). | Product Owner | Open | CMP-DOC-04 9.2; FRD-GAP-018 | -
BAD-DEC-013 |  | Product | Reward economics: nature of the wallet, earning and redemption rules, caps, expiry and total budget. |  |  | Zero functional requirements. Uncapped financial liability if built without designed economics (BAD-RISK-010). | Project Owner | Open | CMP-DOC-04 9.2; FRD-GAP-026; NOTIF-082 | -
BAD-DEC-014 |  | Product | Launch strategy: target corridors and how initial supply is seeded. |  |  | BAD-RISK-002 corridor liquidity unmitigated | Product Owner | Open | BAD-DEC-014; BAD-RISK-002 | -
BAD-DEC-015 |  | Architecture | Final booking and trip state models. |  |  | FRD-GAP-016 - the state machine engine is buildable; the definitions are not (GPS 12.1). | Solution Architect | Open | FRD-GAP-016; BADR-13 | -
BAD-DEC-016 |  | Operations | Moderation and enforcement policy: escalation tiers, penalties, appeal rights. |  |  | FRD-GAP-022, 024, 025. ADM-192 additionally prohibits any content-scanning capability. | Project Owner | Open | FRD-GAP-022; FRD-GAP-025; ADM-192 | -
BAD-DEC-017 |  | Publishing | Whether and how a driver may edit a ride after bookings exist. |  |  | FRD-GAP-007 | Product Owner | Open | FRD-GAP-007 | -
BAD-DEC-018 |  | Quality | Set KPI and quality targets. |  |  | Blocks 69 quality targets, 11 of 21 sizing decisions, every alert threshold and 5 verification categories (TR-084, TR-085). | Project Owner | Open | GAP-012; TR-085 | -
BAD-DEC-019 |  | Legal | Position on insurance: what the platform does and does not provide, and how this is communicated. |  |  | The prohibition on claiming cover applies today regardless (FRD 8.5). What the rules positively say is blocked. | Project Owner | Open | BAD-RISK-006; NFR-137 | -
BAD-DEC-020 |  | Product | Approve or amend the proposed MVP scope in CMP-DOC-01 24. |  |  | Phase 1 undefined. The proposed scope is a RECOMMENDATION; none of its six entry preconditions is satisfied. | Project Owner | Open | BAD-DEC-020 | -
BAD-DEC-021 |  | Privacy | Data retention and deletion policy, and the account-closure path. |  |  | FRD-GAP-028, 029. Location history accumulates without bound today (FRD-RISK-007). Blocks the restore reconciliation procedure. | Project Owner | Open | FRD-GAP-028; FRD-GAP-029; DB 13.2 | -
BAD-DEC-022 |  | Privacy | Privacy boundaries between users: phone numbers, precise locations, home locations, live-share audience. |  |  | FRD-GAP-001, 008, 019, 021. Screen 24 is Partial for this reason. | Project Owner | Open | FRD-GAP-001; FRD-GAP-008; FRD-GAP-019; FRD-GAP-021 | -
BAD-DEC-023 |  | Brand | Final product and brand name. |  |  | User-facing asset rework. All strings are in resources so the change is contained (MOB-012). | Project Owner | Open | BAD-DEC-023 | -
BAD-DEC-024 |  | Governance | Confirm the identifier convention. |  |  | Potential renumbering under change control | Documentation Manager | Open | BAD-DEC-024 | -
BAD-DEP-004 |  | Supplier | Select the payment service provider. |  |  | No payment adapter can be written. Seven selection gates are stated in CMP-DOC-14 14.1. | Project Owner | Open | PAY 14.1 | -
BAD-DEP-009 |  | Supplier | Select the hosting provider. |  |  | Sizing decision 10 and through it the other 20; protocol versions and cipher selection (OPS-049). | Project Owner | Open | OPS-049; GAP-014 | -
TECH-DEC-01 |  | Architecture | Choose the route-overlap algorithm and any minimum overlap threshold. |  |  | FRD-RISK-008 - otherwise chosen by whoever implements FRD-FR-077 first. This is the platform differentiating capability. | Solution Architect | Open | BAD-RULE-023; FRD-FR-077 | CMP-IMP-153
TECH-DEC-02 |  | Mobile | Choose the supported Android device range. |  |  | OPS-111 declares a range nobody has chosen (OPS-112). | Solution Architect | Open | MOB-OQ-001; NFR-094 | -
TECH-DEC-03 |  | Mobile | Choose the accessibility conformance standard. |  |  | Accessibility verification cannot be specified against a standard. | Product Owner | Open | MOB-OQ-002; NFR-088 | -
TECH-DEC-04 |  | Database | Set monetary precision. |  |  | DB-032 depends on the largest plausible amount, which depends on scale figures not supplied (GAP-016). | Solution Architect | Open | DB-032; GAP-016 | -
TECH-DEC-05 |  | Security | Set phone verification attempt limits and the cool-off period. |  |  | FRD-FR-010 and 011 are testable once the value is set. | Security Analyst | Open | FRD-OQ-003; NFR-057 | -
TECH-DEC-06 |  | Security | Answer who owns incident response. |  |  | Release readiness criteria 9 and 10 (TR 10.1). | Project Owner | Open | SEC-OQ-07 | -
GAP-013 |  | Security | Own fraud detection and response. |  |  | Unowned through the whole chain: no requirement, no software element, no reservation, no component. | Security Analyst | Open | GAP-005; GAP-013 | -
GAP-016 |  | Architecture | Supply launch scale figures: concurrent bookings, rides per day, active users. |  |  | Three backend architectural assumptions hold only at launch scale; index and partitioning strategy needs the same figure. | Product Owner | Open | BE-OQ-01; GAP-016 | -
GAP-017 |  | Trip | Decide pickup and drop sequencing on a multi-passenger trip. |  |  | FRD-FR-159 is unimplementable for a multi-passenger trip until decided - which is the product premise. | Product Owner | Open | GAP-017; FRD-FR-159 | -
GAP-018 |  | Compliance | Decide how user agreement to the rules of participation is recorded. |  |  | Integrity-critical and not carried forward. Needs a functional requirement, an operation and a table. | Solution Architect | Open | GAP-018; NFR-138 | -
GAP-019 |  | Audit | Decide whether the evidential record carries the originating element, or amend SRS-REQ-128. |  |  | Blocking baselining of CMP-DOC-06. | Solution Architect | Open | GAP-019; SRS-REQ-128 | -
GAP-020 |  | Search | State explicitly that a ride with fewer available seats than requested is excluded from results. |  |  | A decision record prose is not a specification. Blocking baselining of CMP-DOC-04. | Backend Lead | Open | GAP-020; FRD-FR-083 | CMP-IMP-161
DOC-CONFLICT-01 |  | Governance | Reconcile the ratings interface and table in CMP-DOC-10 and CMP-DOC-11 against the zero-requirement position in CMP-DOC-04. |  |  | CMP-DOC-10 11.9 lists POST /trips/{id}/ratings citing FRD-FR-172 (a messaging requirement) and CMP-DOC-11 6.7 lists op_trip_ratings. A developer following CMP-DOC-10 would build a withheld feature. | Documentation Manager | Open | API 11.9; DB 6.7; CMP-DOC-04 9.2 | -
REL-DEC-01 |  | Governance | Decide what constitutes a release gate beyond the 25 non-suppressible obligations. |  |  | A build gate is technical; a release gate is a business decision (TR-118). | Project Owner | Open | TR-115; TC-201 | -

## 10_Dependencies
CMP - DEPENDENCIES
Feature-level build order plus the decision, supplier and approval dependencies that gate construction.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Dependency ID | Work ID | Dependency Type | Dependency | Required By | Status | Owner | Notes
DEP-001 | FEAT-004 | Work Item | FEAT-002 Laravel foundation; FEAT-003 database foundation | FEAT-004 Authentication & Session | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-002 | FEAT-005 | Work Item | FEAT-004 authentication and session | FEAT-005 Registration & Phone Verification | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-003 | FEAT-006 | Work Item | FEAT-004 authentication and session | FEAT-006 Profile & Counterparty Disclosure | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-004 | FEAT-007 | Work Item | FEAT-002 Laravel foundation; FEAT-004 authentication | FEAT-007 Roles & Authorisation | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-005 | FEAT-008 | Work Item | FEAT-007 roles and authorisation | FEAT-008 Vehicle Management | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-006 | FEAT-009 | Work Item | FEAT-008 vehicle management; FEAT-032 backend authority | FEAT-009 Ride Publishing | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-007 | FEAT-010 | Work Item | FEAT-009 ride publishing | FEAT-010 Ride Preferences | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-008 | FEAT-011 | Work Item | FEAT-009 ride publishing | FEAT-011 Ride Search & Route Matching | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-009 | FEAT-012 | Work Item | FEAT-011 search and matching | FEAT-012 Ride Detail & Commitment Surface | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-010 | FEAT-013 | Work Item | FEAT-012 ride detail and commitment surface | FEAT-013 Ride Request | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-011 | FEAT-014 | Work Item | FEAT-013 ride request; FEAT-016 payment verification | FEAT-014 Booking & Seat Allocation | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-012 | FEAT-015 | Work Item | FEAT-014 booking and seat allocation | FEAT-015 Fare & Payment Initiation | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-013 | FEAT-016 | Work Item | FEAT-015 fare and payment initiation; FEAT-017 ledger | FEAT-016 Payment Verification & Reconciliation | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-014 | FEAT-017 | Work Item | FEAT-003 database foundation | FEAT-017 Ledger | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-015 | FEAT-018 | Work Item | FEAT-014 booking and seat allocation | FEAT-018 Trip Execution | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-016 | FEAT-019 | Work Item | FEAT-018 trip execution | FEAT-019 Live Position Tracking | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-017 | FEAT-020 | Work Item | FEAT-019 live position tracking | FEAT-020 Estimates & Multi-Passenger Trip | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-018 | FEAT-021 | Work Item | FEAT-018 trip execution | FEAT-021 Trip History & Records | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-019 | FEAT-022 | Work Item | FEAT-014 booking and seat allocation | FEAT-022 Messaging | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-020 | FEAT-023 | Work Item | FEAT-002 Laravel foundation | FEAT-023 Notifications | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-021 | FEAT-024 | Work Item | FEAT-006 profile | FEAT-024 Emergency Contacts | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-022 | FEAT-025 | Work Item | FEAT-002 Laravel foundation; FEAT-033 evidential log | FEAT-025 Safety Incident Pipeline | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-023 | FEAT-026 | Work Item | FEAT-025 safety incident pipeline | FEAT-026 Safety Centre & Safety Surface | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-024 | FEAT-027 | Work Item | FEAT-002 Laravel foundation; FEAT-033 evidential log | FEAT-027 Admin Foundation & Projections | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-025 | FEAT-028 | Work Item | FEAT-027 admin foundation and projections | FEAT-028 Admin Inspection & Intervention | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-026 | FEAT-029 | Work Item | FEAT-027 admin foundation; FEAT-016 payment verification | FEAT-029 Admin Payment Reconciliation | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-027 | FEAT-030 | Work Item | FEAT-027 admin foundation; FEAT-025 safety pipeline | FEAT-030 Admin Safety & Support | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-028 | FEAT-031 | Work Item | FEAT-027 admin foundation and projections | FEAT-031 Admin Operational Reporting | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-029 | FEAT-032 | Work Item | FEAT-002 Laravel foundation | FEAT-032 Backend Authority & Idempotency | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-030 | FEAT-033 | Work Item | FEAT-002 Laravel foundation; FEAT-003 database foundation | FEAT-033 Evidential Log & Audit | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-031 | FEAT-034 | Work Item | FEAT-032 backend authority | FEAT-034 Degraded Operation & Configuration | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-032 | FEAT-035 | Work Item | FEAT-002 Laravel foundation | FEAT-035 API Contract & Versioning | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-033 | FEAT-036 | Work Item | FEAT-002 Laravel foundation; FEAT-003 database foundation | FEAT-036 Security Controls | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-034 | FEAT-037 | Work Item | FEAT-001 Android foundation; FEAT-002 Laravel foundation | FEAT-037 Verification & Test Infrastructure | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-035 | FEAT-038 | Work Item | FEAT-037 verification and test infrastructure | FEAT-038 Build, Pipeline & Environments | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-036 | FEAT-039 | Work Item | FEAT-038 build, pipeline and environments | FEAT-039 Observability & Operations | Not Ready | Delivery | Build order derived from the architecture and requirement chain.
DEP-037 | - | Business Decision | BAD-DEC-003 fare model | FEAT-009 Ride Publishing; FEAT-015 Fare & Payment Initiation | Blocked | Project Owner | Screen 7 cannot state the amount payable until this is taken (FRD-GAP-005, FRD-GAP-013).
DEP-038 | - | Business Decision | BAD-DEC-007 booking model | FEAT-013 Ride Request; FEAT-014 Booking | Blocked | Project Owner | Three critical gaps from one decision: acceptance, seat holding and payment timing.
DEP-039 | - | Business Decision | BAD-DEC-009 cancellation and no-show | FEAT-009; FEAT-014; FEAT-018; FEAT-043 | Blocked | Project Owner | Live product defect - a driver with confirmed bookings has no way out.
DEP-040 | - | Business Decision | BAD-DEC-010 refund policy | FEAT-014; FEAT-016; FEAT-029; FEAT-043 | Blocked | Project Owner | Live product defect - the platform can hold money it cannot return.
DEP-041 | - | Business Decision | BAD-DEC-005 verification policy | FEAT-007; FEAT-008; FEAT-044 | Blocked | Project Owner | Nothing can set a verification standing until this is taken.
DEP-042 | - | Business Decision | BAD-DEC-006 account states and admin role set | FEAT-027 Admin Foundation; FEAT-044 | Blocked | Project Owner | The administrative surface cannot deploy until at least one role exists (ADM-168).
DEP-043 | - | Business Decision | BAD-DEC-011 safety response protocol | FEAT-026 Safety Centre | Blocked | Trust & Safety | Launch gate. Do not ship SOS. A response capability must also be staffed.
DEP-044 | - | Business Decision | BAD-DEC-018 KPI and quality targets | FEAT-031; FEAT-038; FEAT-039 | Blocked | Project Owner | Blocks 69 quality targets, 11 sizing decisions and every alert threshold.
DEP-045 | - | Business Decision | BAD-DEC-021 retention and closure | FEAT-019; FEAT-038; FEAT-039; FEAT-044 | Blocked | Project Owner | Location history accumulates without bound until this is set (FRD-RISK-007).
DEP-046 | - | Business Decision | BAD-DEC-022 privacy boundaries | FEAT-006; FEAT-012; FEAT-022; FEAT-026 | Blocked | Project Owner | Closes four gaps across disclosure, result precision, messaging availability and trip sharing.
DEP-047 | - | Supplier Selection | BAD-DEP-004 payment service provider | FEAT-016 Payment Verification | Blocked | Project Owner | The port is buildable; the adapter needs a provider. Seven gates in CMP-DOC-14 14.1.
DEP-048 | - | Supplier Selection | SMS/OTP provider | FEAT-005 Registration & Phone Verification | Blocked | Project Owner | Unselected. The port is buildable; the adapter is not.
DEP-049 | - | Supplier Selection | BAD-DEP-009 hosting provider | FEAT-038 Build, Pipeline & Environments | Blocked | Project Owner | Sizing decision 10 and through it the other 20. Blocks all provisioning (OPS-014).
DEP-050 | - | Supplier Selection | Transactional email provider | FEAT-023 Notifications | Blocked | Project Owner | Unselected (README 3.2).
DEP-051 | - | Technical Decision | Route-overlap algorithm and threshold | FEAT-011 Ride Search & Route Matching | Not Ready | Solution Architect | Route to CMP-DOC-07 as a named decision before building 5.1 (FR-06, FRD-RISK-008).
DEP-052 | - | Technical Decision | Monetary precision | FEAT-003 Database Foundation | Not Ready | Solution Architect | Depends on launch scale figures (GAP-016).
DEP-053 | - | Data | Launch scale figures | FEAT-003; FEAT-011; FEAT-038 | Not Ready | Product Owner | Concurrent bookings, rides per day, active users. Three architectural assumptions depend on it.
DEP-054 | - | Document Approval | CMP-DOC-01 to CMP-DOC-20 approval in chain order | All features | Not Ready | Project Owner | Zero of twenty approved. Do not baseline for construction until approved (FRD-RISK-001).
DEP-055 | - | Infrastructure | The 21 sizing decisions | FEAT-038; FEAT-039 | Blocked | Project Owner / DevOps | The sizing class blocks everything downstream of it (TR-081, OPS-014).
DEP-056 | - | External Service | Google Maps Platform, Places and Routes access | FEAT-009; FEAT-011; FEAT-019; FEAT-020 | Not Ready | Delivery | Route resolution, search matching and estimates all depend on it. Cost is attributed (GADR-12).
DEP-057 | - | External Service | Firebase Cloud Messaging, Crashlytics, Performance | FEAT-023; FEAT-039 | Not Ready | Delivery | Notification delivery and client observability.

## 11_Risks
CMP - RISKS
Seeded from the risk registers of CMP-DOC-04, CMP-DOC-20 and CMP-DOC-01. 36 of 183 chain risks are rated at severity 20 or above.
OWNER-MAINTAINED LOG - add one row per event. Drop-downs are on 13_Dropdowns.
Risk ID | Date | Area | Risk | Probability | Impact | Risk Level | Mitigation | Owner | Status | Notes
RISK-001 |  | Requirements | Twenty unapproved predecessor documents. Changes in review propagate into build instructions already acted on. | High | High | Critical | Do not baseline for construction until the chain is approved in order. Track approval as release criterion 1. | Project Owner | Open | FRD-RISK-001; TR criterion 1
RISK-002 |  | Requirements | A developer implements a gap. Faced with an undecided behaviour, someone writes a reasonable-looking flow and business policy is set by default. | High | High | Critical | Every blocked work item in 02_Work_Items names its decision. Escalate, never infer. This is the highest-severity risk in CMP-DOC-04. | Delivery Lead | Open | FRD-RISK-002; FR-10
RISK-003 |  | Product | The two live product defects ship: a driver strands passengers, or the platform holds money it cannot return. | Medium | High | Critical | Close BAD-DEC-009 and BAD-DEC-010 before the first real booking. Neither requires engineering. | Project Owner | Open | FRD-RISK-003; GAP-008; GAP-009
RISK-004 |  | Product | Reputation is never captured. Trips complete while rating is withheld and the history cannot be reconstructed. | High | Medium | High | Resolve BAD-DEC-012 before first release. | Product Owner | Open | FRD-RISK-004
RISK-005 |  | Safety | The SOS control is built because the safety pipeline is fully specified and looks complete. | Medium | High | High | FRD-FR-195 states the prohibition as a testable requirement. FEAT-026 records it as DO NOT BUILD. | Trust & Safety | Open | FRD-RISK-005; BAD-RISK-005
RISK-006 |  | Quality | Integrity requirements are descoped under delivery pressure. 1,412 integrity-critical statements exist across the chain. | Medium | High | High | Every integrity-critical requirement needs a negative test (FR-04). 25 obligations are non-suppressible at gate 4. | QA Analyst | Open | FRD-RISK-006; TC-021
RISK-007 |  | Privacy | Location history accumulates without bound. FRD-FR-148 records position on every trip and no retention rule exists. | High | Medium | High | Resolve BAD-DEC-021 before real trips are tracked. Position history is already separable for independent removal (DB-073). | Project Owner | Open | FRD-RISK-007; FRD-GAP-028
RISK-008 |  | Architecture | The route-overlap algorithm is chosen implicitly by whoever implements FRD-FR-077 first. | High | Medium | High | Route explicitly to CMP-DOC-07 as a named technical decision before building the search feature. | Solution Architect | Open | FRD-RISK-008; FR-06
RISK-009 |  | Governance | Requirements are treated as complete because the count is large, masking that three functional areas are empty. | Medium | Medium | Medium | CMP-DOC-04 9.2 states the empty areas. FEAT-040 to FEAT-042 carry them as explicitly withheld. | Documentation Manager | Open | FRD-RISK-009
RISK-010 |  | Delivery | A structural rule is relaxed under delivery pressure. Recorded independently by six documents - the most common severity-20 risk in the chain. | High | High | Critical | Eight of thirteen structural rules have no suppression path in the pipeline. Gate 4 admits no exception. | Delivery Lead | Open | TR-087; TC-038; OPS-093
RISK-011 |  | Delivery | An unresolved decision is resolved by default rather than decided - the second most common severity-20 theme. | High | High | Critical | 66 work items are marked Blocked with the deciding item named. None may be started. | Project Owner | Open | TR-088; TR-084
RISK-012 |  | Delivery | A distinction collapses in implementation - implemented read as committed, committed read as pushed, a passing test read as readiness. | High | Medium | High | The tracker separates Implemented, Committed, Pushed, Tested, Reviewed and Completed as independent stages, each with its own log sheet. | Delivery Lead | Open | TR-121; TC-181
RISK-013 |  | Planning | The 15-day sprint is read as a capacity commitment. Day allocation here is dependency-ordered, not capacity-fitted, and no team size has been supplied. | High | High | Critical | 01_Dashboard states total effort against the 15-day window. BAD-CON-017 records that no budget, timeline or team composition exists. | Project Owner | Open | BAD-CON-017; BAD-DEC-002
RISK-014 |  | Infrastructure | Nothing can be provisioned. All 21 sizing decisions are open and the hosting provider is unselected. | High | High | Critical | Resolve BAD-DEP-009 first; it unblocks sizing decision 10 and through it the other 20. | Project Owner / DevOps | Open | TR-081; OPS-014
RISK-015 |  | Security | Fraud is unowned through the entire chain - no requirement, no software element, no reservation, no component. | Medium | High | High | Own it before any real money moves. Recorded as GAP-013 and carried since CMP-DOC-06. | Security Analyst | Open | GAP-005; GAP-013
RISK-016 |  | Operations | A safety responder can close an incident and take no action against the account involved. | High | High | Critical | Resolve BAD-DEC-006. Until then the operational consequence must be understood, not worked around. | Project Owner | Open | ADM-196; FRD-GAP-024
RISK-017 |  | Reporting | A dashboard reports zero for a behaviour that is not implemented, and zero reads as good news. | Medium | High | High | FRD-FR-236 requires a measure to be reported unavailable, never zero. Same rule applied to this workbook. | Product Analyst | Open | FRD-FR-236; ADM-027
RISK-018 |  | Governance | A developer follows CMP-DOC-10 and builds a ratings feature that CMP-DOC-04 withholds. | Medium | Medium | Medium | Recorded as DOC-CONFLICT-01 on 09_Decisions. Reconcile before construction of the trip feature. | Documentation Manager | Open | API 11.9; DB 6.7
RISK-019 |  | Legal | Regulatory characterisation is unknown, particularly if the platform sets fares or takes a fee. | High | High | Critical | Obtain the legal opinion before build (BAD-DEC-001). Do not finalise fare or fee design until then. | Project Owner | Open | BAD-RISK-001
RISK-020 |  | Quality | A passing test suite is read as readiness, when the largest known risks are undecided rather than defective. | High | High | Critical | Any readiness statement must carry the untested-because-undecided set with it. | QA Analyst | Open | TR-119; TR-121

## 12_Document_Traceability
CMP - DOCUMENT TRACEABILITY
One row per work item. Implementation Status is a live reference to 02_Work_Items - it is never typed here. All source documents are at v0.1 Draft; none is approved.
DERIVED SHEET - the only editable column is Notes. Every other value comes from the documentation or from 02_Work_Items.
Work ID | Epic | Feature | Requirement ID | Use Case ID | Document | Document Version | Section / Statement | Implementation Status | Notes
CMP-IMP-001 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-001; MADR-08; ARCH-014 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-001; MADR-08; ARCH-014
CMP-IMP-002 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-001; MOB-002; MOB-003; MOB-005 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-001; MOB-002; MOB-003
CMP-IMP-003 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-007; MOB-161; OPS-108; OPS-109; TC-037 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-007; MOB-161; OPS-108
CMP-IMP-004 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-009; MADR-02; UXDR-02; API-047 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-009; MADR-02; UXDR-02
CMP-IMP-005 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-009; MADR-10; AADR-02 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-009; MADR-10; AADR-02
CMP-IMP-006 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MADR-03; MOB-005 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MADR-03; MOB-005
CMP-IMP-007 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MADR-09; MOB-166 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MADR-09; MOB-166
CMP-IMP-008 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-013; MOB-162; MOB-163; OPS-107; NFR-108 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-013; MOB-162; MOB-163
CMP-IMP-009 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-010; MOB-011; OPS-110; SRS-REQ-125; TC-037 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-010; MOB-011; OPS-110
CMP-IMP-010 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-164; OPS-111; NFR-093; NFR-094 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-164; OPS-111; NFR-093 |  | Decision Required - supported device range is unresolved (MOB-OQ-001, OPS-112).
CMP-IMP-011 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-165; OPS-113; NFR-156 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-165; OPS-113; NFR-156 |  | Budget figure unset (OPS-114, GAP-015). Measure now so a budget can be set from observation.
CMP-IMP-012 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MADR-08; MOB-020; UX-010 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MADR-08; MOB-020; UX-010
CMP-IMP-013 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-012; ARCH-027; NFR-110 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-012; ARCH-027; NFR-110
CMP-IMP-014 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB 5.3; UX-015; NFR-088 | - | TBD | v0.1 Draft | MOB 5.3; UX-015; NFR-088 |  | Decision Required - accessibility conformance standard is unchosen (MOB-OQ-002, UX 15.3).
CMP-IMP-015 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-057; API-024; API-025; API-027 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-057; API-024; API-025
CMP-IMP-016 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | UX-004; UX-005; API-026 | - | CMP-DOC-12 UI/UX Specification | v0.1 Draft | UX-004; UX-005; API-026
CMP-IMP-017 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | MOB-015; MOB-016; MOB-017; UXDR-05; UX-015; UX-016; UX-017 | - | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-015; MOB-016; MOB-017
CMP-IMP-018 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | UXDR-07; UX 5.1 | - | CMP-DOC-12 UI/UX Specification | v0.1 Draft | UXDR-07; UX 5.1
CMP-IMP-019 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | UXDR-03; UX 7; MADR-10; AADR-02 | - | CMP-DOC-12 UI/UX Specification | v0.1 Draft | UXDR-03; UX 7; MADR-10
CMP-IMP-020 | EPIC-01 Foundation & Architecture | FEAT-001 Project Foundation - Android | UXDR-16; UX 15.2 | - | CMP-DOC-12 UI/UX Specification | v0.1 Draft | UXDR-16; UX 15.2
CMP-IMP-021 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-001; BE-004; BADR-01; ARCH-014 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-001; BE-004; BADR-01
CMP-IMP-022 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-002; BE-003; BE-014; BADR-18; TC-037 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-002; BE-003; BE-014
CMP-IMP-023 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-041; BE-042; BE-043; BE-046; BADR-03 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-041; BE-042; BE-043
CMP-IMP-024 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-047; BE-054; ARCH-032; BADR-03 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-047; BE-054; ARCH-032
CMP-IMP-025 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-045; BE-051; BADR-08; ARCH-124; DADR-13 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-045; BE-051; BADR-08
CMP-IMP-026 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-020; BE-022; BE-039; BADR-06 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-020; BE-022; BE-039
CMP-IMP-027 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-131; BE-133; BADR-07 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-131; BE-133; BADR-07
CMP-IMP-028 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-135; BE-136; BE-137; BE-140; BE-141 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-135; BE-136; BE-137
CMP-IMP-029 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-143; BE-145; BE-146; BE-147; BE-148 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-143; BE-145; BE-146
CMP-IMP-030 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-036; BADR-11; ARCH-061 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-036; BADR-11; ARCH-061
CMP-IMP-031 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE 13.1; BADR-12; ARCH-146; DB-008 | - | TBD | v0.1 Draft | BE 13.1; BADR-12; ARCH-146
CMP-IMP-032 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-038; BADR-13; ARCH-037; DB-039 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-038; BADR-13; ARCH-037 |  | Six state models are undecided (BAD-DEC-015 and others). The engine is buildable; the definitions are not.
CMP-IMP-033 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-044; BADR-14; SADR-06; ARCH-031 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-044; BADR-14; SADR-06
CMP-IMP-034 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BADR-17; BE 14.2; AADR-02 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BADR-17; BE 14.2; AADR-02
CMP-IMP-035 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BADR-16; BE-191; OPS-041; AADR-11 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BADR-16; BE-191; OPS-041
CMP-IMP-036 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-009; BE-010; BE-011; BE-012; BE 17.2; TC-037 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-009; BE-010; BE-011
CMP-IMP-037 | EPIC-01 Foundation & Architecture | FEAT-002 Project Foundation - Laravel | BE-037; BE 8.1; BADR-05 | - | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-037; BE 8.1; BADR-05
CMP-IMP-038 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-001; DB-009; DB-010; OPS-024; DADR-02 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-001; DB-009; DB-010
CMP-IMP-039 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-002; DB-003; DB-014; DADR-01 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-002; DB-003; DB-014
CMP-IMP-040 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-021; DB-022; DB-023; DB-024; DADR-03; API-013; API-014 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-021; DB-022; DB-023
CMP-IMP-041 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-025; DB-026; DB-027; DADR-04; API-112 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-025; DB-026; DB-027
CMP-IMP-042 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-031; DB-033; DB-034; DB-035; DB-036; DADR-06 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-031; DB-033; DB-034 |  | Decision Required - monetary precision is unset (DB-032), depending on scale figures not supplied (GAP-016).
CMP-IMP-043 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-038; SADR-09; SEC-119; SEC-121; BE-102 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-038; SADR-09; SEC-119
CMP-IMP-044 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-020; DADR-14; SRS-REQ-101 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-020; DADR-14; SRS-REQ-101
CMP-IMP-045 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-015; DB-016; DB-017; DB-018; DB-019 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-015; DB-016; DB-017
CMP-IMP-046 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB 16; DB-218; DB-219; OPS-034 | - | TBD | v0.1 Draft | DB 16; DB-218; DB-219
CMP-IMP-047 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DADR-09; OPS 11.2; TC 9 | - | CMP-DOC-11 Database Design | v0.1 Draft | DADR-09; OPS 11.2; TC 9
CMP-IMP-048 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-012; DB-013; DB-029; DB-030 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-012; DB-013; DB-029
CMP-IMP-049 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB-040; DB-058; DB-063; DB-070; DADR-16 | - | CMP-DOC-11 Database Design | v0.1 Draft | DB-040; DB-058; DB-063
CMP-IMP-050 | EPIC-01 Foundation & Architecture | FEAT-003 Project Foundation - Database | DB 15; TC 9 | - | TBD | v0.1 Draft | DB 15; TC 9
CMP-IMP-051 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | DB-041; DB-042; DB-044; DB-045 | UC-001; UC-003 | CMP-DOC-11 Database Design | v0.1 Draft | DB-041; DB-042; DB-044
CMP-IMP-052 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | BE-017; BE-019; BE-021; BE-022 | UC-001 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-017; BE-019; BE-021
CMP-IMP-053 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-014; FRD-FR-016; API 11.1; SEC 6 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-014; FRD-FR-016; API 11.1
CMP-IMP-054 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-015; AADR-14; SEC 5 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-015; AADR-14; SEC 5
CMP-IMP-055 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-017; NFR-055 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-017; NFR-055
CMP-IMP-056 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | NFR-055; API 11.1; SEC 6 | UC-003; UC-004 | CMP-DOC-05 Non-Functional Requirements | v0.1 Draft | NFR-055; API 11.1; SEC 6
CMP-IMP-057 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-019; DB-044; NFR-054; API-103 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-019; DB-044; NFR-054
CMP-IMP-058 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-018 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-018
CMP-IMP-059 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-021 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-021
CMP-IMP-060 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | UX 4.1 Screen 2 | UC-003 | TBD | v0.1 Draft | UX 4.1 Screen 2
CMP-IMP-061 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | MOB-015; UXDR-04; MADR-02 | UC-003; UC-004 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-015; UXDR-04; MADR-02
CMP-IMP-062 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | SEC 13.1; SADR-04; SADR-13; MOB 14 | UC-003; UC-004 | TBD | v0.1 Draft | SEC 13.1; SADR-04; SADR-13
CMP-IMP-063 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | FRD-FR-020; SEC 13.3 | UC-003; UC-004 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-020; SEC 13.3
CMP-IMP-064 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | MADR-04; MOB-004; API 9 | UC-003; UC-004 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MADR-04; MOB-004; API 9
CMP-IMP-065 | EPIC-02 Identity & Access | FEAT-004 Authentication & Session | TC-025; TC-029; TC-030; TC-031; FR-04 | UC-003; UC-004 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-025; TC-029; TC-030
CMP-IMP-066 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | DB-043; FRD-FR-011 | UC-001; UC-002 | CMP-DOC-11 Database Design | v0.1 Draft | DB-043; FRD-FR-011
CMP-IMP-067 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-001; API 9.1 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-001; API 9.1
CMP-IMP-068 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-002; FRD-FR-003 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-002; FRD-FR-003
CMP-IMP-069 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-004 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-004
CMP-IMP-070 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-005; DB-022; DB-023; DB-026 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-005; DB-022; DB-023
CMP-IMP-071 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-006; DB-045 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-006; DB-045
CMP-IMP-072 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-007; API 11.1 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-007; API 11.1
CMP-IMP-073 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-008; FRD-FR-009; API 11.1 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-008; FRD-FR-009; API 11.1
CMP-IMP-074 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-009; API-125; DB-041; SADR-08 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-009; API-125; DB-041
CMP-IMP-075 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-010; API-126 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-010; API-126
CMP-IMP-076 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-011; SEC 5.2; NFR-057 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-011; SEC 5.2; NFR-057 |  | Decision Required - attempt limit and cool-off period are unset (FRD-OQ-003, SEC 5.2). The obligation is buildable; the value is not.
CMP-IMP-077 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-012; FRD-FR-255 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-012; FRD-FR-255
CMP-IMP-078 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | FRD-FR-013 | UC-001; UC-002 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-013
CMP-IMP-079 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | BE-036; BADR-11; SADR-11 | UC-001; UC-002 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-036; BADR-11; SADR-11 |  | Decision Required - the SMS/OTP provider is unselected (README 3.2, BAD-DEP series). The port is buildable; the adapter needs a provider.
CMP-IMP-080 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | UX 4.1 Screen 1 | UC-001; UC-002 | TBD | v0.1 Draft | UX 4.1 Screen 1
CMP-IMP-081 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | MOB-015; UXDR-04 | UC-001; UC-002 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-015; UXDR-04
CMP-IMP-082 | EPIC-02 Identity & Access | FEAT-005 Registration & Phone Verification | TC-029; TC-030; FR-04 | UC-001; UC-002 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-083 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-022; API 11.2 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-022; API 11.2
CMP-IMP-084 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-024; FRD-FR-026; API-130 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-024; FRD-FR-026; API-130
CMP-IMP-085 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-025 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-025
CMP-IMP-086 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-023 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-023 |  | Decision Required - the content of the disclosure list is blocked (FRD-GAP-001, BAD-DEC-022). The indicator mechanism is buildable; the list is not.
CMP-IMP-087 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-027; API-128; API-129; SEC 7.3; UXDR-08 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-027; API-128; API-129
CMP-IMP-088 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-027; API-128; API-157 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-027; API-128; API-157
CMP-IMP-089 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-028; UX 9.4 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-028; UX 9.4
CMP-IMP-090 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | FRD-FR-029; UXDR-02 | UC-005; UC-007 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-029; UXDR-02
CMP-IMP-091 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | UX 4.1 Screen 3 | UC-005; UC-007 | TBD | v0.1 Draft | UX 4.1 Screen 3
CMP-IMP-092 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | UX 4.1 Screen 19; UXDR-08 | UC-007 | TBD | v0.1 Draft | UX 4.1 Screen 19; UXDR-08
CMP-IMP-093 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | UX 4.1 Screen 4; UX-010 | - | TBD | v0.1 Draft | UX 4.1 Screen 4; UX-010
CMP-IMP-094 | EPIC-02 Identity & Access | FEAT-006 Profile & Counterparty Disclosure | TC-029; TC-030; FR-04 | UC-005; UC-007 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-095 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | FRD-FR-251; BE-044; SADR-06 | UC-008; UC-080 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-251; BE-044; SADR-06
CMP-IMP-096 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | FRD-FR-252; SEC 7.1 | UC-008; UC-080 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-252; SEC 7.1
CMP-IMP-097 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | FRD-FR-253; BE-053; SADR-15 | UC-008; UC-080 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-253; BE-053; SADR-15
CMP-IMP-098 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | FRD-FR-254; SEC 7.2 | UC-008; UC-080 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-254; SEC 7.2
CMP-IMP-099 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | FRD-FR-030; FRD-FR-031 | UC-008; UC-080 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-030; FRD-FR-031 |  | Decision Required - driver eligibility criteria are blocked (FRD-GAP-002, BAD-DEC-005).
CMP-IMP-100 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | FRD-FR-032 | UC-008; UC-080 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-032
CMP-IMP-101 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | UX 4.1 Screen 31 | UC-004; UC-008 | TBD | v0.1 Draft | UX 4.1 Screen 31
CMP-IMP-102 | EPIC-02 Identity & Access | FEAT-007 Roles & Authorisation | TC-029; TC-030; SEC 19.1; FR-04 | UC-008; UC-080 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; SEC 19.1
CMP-IMP-103 | EPIC-03 Supply | FEAT-008 Vehicle Management | DB-047; DB-048; DB-049; API-132 | UC-010; UC-011; UC-012 | CMP-DOC-11 Database Design | v0.1 Draft | DB-047; DB-048; DB-049
CMP-IMP-104 | EPIC-03 Supply | FEAT-008 Vehicle Management | BE-017; BE-019; BE-021 | UC-010; UC-011; UC-012 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-017; BE-019; BE-021
CMP-IMP-105 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-033; FRD-FR-034; FRD-FR-035; API 11.3 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-033; FRD-FR-034; FRD-FR-035
CMP-IMP-106 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-036; API-132; DB-047 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-036; API-132; DB-047 |  | Decision Required - the source and evidencing of lawful capacity is blocked (FRD-GAP-004, BAD-DEC-005).
CMP-IMP-107 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-037; API 11.3 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-037; API 11.3
CMP-IMP-108 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-038 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-038 |  | Decision Required - whether duplicate registration is ever permitted, and on what evidence, is open (FRD-OQ-004).
CMP-IMP-109 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-039; FRD-FR-040; FRD-FR-041; FRD-FR-042 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-039; FRD-FR-040; FRD-FR-041 |  | Decision Required - which amendments are disqualifying is open (FRD-OQ-005).
CMP-IMP-110 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-043; FRD-FR-044; FRD-FR-045; API-133; DB-048 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-043; FRD-FR-044; FRD-FR-045
CMP-IMP-111 | EPIC-03 Supply | FEAT-008 Vehicle Management | FRD-FR-046; FRD-FR-047; FRD-FR-048 | UC-010; UC-011; UC-012 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-046; FRD-FR-047; FRD-FR-048
CMP-IMP-112 | EPIC-03 Supply | FEAT-008 Vehicle Management | UX 4.1 Screen 5 | UC-010; UC-011; UC-012 | TBD | v0.1 Draft | UX 4.1 Screen 5
CMP-IMP-113 | EPIC-03 Supply | FEAT-008 Vehicle Management | MOB-015; MADR-04; MADR-05 | UC-010; UC-011; UC-012 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-015; MADR-04; MADR-05
CMP-IMP-114 | EPIC-03 Supply | FEAT-008 Vehicle Management | TC-029; TC-030; FR-04 | UC-010; UC-011; UC-012 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-115 | EPIC-03 Supply | FEAT-009 Ride Publishing | DB-051; DB-052; DB-057; DB-058; DADR-08 | UC-014; UC-016; UC-018 | CMP-DOC-11 Database Design | v0.1 Draft | DB-051; DB-052; DB-057
CMP-IMP-116 | EPIC-03 Supply | FEAT-009 Ride Publishing | DB-050; DADR-05; DB 7; ARCH-053 | UC-014; UC-016; UC-018 | CMP-DOC-11 Database Design | v0.1 Draft | DB-050; DADR-05; DB 7
CMP-IMP-117 | EPIC-03 Supply | FEAT-009 Ride Publishing | BE-017; BE-018; BADR-02; BADR-04 | UC-014; UC-016; UC-018 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-017; BE-018; BADR-02
CMP-IMP-118 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-049; FRD-FR-050; FRD-FR-054; API 11.4 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-049; FRD-FR-050; FRD-FR-054
CMP-IMP-119 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-051; DB-051; DB-052; BE-050; BE-052 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-051; DB-051; DB-052
CMP-IMP-120 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-052; AADR-14 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-052; AADR-14
CMP-IMP-121 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-053; API-136; FRD-FR-260 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-053; API-136; FRD-FR-260
CMP-IMP-122 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-055 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-055
CMP-IMP-123 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-056; FRD-FR-057 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-056; FRD-FR-057
CMP-IMP-124 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-058; FRD-FR-059; BE-023; API-134 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-058; FRD-FR-059; BE-023
CMP-IMP-125 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-064; FRD-FR-065 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-064; FRD-FR-065 |  | Eligibility criteria depend on BAD-DEC-005 (FRD-GAP-002); the evaluation hook is buildable.
CMP-IMP-126 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-066 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-066
CMP-IMP-127 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-067; FRD-FR-244; BE-049 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-067; FRD-FR-244; BE-049
CMP-IMP-128 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-068 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-068
CMP-IMP-129 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-069; API-139; DB-056 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-069; API-139; DB-056
CMP-IMP-130 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-070; API-139; DB-056 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-070; API-139; DB-056 |  | FRD-GAP-006 - the driver has no specified way out. Do not invent one. Blocked on BAD-DEC-009.
CMP-IMP-131 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-071 | UC-014; UC-016; UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-071
CMP-IMP-132 | EPIC-03 Supply | FEAT-009 Ride Publishing | FRD-FR-072; API 11.4 | UC-018 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-072; API 11.4
CMP-IMP-133 | EPIC-03 Supply | FEAT-009 Ride Publishing | ARCH-080; API-135; API-048; ADM-037 | UC-014; UC-016; UC-018 | CMP-DOC-07 System Architecture | v0.1 Draft | ARCH-080; API-135; API-048
CMP-IMP-134 | EPIC-03 Supply | FEAT-009 Ride Publishing | API-137; DB-055; ARCH-096 | UC-014; UC-016; UC-018 | CMP-DOC-10 API Specification | v0.1 Draft | API-137; DB-055; ARCH-096
CMP-IMP-135 | EPIC-03 Supply | FEAT-009 Ride Publishing | UX 4.1 Screen 7 | UC-014; UC-016; UC-018 | TBD | v0.1 Draft | UX 4.1 Screen 7 |  | PARTIAL screen - it cannot state the amount payable. Blocked on BAD-DEC-003 (FRD-GAP-005).
CMP-IMP-136 | EPIC-03 Supply | FEAT-009 Ride Publishing | UX 4.1 Screen 6 | UC-018 | TBD | v0.1 Draft | UX 4.1 Screen 6
CMP-IMP-137 | EPIC-03 Supply | FEAT-009 Ride Publishing | UX 4.1 Screen 9 | UC-016 | TBD | v0.1 Draft | UX 4.1 Screen 9
CMP-IMP-138 | EPIC-03 Supply | FEAT-009 Ride Publishing | MOB-015; MADR-04; UXDR-04 | UC-014; UC-016; UC-018 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-015; MADR-04; UXDR-04
CMP-IMP-141 | EPIC-03 Supply | FEAT-009 Ride Publishing | TC-029; TC-030; FR-04 | UC-014; UC-016; UC-018 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-142 | EPIC-03 Supply | FEAT-010 Ride Preferences | DB-054; FRD-FR-062 | UC-015 | CMP-DOC-11 Database Design | v0.1 Draft | DB-054; FRD-FR-062
CMP-IMP-143 | EPIC-03 Supply | FEAT-010 Ride Preferences | FRD-FR-060 | UC-015 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-060
CMP-IMP-144 | EPIC-03 Supply | FEAT-010 Ride Preferences | FRD-FR-061 | UC-015 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-061
CMP-IMP-145 | EPIC-03 Supply | FEAT-010 Ride Preferences | FRD-FR-062 | UC-015 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-062
CMP-IMP-146 | EPIC-03 Supply | FEAT-010 Ride Preferences | FRD-FR-063; FRD-FR-092 | UC-015 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-063; FRD-FR-092
CMP-IMP-147 | EPIC-03 Supply | FEAT-010 Ride Preferences | UX 4.1 Screen 8 | UC-015 | TBD | v0.1 Draft | UX 4.1 Screen 8
CMP-IMP-148 | EPIC-03 Supply | FEAT-010 Ride Preferences | TC-029; TC-030 | UC-015 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030
CMP-IMP-149 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | AADR-10; API-140; API-143; FRD-FR-073 | UC-019; UC-020; UC-021 | CMP-DOC-10 API Specification | v0.1 Draft | AADR-10; API-140; API-143
CMP-IMP-150 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-074 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-074
CMP-IMP-151 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-075 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-075
CMP-IMP-152 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-076; DB 14.2 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-076; DB 14.2
CMP-IMP-153 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | BE-034; BE-035; BE-040; ADR-03 | UC-019; UC-020; UC-021 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-034; BE-035; BE-040 |  | TECHNICAL DECISION REQUIRED - the overlap algorithm and any minimum overlap threshold are deliberately unspecified (BAD-RULE-023, FRD-RISK-008). Route this as a named decision before implementing.
CMP-IMP-154 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-077 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-077
CMP-IMP-155 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-078; BAD-OPP-001 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-078; BAD-OPP-001
CMP-IMP-156 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | DB-053; ARCH-081; DADR-08 | UC-019; UC-020; UC-021 | CMP-DOC-11 Database Design | v0.1 Draft | DB-053; ARCH-081; DADR-08
CMP-IMP-157 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-079 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-079
CMP-IMP-158 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-080 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-080
CMP-IMP-159 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-081 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-081
CMP-IMP-160 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-082 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-082
CMP-IMP-161 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-083; GAP-020 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-083; GAP-020 |  | GAP-020 - no downstream statement carries this exclusion into the coarse filter. Record the criterion explicitly rather than inheriting it from a decision record prose.
CMP-IMP-162 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-084; ADM-037; API-135 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-084; ADM-037; API-135
CMP-IMP-163 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-085 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-085
CMP-IMP-164 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-086 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-086
CMP-IMP-165 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-087; UXDR-09; API-142 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-087; UXDR-09; API-142
CMP-IMP-166 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-088; NFR-085; UXDR-09 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-088; NFR-085; UXDR-09
CMP-IMP-167 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-093; API-143 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-093; API-143
CMP-IMP-168 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | API-144; ARCH-081; FRD-FR-235 | UC-019; UC-020; UC-021 | CMP-DOC-10 API Specification | v0.1 Draft | API-144; ARCH-081; FRD-FR-235 |  | Behaviour on an empty result set - whether alternatives are offered and which - is withheld (BAD-OQ-007, UC-022). Return empty; offer nothing.
CMP-IMP-169 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | FRD-FR-096; FRD-FR-256; FRD-FR-259 | UC-019; UC-020; UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-096; FRD-FR-256; FRD-FR-259
CMP-IMP-170 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | UX 4.1 Screen 10 | UC-019 | TBD | v0.1 Draft | UX 4.1 Screen 10
CMP-IMP-171 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | UX 4.1 Screen 11; UX 10 | UC-020 | TBD | v0.1 Draft | UX 4.1 Screen 11; UX 10
CMP-IMP-172 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | MOB-015; MOB-010; MADR-04 | UC-019; UC-020; UC-021 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MOB-015; MOB-010; MADR-04
CMP-IMP-173 | EPIC-04 Discovery | FEAT-011 Ride Search & Route Matching | TC-029; TC-030; FR-04; FR-06 | UC-019; UC-020; UC-021 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-174 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | FRD-FR-089; AADR-09 | UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-089; AADR-09
CMP-IMP-175 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | FRD-FR-090; API-141; API-049 | UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-090; API-141; API-049
CMP-IMP-176 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | FRD-FR-091; FRD-FR-047 | UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-091; FRD-FR-047
CMP-IMP-177 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | FRD-FR-094 | UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-094
CMP-IMP-178 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | FRD-FR-095 | UC-021 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-095
CMP-IMP-179 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | API 11.4; AADR-08; API-051 | UC-021 | TBD | v0.1 Draft | API 11.4; AADR-08; API-051
CMP-IMP-180 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | UX 4.1 Screen 12 | UC-021 | TBD | v0.1 Draft | UX 4.1 Screen 12
CMP-IMP-181 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | UX 4.1 Screen 13; UXDR-06; UX 9 | UC-021 | TBD | v0.1 Draft | UX 4.1 Screen 13; UXDR-06; UX 9 |  | PARTIAL screen - it cannot state whether a request requires driver acceptance (BAD-DEC-007) nor the fare composition (BAD-DEC-003).
CMP-IMP-182 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | UX 9.4; UXDR-08 | UC-021 | TBD | v0.1 Draft | UX 9.4; UXDR-08 |  | Decision Required - the precision of counterparty location disclosed before a booking exists is blocked (FRD-GAP-008, BAD-DEC-022).
CMP-IMP-183 | EPIC-04 Discovery | FEAT-012 Ride Detail & Commitment Surface | TC-030; TC-031 | UC-021 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-030; TC-031
CMP-IMP-184 | EPIC-05 Transaction | FEAT-013 Ride Request | DB-061; DB-062; DB-039 | UC-023 | CMP-DOC-11 Database Design | v0.1 Draft | DB-061; DB-062; DB-039
CMP-IMP-185 | EPIC-05 Transaction | FEAT-013 Ride Request | BE-017; BE-019; BE-021 | UC-023 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-017; BE-019; BE-021
CMP-IMP-186 | EPIC-05 Transaction | FEAT-013 Ride Request | FRD-FR-097; FRD-FR-100; API 11.6 | UC-023 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-097; FRD-FR-100; API 11.6
CMP-IMP-187 | EPIC-05 Transaction | FEAT-013 Ride Request | FRD-FR-098 | UC-023 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-098
CMP-IMP-188 | EPIC-05 Transaction | FEAT-013 Ride Request | FRD-FR-099 | UC-023 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-099
CMP-IMP-189 | EPIC-05 Transaction | FEAT-013 Ride Request | FRD-FR-101; API-146 | UC-023 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-101; API-146
CMP-IMP-190 | EPIC-05 Transaction | FEAT-013 Ride Request | FRD-FR-102 | UC-023 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-102
CMP-IMP-191 | EPIC-05 Transaction | FEAT-013 Ride Request | FRD-FR-103; FRD-FR-197 | UC-023 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-103; FRD-FR-197
CMP-IMP-192 | EPIC-05 Transaction | FEAT-013 Ride Request | API 11.6 | UC-023 | TBD | v0.1 Draft | API 11.6
CMP-IMP-193 | EPIC-05 Transaction | FEAT-013 Ride Request | API 11.6 | UC-023 | TBD | v0.1 Draft | API 11.6
CMP-IMP-194 | EPIC-05 Transaction | FEAT-013 Ride Request | UX 4.1 Screen 14 | UC-023 | TBD | v0.1 Draft | UX 4.1 Screen 14 |  | PARTIAL screen - it cannot state whether a request requires driver acceptance (BAD-DEC-007, FRD-GAP-009).
CMP-IMP-195 | EPIC-05 Transaction | FEAT-013 Ride Request | UX 4.1 Screen 9 | UC-023 | TBD | v0.1 Draft | UX 4.1 Screen 9 |  | Accept and decline controls depend on BAD-DEC-007. Build the listing; withhold controls the platform cannot honour (FRD-FR-195, UX-006).
CMP-IMP-199 | EPIC-05 Transaction | FEAT-013 Ride Request | TC-029; TC-030; FR-04 | UC-023 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-200 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | DB-059; DB-060; DB-061; DB-063 | UC-025; UC-029 | CMP-DOC-11 Database Design | v0.1 Draft | DB-059; DB-060; DB-061
CMP-IMP-201 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | BE-025; BE-012; BAD-RULE-028; FRD-FR-106 | UC-025; UC-029 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-025; BE-012; BAD-RULE-028
CMP-IMP-202 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | BE-024; FRD-FR-107; DB 7; BAD-RULE-027 | UC-025; UC-029 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-024; FRD-FR-107; DB 7
CMP-IMP-203 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | BADR-04; DADR-05; BE-054; ARCH-053 | UC-025; UC-029 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BADR-04; DADR-05; BE-054
CMP-IMP-204 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | API-148; FRD-FR-105; AADR-07 | UC-025; UC-029 | CMP-DOC-10 API Specification | v0.1 Draft | API-148; FRD-FR-105; AADR-07
CMP-IMP-205 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-104; FRD-FR-238; FRD-FR-239; FRD-FR-240 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-104; FRD-FR-238; FRD-FR-239
CMP-IMP-206 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-105; API-149; BE-056 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-105; API-149; BE-056
CMP-IMP-207 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-106; BE-025; API-145 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-106; BE-025; API-145
CMP-IMP-208 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-108; PAY 13.2 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-108; PAY 13.2 |  | The return of value itself is BLOCKED (FRD-GAP-014, GAP-009, BAD-DEC-010). Record the initiation; do not invent the refund.
CMP-IMP-209 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-109 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-109
CMP-IMP-210 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-110; FRD-FR-238 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-110; FRD-FR-238
CMP-IMP-211 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-111 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-111
CMP-IMP-212 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | BE-048; BE-049; BE-050; BE-053; SRS-REQ-040; SRS-REQ-041 | UC-025; UC-029 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-048; BE-049; BE-050
CMP-IMP-213 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-112; FRD-FR-244; FRD-FR-245 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-112; FRD-FR-244; FRD-FR-245
CMP-IMP-214 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-113; FRD-FR-197 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-113; FRD-FR-197
CMP-IMP-215 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-114; API 11.7 | UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-114; API 11.7
CMP-IMP-216 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-115; UXDR-02; UX 6 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-115; UXDR-02; UX 6
CMP-IMP-217 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | FRD-FR-116; DB-064 | UC-025; UC-029 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-116; DB-064 |  | Build the record now; the consequence is undecided (FRD-GAP-012, BAD-DEC-009). Recording costs nothing and makes the eventual policy enforceable retrospectively (FRD-ASM-004).
CMP-IMP-218 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | UX 4.1 Screens 17, 18 | UC-029 | TBD | v0.1 Draft | UX 4.1 Screens 17, 18
CMP-IMP-219 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | UXDR-14; UX 11 | UC-025; UC-029 | CMP-DOC-12 UI/UX Specification | v0.1 Draft | UXDR-14; UX 11
CMP-IMP-220 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | TADR-08; TC 12.1; BE-024; NFR-028 | UC-025; UC-029 | CMP-DOC-18 Testing & QA | v0.1 Draft | TADR-08; TC 12.1; BE-024
CMP-IMP-221 | EPIC-05 Transaction | FEAT-014 Booking & Seat Allocation | TC-029; TC-030; FR-04 | UC-025; UC-029 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-222 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-117; BE-032; ARCH-083; BAD-RULE-034 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-117; BE-032; ARCH-083
CMP-IMP-223 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-118; API-150; FRD-FR-238; FRD-FR-239 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-118; API-150; FRD-FR-238
CMP-IMP-224 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-119; UX 9.1 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-119; UX 9.1
CMP-IMP-225 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-120 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-120
CMP-IMP-226 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-121 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-121
CMP-IMP-227 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | PADR-01; PAY 5 | UC-030; UC-031 | CMP-DOC-14 Payment & UPI | v0.1 Draft | PADR-01; PAY 5
CMP-IMP-228 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-122; API 11.8; BE-050; BE-052 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-122; API 11.8; BE-050
CMP-IMP-229 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-123; PADR-02; MOB 8.3 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-123; PADR-02; MOB 8.3
CMP-IMP-230 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-124; PADR-03; API-154; BAD-RULE-032 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-124; PADR-03; API-154
CMP-IMP-231 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | PADR-08; DB-037; DB-068; SEC 12; API-053 | UC-030; UC-031 | CMP-DOC-14 Payment & UPI | v0.1 Draft | PADR-08; DB-037; DB-068
CMP-IMP-232 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | FRD-FR-137; PADR-12; FRD-FR-259 | UC-030; UC-031 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-137; PADR-12; FRD-FR-259
CMP-IMP-233 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | UX 4.1 Screen 15; UXDR-10; UX 11.1 | UC-031 | TBD | v0.1 Draft | UX 4.1 Screen 15; UXDR-10; UX 11.1
CMP-IMP-235 | EPIC-05 Transaction | FEAT-015 Fare & Payment Initiation | TC-029; TC-030; TC-031; FR-04 | UC-030; UC-031 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; TC-031
CMP-IMP-236 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | DB-065; DB-066; DB-067; DB-069; DB-070 | UC-031; UC-032; UC-033 | CMP-DOC-11 Database Design | v0.1 Draft | DB-065; DB-066; DB-067
CMP-IMP-237 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | BE-026; BE-027; PADR-07; SRS-REQ-155; SRS-REQ-156 | UC-031; UC-032; UC-033 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-026; BE-027; PADR-07
CMP-IMP-238 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-125; FRD-FR-126; PADR-04 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-125; FRD-FR-126; PADR-04
CMP-IMP-239 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | BE-131; BE-135; BE-137; BE-139 | UC-031; UC-032; UC-033 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-131; BE-135; BE-137
CMP-IMP-240 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-127; FRD-FR-128; PADR-04 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-127; FRD-FR-128; PADR-04
CMP-IMP-241 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-129 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-129
CMP-IMP-242 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-130; FRD-FR-131; FRD-FR-258; PADR-06 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-130; FRD-FR-131; FRD-FR-258
CMP-IMP-243 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-132; BE-145; PADR-06 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-132; BE-145; PADR-06
CMP-IMP-244 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-134; DB-067 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-134; DB-067
CMP-IMP-245 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-135; API-156 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-135; API-156
CMP-IMP-246 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | FRD-FR-136; UXDR-10 | UC-031; UC-032; UC-033 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-136; UXDR-10
CMP-IMP-247 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | PADR-10; BE-036; PAY 9; SADR-11 | UC-031; UC-032; UC-033 | CMP-DOC-14 Payment & UPI | v0.1 Draft | PADR-10; BE-036; PAY 9 |  | Decision Required - the PSP is unselected (BAD-DEP-004). The port is buildable; the adapter needs a provider. Seven selection gates are stated in PAY 14.1.
CMP-IMP-248 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | PADR-09; AADR-12; API 13 | UC-031; UC-032; UC-033 | CMP-DOC-14 Payment & UPI | v0.1 Draft | PADR-09; AADR-12; API 13
CMP-IMP-249 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | API-153; DB-066; AADR-06; BAD-RULE-033 | UC-031; UC-032; UC-033 | CMP-DOC-10 API Specification | v0.1 Draft | API-153; DB-066; AADR-06
CMP-IMP-250 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | API-157; ARCH-126 | UC-031; UC-032; UC-033 | CMP-DOC-10 API Specification | v0.1 Draft | API-157; ARCH-126
CMP-IMP-251 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | UX 4.1 Screen 16 | UC-032 | TBD | v0.1 Draft | UX 4.1 Screen 16
CMP-IMP-252 | EPIC-05 Transaction | FEAT-016 Payment Verification & Reconciliation | TC-029; TC-030; FR-03; FR-04; PAY 16 | UC-031; UC-032; UC-033 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-03
CMP-IMP-253 | EPIC-05 Transaction | FEAT-017 Ledger | DB-005; DB 8; DADR-07; DB-031 | UC-032 | CMP-DOC-11 Database Design | v0.1 Draft | DB-005; DB 8; DADR-07
CMP-IMP-254 | EPIC-05 Transaction | FEAT-017 Ledger | FRD-FR-133; BE-048; ARCH-112 | UC-032 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-133; BE-048; ARCH-112
CMP-IMP-255 | EPIC-05 Transaction | FEAT-017 Ledger | PADR-11; DADR-07 | UC-032 | CMP-DOC-14 Payment & UPI | v0.1 Draft | PADR-11; DADR-07
CMP-IMP-256 | EPIC-05 Transaction | FEAT-017 Ledger | DADR-06; DB-031 | UC-032 | CMP-DOC-11 Database Design | v0.1 Draft | DADR-06; DB-031
CMP-IMP-257 | EPIC-05 Transaction | FEAT-017 Ledger | FRD-FR-222; FRD-FR-223 | UC-032 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-222; FRD-FR-223
CMP-IMP-259 | EPIC-05 Transaction | FEAT-017 Ledger | TC-029; TC-030; FR-04 | UC-032 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-260 | EPIC-06 Journey | FEAT-018 Trip Execution | DB-071; DB-072; DB-075; DADR-11 | UC-038; UC-042 | CMP-DOC-11 Database Design | v0.1 Draft | DB-071; DB-072; DB-075
CMP-IMP-261 | EPIC-06 Journey | FEAT-018 Trip Execution | BE-028; BE-012; SRS-REQ-159; FRD-FR-142 | UC-038; UC-042 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-028; BE-012; SRS-REQ-159
CMP-IMP-262 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-141; FRD-FR-143; API-159; API 11.9 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-141; FRD-FR-143; API-159
CMP-IMP-263 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-142; BE-028 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-142; BE-028
CMP-IMP-264 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-144; FRD-FR-244 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-144; FRD-FR-244
CMP-IMP-265 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-145 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-145
CMP-IMP-266 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-146; FRD-FR-197 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-146; FRD-FR-197
CMP-IMP-267 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-147 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-147
CMP-IMP-268 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-165; FRD-FR-166; API 11.9 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-165; FRD-FR-166; API 11.9
CMP-IMP-269 | EPIC-06 Journey | FEAT-018 Trip Execution | FRD-FR-167; FRD-FR-248; FRD-FR-249 | UC-038; UC-042 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-167; FRD-FR-248; FRD-FR-249
CMP-IMP-270 | EPIC-06 Journey | FEAT-018 Trip Execution | UX 4.1 Screen 22; UX-009 | UC-042 | TBD | v0.1 Draft | UX 4.1 Screen 22; UX-009
CMP-IMP-273 | EPIC-06 Journey | FEAT-018 Trip Execution | TC-029; TC-030; FR-04 | UC-038; UC-042 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-274 | EPIC-06 Journey | FEAT-019 Live Position Tracking | DB-073; DB-074; GADR-03 | UC-039 | CMP-DOC-11 Database Design | v0.1 Draft | DB-073; DB-074; GADR-03
CMP-IMP-275 | EPIC-06 Journey | FEAT-019 Live Position Tracking | MADR-07; GADR-01; GADR-04; GPS 5.1 | UC-039 | CMP-DOC-08 Mobile Architecture | v0.1 Draft | MADR-07; GADR-01; GADR-04
CMP-IMP-276 | EPIC-06 Journey | FEAT-019 Live Position Tracking | MOB 8.2; FRD-FR-152 | UC-039 | TBD | v0.1 Draft | MOB 8.2; FRD-FR-152
CMP-IMP-277 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-148; ARCH-093; GADR-02 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-148; ARCH-093; GADR-02
CMP-IMP-278 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GADR-06; API-162; MOB-135; OPS-118 | UC-039 | CMP-DOC-15 GPS / Live Trip | v0.1 Draft | GADR-06; API-162; MOB-135
CMP-IMP-279 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS 6.2; GADR-11 | UC-039 | TBD | v0.1 Draft | GPS 6.2; GADR-11
CMP-IMP-280 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-149; GADR-11; API 11.9 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-149; GADR-11; API 11.9
CMP-IMP-281 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-150; API-161; GADR-05 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-150; API-161; GADR-05
CMP-IMP-282 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-151; GADR-07 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-151; GADR-07 |  | Open question - what the passenger sees when the driver becomes unreachable mid-trip is unresolved (FRD-OQ-009).
CMP-IMP-283 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-152; GADR-08 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-152; GADR-08
CMP-IMP-284 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-153; GADR-13 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-153; GADR-13
CMP-IMP-285 | EPIC-06 Journey | FEAT-019 Live Position Tracking | FRD-FR-154 | UC-039 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-154
CMP-IMP-286 | EPIC-06 Journey | FEAT-019 Live Position Tracking | UX 4.1 Screen 21; UXDR-11; UX-009; UX-011 | UC-039; UC-040 | TBD | v0.1 Draft | UX 4.1 Screen 21; UXDR-11; UX-009
CMP-IMP-287 | EPIC-06 Journey | FEAT-019 Live Position Tracking | GPS 10; DB-073; DB-179 | UC-039 | TBD | v0.1 Draft | GPS 10; DB-073; DB-179 |  | Decision Required - position retention period is unset (BAD-DEC-021, FRD-RISK-007). Location history accumulates without bound until it is set.
CMP-IMP-288 | EPIC-06 Journey | FEAT-019 Live Position Tracking | TC-029; TC-030; FR-04; GPS 14 | UC-039 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-289 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-155; FRD-FR-157 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-155; FRD-FR-157
CMP-IMP-290 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-156; FRD-FR-157 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-156; FRD-FR-157
CMP-IMP-291 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-158; GADR-07 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-158; GADR-07
CMP-IMP-292 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-159; GADR-10 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-159; GADR-10 |  | BLOCKED in part - pickup and drop sequencing on a multi-passenger trip is undecided (GAP-017, GPS 12.4). FRD-FR-159 is unimplementable for a multi-passenger trip until it is decided.
CMP-IMP-293 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-161 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-161
CMP-IMP-294 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-162; GADR-09 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-162; GADR-09
CMP-IMP-295 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-163; UXDR-08 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-163; UXDR-08
CMP-IMP-296 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-164 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-164
CMP-IMP-297 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | UX 4.1 Screen 23 | UC-044 | TBD | v0.1 Draft | UX 4.1 Screen 23
CMP-IMP-298 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | FRD-FR-160 | UC-040; UC-044 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-160 |  | Release R2 by FRD-FR-160. Open question whether the deferral is correct (FRD-OQ-007).
CMP-IMP-299 | EPIC-06 Journey | FEAT-020 Estimates & Multi-Passenger Trip | TC-029; TC-030; FR-04 | UC-040; UC-044 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-300 | EPIC-06 Journey | FEAT-021 Trip History & Records | FRD-FR-168; API 11.9 | UC-043 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-168; API 11.9
CMP-IMP-301 | EPIC-06 Journey | FEAT-021 Trip History & Records | FRD-FR-166; DB-072; NFR-126 | UC-043 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-166; DB-072; NFR-126
CMP-IMP-302 | EPIC-06 Journey | FEAT-021 Trip History & Records | FRD-FR-048 | UC-043 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-048
CMP-IMP-303 | EPIC-06 Journey | FEAT-021 Trip History & Records | UX 4.1 Screen 20 | UC-043 | TBD | v0.1 Draft | UX 4.1 Screen 20
CMP-IMP-304 | EPIC-06 Journey | FEAT-021 Trip History & Records | TC-029; TC-030 | UC-043 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030
CMP-IMP-305 | EPIC-07 Communication | FEAT-022 Messaging | NADR-02; NADR-03; NADR-06; FRD-FR-170; FRD-FR-172 | UC-045; UC-046; UC-047 | CMP-DOC-16 Communication & Notifications | v0.1 Draft | NADR-02; NADR-03; NADR-06
CMP-IMP-306 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-169; API 11.10 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-169; API 11.10
CMP-IMP-307 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-170 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-170
CMP-IMP-308 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-171 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-171
CMP-IMP-309 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-173; NADR-09 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-173; NADR-09
CMP-IMP-310 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-174; NADR-06 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-174; NADR-06
CMP-IMP-311 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-175; FRD-FR-260 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-175; FRD-FR-260
CMP-IMP-312 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-176; NOTIF 5.6 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-176; NOTIF 5.6
CMP-IMP-313 | EPIC-07 Communication | FEAT-022 Messaging | API 11.10 | UC-045; UC-046; UC-047 | TBD | v0.1 Draft | API 11.10
CMP-IMP-314 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-177; MADR-05 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-177; MADR-05
CMP-IMP-315 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-178; UXDR-02 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-178; UXDR-02
CMP-IMP-316 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-179; MADR-05; MADR-06; UXDR-14; NADR-04 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-179; MADR-05; MADR-06
CMP-IMP-317 | EPIC-07 Communication | FEAT-022 Messaging | FRD-FR-180; NOTIF 10.3 | UC-045; UC-046; UC-047 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-180; NOTIF 10.3
CMP-IMP-318 | EPIC-07 Communication | FEAT-022 Messaging | UX 4.1 Screens 24, 25 | UC-045; UC-046; UC-047 | TBD | v0.1 Draft | UX 4.1 Screens 24, 25
CMP-IMP-320 | EPIC-07 Communication | FEAT-022 Messaging | TC-029; TC-030; FR-04; NOTIF 13 | UC-045; UC-046; UC-047 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-321 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-203; NADR-13; API 11.11 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-203; NADR-13; API 11.11
CMP-IMP-322 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-197; NADR-10; NOTIF-081 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-197; NADR-10; NOTIF-081
CMP-IMP-323 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-198; NOTIF-081; NADR-13 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-198; NOTIF-081; NADR-13
CMP-IMP-324 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-199; NADR-08 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-199; NADR-08
CMP-IMP-325 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-200; NOTIF-089; NOTIF-090 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-200; NOTIF-089; NOTIF-090
CMP-IMP-326 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-201; NOTIF-084; NOTIF-088; NFR-076 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-201; NOTIF-084; NOTIF-088
CMP-IMP-327 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-202; NOTIF-085; NOTIF-086; NOTIF-087; NADR-07 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-202; NOTIF-085; NOTIF-086
CMP-IMP-328 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-203; NOTIF-094; NOTIF-095 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-203; NOTIF-094; NOTIF-095
CMP-IMP-329 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-204; NADR-09 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-204; NADR-09
CMP-IMP-330 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-205; FRD-FR-260; BE-131 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-205; FRD-FR-260; BE-131
CMP-IMP-331 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-206 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-206
CMP-IMP-332 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-207; API 11.11 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-207; API 11.11
CMP-IMP-333 | EPIC-07 Communication | FEAT-023 Notifications | FRD-FR-208 | UC-062; UC-063; UC-064 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-208
CMP-IMP-334 | EPIC-07 Communication | FEAT-023 Notifications | NADR-12; BE-036; NOTIF 9 | UC-062; UC-063; UC-064 | CMP-DOC-16 Communication & Notifications | v0.1 Draft | NADR-12; BE-036; NOTIF 9
CMP-IMP-335 | EPIC-07 Communication | FEAT-023 Notifications | API 11.11 | UC-062; UC-063; UC-064 | TBD | v0.1 Draft | API 11.11
CMP-IMP-336 | EPIC-07 Communication | FEAT-023 Notifications | NADR-05; UXDR-12; NOTIF 10.1 | UC-062; UC-063; UC-064 | CMP-DOC-16 Communication & Notifications | v0.1 Draft | NADR-05; UXDR-12; NOTIF 10.1
CMP-IMP-337 | EPIC-07 Communication | FEAT-023 Notifications | NOTIF-093; UX-160; UXDR-16 | UC-062; UC-063; UC-064 | CMP-DOC-16 Communication & Notifications | v0.1 Draft | NOTIF-093; UX-160; UXDR-16
CMP-IMP-338 | EPIC-07 Communication | FEAT-023 Notifications | MOB 8.4; README 3 | UC-062; UC-063; UC-064 | TBD | v0.1 Draft | MOB 8.4; README 3
CMP-IMP-339 | EPIC-07 Communication | FEAT-023 Notifications | UX 4.1 Screens 26, 27 | UC-062; UC-063; UC-064 | TBD | v0.1 Draft | UX 4.1 Screens 26, 27
CMP-IMP-340 | EPIC-07 Communication | FEAT-023 Notifications | NOTIF-082 | UC-062; UC-063; UC-064 | CMP-DOC-16 Communication & Notifications | v0.1 Draft | NOTIF-082 |  | The reward category exists in FRD-FR-197 but no reward behaviour is specified (BAD-DEC-013). Do not issue in it.
CMP-IMP-341 | EPIC-07 Communication | FEAT-023 Notifications | TC-029; TC-030; FR-04; NOTIF 13 | UC-062; UC-063; UC-064 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-342 | EPIC-08 Safety | FEAT-024 Emergency Contacts | DB 6.2; DB-035 | UC-048 | TBD | v0.1 Draft | DB 6.2; DB-035
CMP-IMP-343 | EPIC-08 Safety | FEAT-024 Emergency Contacts | FRD-FR-181; FRD-FR-184; API 11.2 | UC-048 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-181; FRD-FR-184; API 11.2
CMP-IMP-344 | EPIC-08 Safety | FEAT-024 Emergency Contacts | FRD-FR-182; API 11.2 | UC-048 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-182; API 11.2
CMP-IMP-345 | EPIC-08 Safety | FEAT-024 Emergency Contacts | FRD-FR-183; API-131 | UC-048 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-183; API-131
CMP-IMP-346 | EPIC-08 Safety | FEAT-024 Emergency Contacts | UX 4.1 Screen 29 | UC-048 | TBD | v0.1 Draft | UX 4.1 Screen 29
CMP-IMP-347 | EPIC-08 Safety | FEAT-024 Emergency Contacts | TC-029; TC-030 | UC-048 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030
CMP-IMP-348 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | DB-077; DB-078; FRD-FR-187 | UC-051 | CMP-DOC-11 Database Design | v0.1 Draft | DB-077; DB-078; FRD-FR-187
CMP-IMP-349 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | BE-029; FRD-FR-227; FRD-FR-228; SRS-REQ-160 | UC-051 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-029; FRD-FR-227; FRD-FR-228
CMP-IMP-350 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-185; FRD-FR-188 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-185; FRD-FR-188
CMP-IMP-351 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-186; FRD-FR-187 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-186; FRD-FR-187
CMP-IMP-352 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-189; ADM-044; BE-132 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-189; ADM-044; BE-132
CMP-IMP-353 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-190; BE-138; NFR-030 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-190; BE-138; NFR-030
CMP-IMP-354 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-191 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-191
CMP-IMP-355 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-192; FRD-FR-229 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-192; FRD-FR-229
CMP-IMP-356 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | FRD-FR-193; FRD-FR-244 | UC-051 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-193; FRD-FR-244
CMP-IMP-357 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | BE-132; OPS-040; BD-04 | UC-051 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-132; OPS-040; BD-04
CMP-IMP-358 | EPIC-08 Safety | FEAT-025 Safety Incident Pipeline | TC-029; TC-030; FR-04; FR-05 | UC-051 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-359 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | AADR-11; API 12; BADR-16 | UC-054; UC-083 | CMP-DOC-10 API Specification | v0.1 Draft | AADR-11; API 12; BADR-16
CMP-IMP-360 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | OPS-045; OPS-046; OPS-047; SEC-180; API-172 | UC-054; UC-083 | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-045; OPS-046; OPS-047
CMP-IMP-361 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | OPS-037; OPS-041; BE-191 | UC-054; UC-083 | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-037; OPS-041; BE-191
CMP-IMP-362 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | FRD-FR-194; FRD-FR-196 | UC-054; UC-083 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-194; FRD-FR-196
CMP-IMP-363 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | FRD-FR-195; UX-006; UXDR-13; MOB-150 | UC-054; UC-083 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-195; UX-006; UXDR-13
CMP-IMP-364 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | UX-011; NFR-092 | UC-054; UC-083 | CMP-DOC-12 UI/UX Specification | v0.1 Draft | UX-011; NFR-092
CMP-IMP-365 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | UX 4.1 Screen 28; UX 13.1 | UC-054; UC-083 | TBD | v0.1 Draft | UX 4.1 Screen 28; UX 13.1
CMP-IMP-366 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | UX 4.1 Screen 30; SRS-REQ-179 | UC-083 | TBD | v0.1 Draft | UX 4.1 Screen 30; SRS-REQ-179
CMP-IMP-367 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | FRD 8.5 prohibition; BRD-REQ-187; BAD-RISK-006; NFR-137 | UC-054; UC-083 | TBD | v0.1 Draft | FRD 8.5 prohibition; BRD-REQ-187; BAD-RISK-006
CMP-IMP-372 | EPIC-08 Safety | FEAT-026 Safety Centre & Safety Surface | TC-029; TC-030; FR-05 | UC-054; UC-083 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-05
CMP-IMP-373 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | BADR-15; OPS-050; ADM 4 | UC-070 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BADR-15; OPS-050; ADM 4
CMP-IMP-374 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADMR-01; ADM-017; ADM-018; BADR-15 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADMR-01; ADM-017; ADM-018
CMP-IMP-375 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-033; DB-006; DB-139 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-033; DB-006; DB-139
CMP-IMP-376 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-034; ADM-039; ADM-043; BE-119; BE-124 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-034; ADM-039; ADM-043
CMP-IMP-377 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-035; ADM-042; BE-120; BE-126 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-035; ADM-042; BE-120
CMP-IMP-378 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-036; BE-121; DB-130 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-036; BE-121; DB-130
CMP-IMP-379 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-037; ARCH-056; DB-131 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-037; ARCH-056; DB-131
CMP-IMP-380 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-046; ADM-047; ADM-050; UX-042; UX-044 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-046; ADM-047; ADM-050 |  | Projection staleness bounds are configuration and their values are unset (ADM-049).
CMP-IMP-381 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-048; ADM-038 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-048; ADM-038
CMP-IMP-382 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-023; ADM-024; ADM-025; SEC-121 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-023; ADM-024; ADM-025
CMP-IMP-383 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-026; ADM-027; API-118; API-119 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-026; ADM-027; API-118
CMP-IMP-384 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-029; ARCH-132; API-042 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-029; ARCH-132; API-042
CMP-IMP-385 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-030; ADM-031; BE-053 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-030; ADM-031; BE-053
CMP-IMP-386 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-032; ADMR-08 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-032; ADMR-08
CMP-IMP-387 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-163; ADM-164; ADM-170; ADMR-12 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-163; ADM-164; ADM-170 |  | BLOCKED for deployment - the administrative surface cannot be deployed until at least one role exists (ADM-168). The role set is undecided (ADM-166, BAD-DEC-006).
CMP-IMP-388 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | ADM-165; SEC-206; ADMR-06 | UC-070 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-165; SEC-206; ADMR-06
CMP-IMP-389 | EPIC-09 Operations | FEAT-027 Admin Foundation & Projections | TC-029; TC-030; ADM 16 | UC-070 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; ADM 16
CMP-IMP-390 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-209; ADM-020; ADM 7.1 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-209; ADM-020; ADM 7.1
CMP-IMP-391 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-210; ADM-021; ADM-022 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-210; ADM-021; ADM-022
CMP-IMP-392 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-211; ADM 7.3 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-211; ADM 7.3
CMP-IMP-393 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-212; ADMR-08; ADM 14.1 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-212; ADMR-08; ADM 14.1 |  | Open question - whether inspection should be audited or only state changes, and the audit volume consequence, is unresolved (FRD-OQ-006).
CMP-IMP-394 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-213; ADMR-06; SEC-065 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-213; ADMR-06; SEC-065
CMP-IMP-395 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | ADM-028; ADM-164; SEC-067 | UC-070; UC-071 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-028; ADM-164; SEC-067
CMP-IMP-396 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-214; ADMR-04; ADMR-07; ADM 8.1 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-214; ADMR-04; ADMR-07
CMP-IMP-397 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-215; ADMR-05; ADM 8.3; BE-024 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-215; ADMR-05; ADM 8.3
CMP-IMP-398 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-216; ADMR-05; BE-026 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-216; ADMR-05; BE-026
CMP-IMP-399 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-217; ADMR-06 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-217; ADMR-06
CMP-IMP-400 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-218; FRD-FR-246; ADM-165 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-218; FRD-FR-246; ADM-165
CMP-IMP-401 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | FRD-FR-219; FRD-FR-197 | UC-070; UC-071 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-219; FRD-FR-197
CMP-IMP-402 | EPIC-09 Operations | FEAT-028 Admin Inspection & Intervention | TC-029; TC-030; FR-04; ADM 16 | UC-070; UC-071 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-403 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | FRD-FR-138; ADM-038; ADM 9.1 | UC-033; UC-072 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-138; ADM-038; ADM 9.1
CMP-IMP-404 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | FRD-FR-139; PADR-13; ADM 9.2 | UC-033; UC-072 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-139; PADR-13; ADM 9.2
CMP-IMP-405 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | FRD-FR-140 | UC-033; UC-072 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-140
CMP-IMP-406 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | FRD-FR-220; ADM 9 | UC-033; UC-072 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-220; ADM 9 |  | No refund or settlement record exists - both are withheld (GAP-009, BAD-RULE-036, ADM-105).
CMP-IMP-407 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | FRD-FR-221 | UC-033; UC-072 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-221
CMP-IMP-408 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | FRD-FR-222; FRD-FR-223 | UC-033; UC-072 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-222; FRD-FR-223
CMP-IMP-409 | EPIC-09 Operations | FEAT-029 Admin Payment Reconciliation | TC-029; TC-030; FR-04 | UC-033; UC-072 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-410 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-224; ADMR-13; ADM-044 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-224; ADMR-13; ADM-044
CMP-IMP-411 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-225; ADM-164 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-225; ADM-164
CMP-IMP-412 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-226; ADM 10 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-226; ADM 10
CMP-IMP-413 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-227; BE-029; ADMR-09 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-227; BE-029; ADMR-09
CMP-IMP-414 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-228 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-228
CMP-IMP-415 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-229 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-229
CMP-IMP-416 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | DB 6.9; NFR-125 | UC-073; UC-075 | TBD | v0.1 Draft | DB 6.9; NFR-125
CMP-IMP-417 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | BE-030; FRD-FR-233 | UC-073; UC-075 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-030; FRD-FR-233
CMP-IMP-418 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-230 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-230
CMP-IMP-419 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-231; ADM-127 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-231; ADM-127 |  | Reputation records within a support case are withheld (BAD-DEC-012, ADM-127).
CMP-IMP-420 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-232; FRD-FR-246 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-232; FRD-FR-246
CMP-IMP-421 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | FRD-FR-233; ADMR-09 | UC-073; UC-075 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-233; ADMR-09
CMP-IMP-422 | EPIC-09 Operations | FEAT-030 Admin Safety & Support | TC-029; TC-030; FR-04; FR-05 | UC-073; UC-075 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-423 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | FRD-FR-234; ADM 12 | UC-076 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-234; ADM 12
CMP-IMP-424 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | FRD-FR-235; DB-020; DADR-14 | UC-076 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-235; DB-020; DADR-14
CMP-IMP-425 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | FRD-FR-236; ADM-027; ADMR-10 | UC-076 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-236; ADM-027; ADMR-10 |  | FRD-FR-236 prevents a specific damaging defect - a dashboard reporting refunds zero when refunds are unimplemented reads as good news.
CMP-IMP-426 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | ADM-045; ADM-035 | UC-076 | CMP-DOC-17 Admin / Filament | v0.1 Draft | ADM-045; ADM-035
CMP-IMP-427 | EPIC-09 Operations | FEAT-031 Admin Operational Reporting | TC-029; TC-030 | UC-076 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030
CMP-IMP-429 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-237; SRS-REQ-176; ARCH-016 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-237; SRS-REQ-176; ARCH-016
CMP-IMP-430 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-238; AADR-06; API-037 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-238; AADR-06; API-037
CMP-IMP-431 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-239; BE-053 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-239; BE-053
CMP-IMP-432 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-240; SADR-08; SADR-15 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-240; SADR-08; SADR-15
CMP-IMP-433 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-241; AADR-09 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-241; AADR-09
CMP-IMP-434 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-242; MOB-010; MADR-05 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-242; MOB-010; MADR-05
CMP-IMP-435 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | FRD-FR-243; SRS-REQ-176 | UC-078 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-243; SRS-REQ-176 |  | Open question - whether correction requires the client to discard its cache or merely refresh is unresolved (FRD-OQ-010).
CMP-IMP-436 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | AADR-04; API-057; BE-045 | UC-078 | CMP-DOC-10 API Specification | v0.1 Draft | AADR-04; API-057; BE-045
CMP-IMP-437 | EPIC-10 Cross-Cutting Integrity | FEAT-032 Backend Authority & Idempotency | TC-029; TC-030; TC-031; FR-04 | UC-078 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; TC-031
CMP-IMP-438 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | DB-004; DB 9.1; DB 9.3; DADR-09 | UC-079 | CMP-DOC-11 Database Design | v0.1 Draft | DB-004; DB 9.1; DB 9.3
CMP-IMP-439 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | BADR-09; BE-105; DB-004 | UC-079 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BADR-09; BE-105; DB-004
CMP-IMP-440 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | DB 9.2; DB 9.3; DADR-09 | UC-079 | TBD | v0.1 Draft | DB 9.2; DB 9.3; DADR-09
CMP-IMP-441 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | SADR-07; SEC 10; SEC 10.1 | UC-079 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-07; SEC 10; SEC 10.1
CMP-IMP-442 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | FRD-FR-244 | UC-079 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-244
CMP-IMP-443 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | FRD-FR-245; FRD-FR-246; BE-107 | UC-079 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-245; FRD-FR-246; BE-107
CMP-IMP-444 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | FRD-FR-247 | UC-079 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-247
CMP-IMP-445 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | FRD-FR-248; BE-049 | UC-079 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-248; BE-049
CMP-IMP-446 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | FRD-FR-249 | UC-079 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-249
CMP-IMP-447 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | FRD-FR-250; ADM 14.3 | UC-079 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-250; ADM 14.3
CMP-IMP-448 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | BE-146; BE-115 | UC-079 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-146; BE-115
CMP-IMP-450 | EPIC-10 Cross-Cutting Integrity | FEAT-033 Evidential Log & Audit | TC-029; TC-030; FR-04 | UC-079 | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; TC-030; FR-04
CMP-IMP-451 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | FRD-FR-255 | UC-081 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-255
CMP-IMP-452 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | FRD-FR-256; UX-006 | UC-081 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-256; UX-006
CMP-IMP-453 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | FRD-FR-257; UXDR-03; UX 7.4 | UC-081 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-257; UXDR-03; UX 7.4
CMP-IMP-454 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | FRD-FR-258; PADR-06 | UC-081 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-258; PADR-06
CMP-IMP-455 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | FRD-FR-259 | UC-081 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-259
CMP-IMP-456 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | FRD-FR-260 | UC-081 | CMP-DOC-04 Functional Requirements | v0.1 Draft | FRD-FR-260
CMP-IMP-457 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | AADR-13; API 14; API 14.1 | UC-081 | CMP-DOC-10 API Specification | v0.1 Draft | AADR-13; API 14; API 14.1
CMP-IMP-458 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | MOB 12.1; MOB-135; OPS-118; API-162 | UC-081 | TBD | v0.1 Draft | MOB 12.1; MOB-135; OPS-118
CMP-IMP-459 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | BE-203; API 11.13; OPS 12.3 | UC-081 | CMP-DOC-09 Backend Architecture | v0.1 Draft | BE-203; API 11.13; OPS 12.3
CMP-IMP-460 | EPIC-10 Cross-Cutting Integrity | FEAT-034 Degraded Operation & Configuration | TADR-09; TC 12.2; TC-030; FR-04 | UC-081 | CMP-DOC-18 Testing & QA | v0.1 Draft | TADR-09; TC 12.2; TC-030
CMP-IMP-461 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-03; API 5 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-03; API 5
CMP-IMP-462 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API-027; API 11.13; API 9.1 | - | CMP-DOC-10 API Specification | v0.1 Draft | API-027; API 11.13; API 9.1
CMP-IMP-463 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-02; API 8; API 8.6 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-02; API 8; API 8.6
CMP-IMP-464 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-14; API-014; UX 14 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-14; API-014; UX 14
CMP-IMP-465 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-09; API-047; UXDR-02 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-09; API-047; UXDR-02
CMP-IMP-466 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-08; API 6.3; API-051 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-08; API 6.3; API-051
CMP-IMP-467 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-05; API 6.1 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-05; API 6.1
CMP-IMP-468 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-06; API-037; FRD-FR-238 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-06; API-037; FRD-FR-238
CMP-IMP-469 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | AADR-07; API 4 | - | CMP-DOC-10 API Specification | v0.1 Draft | AADR-07; API 4
CMP-IMP-470 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | API 10; API-112; API-113; DADR-04 | - | TBD | v0.1 Draft | API 10; API-112; API-113 |  | No limit, window or page size value is stated anywhere in CMP-DOC-10 (API 0.8.4). Values are configuration and unset.
CMP-IMP-471 | EPIC-10 Cross-Cutting Integrity | FEAT-035 API Contract & Versioning | TADR-10; TC-031; API 19 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TADR-10; TC-031; API 19
CMP-IMP-472 | EPIC-11 Security | FEAT-036 Security Controls | SEC 4; SADR-01 | UC-080 | TBD | v0.1 Draft | SEC 4; SADR-01
CMP-IMP-473 | EPIC-11 Security | FEAT-036 Security Controls | SEC 6; SADR-04; NFR-054; NFR-055 | UC-080 | TBD | v0.1 Draft | SEC 6; SADR-04; NFR-054 |  | Bound values are configuration and unset pending BAD-DEC-018.
CMP-IMP-474 | EPIC-11 Security | FEAT-036 Security Controls | SEC 5.3; DB-036; DB-042 | UC-080 | TBD | v0.1 Draft | SEC 5.3; DB-036; DB-042
CMP-IMP-475 | EPIC-11 Security | FEAT-036 Security Controls | SEC 5.2; FRD-FR-011; NFR-057 | UC-080 | TBD | v0.1 Draft | SEC 5.2; FRD-FR-011; NFR-057 |  | Decision Required - limits and cool-off periods are unset (FRD-OQ-003).
CMP-IMP-476 | EPIC-11 Security | FEAT-036 Security Controls | SADR-05; SEC 8; DB-035 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-05; SEC 8; DB-035
CMP-IMP-477 | EPIC-11 Security | FEAT-036 Security Controls | SEC 9; SEC-091; SEC-101; OPS-048 | UC-080 | TBD | v0.1 Draft | SEC 9; SEC-091; SEC-101 |  | Decision Required - protocol versions and cipher selection depend on the unselected hosting provider (OPS-049, BAD-DEP-009).
CMP-IMP-478 | EPIC-11 Security | FEAT-036 Security Controls | SADR-09; DB-038; SEC 11; SEC-119; SEC-121 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-09; DB-038; SEC 11
CMP-IMP-479 | EPIC-11 Security | FEAT-036 Security Controls | SADR-10; SEC 12; DB-037; DB-068 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-10; SEC 12; DB-037
CMP-IMP-480 | EPIC-11 Security | FEAT-036 Security Controls | SADR-13; SEC 13; SEC 13.1; SEC 13.3; SEC 13.4 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-13; SEC 13; SEC 13.1
CMP-IMP-481 | EPIC-11 Security | FEAT-036 Security Controls | SADR-14; SEC 14.1; SEC-163; SEC-165; OPS-098; OPS-116 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-14; SEC 14.1; SEC-163
CMP-IMP-482 | EPIC-11 Security | FEAT-036 Security Controls | SADR-15; SEC 17.1; FRD-FR-240 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-15; SEC 17.1; FRD-FR-240
CMP-IMP-483 | EPIC-11 Security | FEAT-036 Security Controls | SEC 15; API 15; SEC-180; OPS-046 | UC-080 | TBD | v0.1 Draft | SEC 15; API 15; SEC-180 |  | All tuning values are unset (API 15.3, SEC 15).
CMP-IMP-484 | EPIC-11 Security | FEAT-036 Security Controls | SADR-16; SEC 19.1; SEC 19.4; SEC-230 | UC-080 | CMP-DOC-13 Security Design | v0.1 Draft | SADR-16; SEC 19.1; SEC 19.4
CMP-IMP-486 | EPIC-11 Security | FEAT-036 Security Controls | SEC 19; TC 10; FR-04 | UC-080 | TBD | v0.1 Draft | SEC 19; TC 10; FR-04
CMP-IMP-487 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC-025; TC-028; TADR-05 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-025; TC-028; TADR-05
CMP-IMP-488 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 4; TC-026; TC-027; TADR-01; TADR-02; TADR-14 | - | TBD | v0.1 Draft | TC 4; TC-026; TC-027
CMP-IMP-489 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC-017; TC 4.3; TR criterion 6 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-017; TC 4.3; TR criterion 6 |  | Release readiness criterion 6 (TR 10.1) - not started. This is analysis work, not construction, and it gates gate 4.
CMP-IMP-490 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC-037; TC-038; TC-021; OPS-092; OPS-093 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-037; TC-038; TC-021
CMP-IMP-491 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC-029; BE-040; MOB-153 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-029; BE-040; MOB-153
CMP-IMP-492 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC-030; TADR-08; DB-085; OPS-024 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-030; TADR-08; DB-085
CMP-IMP-493 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC-031; TADR-10 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TC-031; TADR-10
CMP-IMP-494 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 9; TC 6.2; DB 15 | - | TBD | v0.1 Draft | TC 9; TC 6.2; DB 15
CMP-IMP-495 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TADR-08; TC 12.1 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TADR-08; TC 12.1
CMP-IMP-496 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TADR-09; TC 12.2; TC-155; OPS-099 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | TADR-09; TC 12.2; TC-155
CMP-IMP-497 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 11; MOB 15 | - | TBD | v0.1 Draft | TC 11; MOB 15
CMP-IMP-498 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | FR-04; TADR-04; TC 4.3 | - | CMP-DOC-18 Testing & QA | v0.1 Draft | FR-04; TADR-04; TC 4.3
CMP-IMP-499 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 13; TC-032; TADR-12 | - | TBD | v0.1 Draft | TC 13; TC-032; TADR-12 |  | Decision Required - the accessibility conformance standard is unchosen (MOB-OQ-002, NFR-088, UX 15.3).
CMP-IMP-500 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 16; OPS-022; TC-203; TC-206 | - | TBD | v0.1 Draft | TC 16; OPS-022; TC-203
CMP-IMP-501 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 15; TC-012; TC-020; TR-111; TR-119 | - | TBD | v0.1 Draft | TC 15; TC-012; TC-020
CMP-IMP-502 | EPIC-12 Quality | FEAT-037 Verification & Test Infrastructure | TC 14.3; TR-119; TR-120; TRDR-11 | - | TBD | v0.1 Draft | TC 14.3; TR-119; TR-120
CMP-IMP-503 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS 5.1; OPS-021; OPS-022; OPS-024; OPS-025; OPS-028 | - | TBD | v0.1 Draft | OPS 5.1; OPS-021; OPS-022 |  | Environment sizing is register decision 9 and is unresolved (OPS-027). Staging cannot be shaped like production in volume until GAP-016 is resolved (OPS-026).
CMP-IMP-504 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-089; OPS-090; OPS-105; OPS 9.1; TC 6.3 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-089; OPS-090; OPS-105
CMP-IMP-505 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-091; TC-021; TC-200; TR-110 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-091; TC-021; TC-200
CMP-IMP-506 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-029; OPS-030; OPS-097; OPS-100; OPS-101 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-029; OPS-030; OPS-097
CMP-IMP-507 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-098; OPS-099; NFR-108; SEC-163 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-098; OPS-099; NFR-108
CMP-IMP-508 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-032; OPS-033; NFR-119 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-032; OPS-033; NFR-119
CMP-IMP-509 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-034; OPS-104; DB-218; DB-219 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-034; OPS-104; DB-218
CMP-IMP-510 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-037; ARCH-143 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-037; ARCH-143
CMP-IMP-511 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-038; ARCH-138; ARCH-139 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-038; ARCH-138; ARCH-139
CMP-IMP-512 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-039; ARCH-140 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-039; ARCH-140
CMP-IMP-513 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-043; BE-133 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-043; BE-133
CMP-IMP-514 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS 8; OPS-116; SEC 14.1; SADR-14 | - | TBD | v0.1 Draft | OPS 8; OPS-116; SEC 14.1 |  | Custody for six unselected suppliers is stated as a property, not a product (OPS 8.2).
CMP-IMP-515 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-107; OPS-115; OPS-116; MOB-168 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-107; OPS-115; OPS-116 |  | Distribution platform obligations beyond the technical are BAD-DEP-008 and are not specified (OPS-120).
CMP-IMP-516 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-117; MOB-131; SRS-REQ-011 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-117; MOB-131; SRS-REQ-011
CMP-IMP-517 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS 11.3; OPS 11.4; DDR-12 | - | TBD | v0.1 Draft | OPS 11.3; OPS 11.4; DDR-12 |  | BLOCKED - the restore reconciliation procedure cannot be completed until retention periods exist (BAD-DEC-021, OPS 15.2). Release readiness criterion 9.
CMP-IMP-519 | EPIC-13 DevOps & Release | FEAT-038 Build, Pipeline & Environments | OPS-031; OPS-090; OPS-105; TC-053; TC-054 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-031; OPS-090; OPS-105
CMP-IMP-520 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | OPS 12.2; OPS-119; DDR-11; TR criterion 11 | - | TBD | v0.1 Draft | OPS 12.2; OPS-119; DDR-11
CMP-IMP-521 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | MOB 13.1; OPS-119; GAP-015 | - | TBD | v0.1 Draft | MOB 13.1; OPS-119; GAP-015
CMP-IMP-522 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | README 3; NFR series | - | Project Control - README | v0.1 Draft | README 3; NFR series
CMP-IMP-523 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | OPS 12.3; BE-203 | - | TBD | v0.1 Draft | OPS 12.3; BE-203
CMP-IMP-524 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | OPS-100; BE-199 | - | CMP-DOC-19 DevOps / Deployment | v0.1 Draft | OPS-100; BE-199
CMP-IMP-525 | EPIC-13 DevOps & Release | FEAT-039 Observability & Operations | OPS 14; OPS-092 break-glass; DDR-13; OPS-050 | - | TBD | v0.1 Draft | OPS 14; OPS-092 break-glass; DDR-13 |  | BLOCKED - incident response ownership is unanswered since CMP-DOC-13 (SEC-OQ-07). Release readiness criteria 9 and 10.

## 13_Dropdowns
Status | Work Type | Platform | Layer | Priority | Yes/No | Push Status | Test Result | Test Type | Severity | Bug Status | Decision Status | Dependency Status | Dependency Type | Risk Level | Probability/Impact | Planned Day
Not Started | UI | Android | UI | P0 | Yes | Not Pushed | Not Tested | Unit | Critical | Open | Open | Not Ready | Business Decision | Low | Low | Day 1
In Analysis | UX | Laravel | ViewModel | P1 | No | Pushed | Pass | Integration | High | In Progress | Decided | Ready | Technical Decision | Medium | Medium | Day 2
Ready | Android | MySQL | Domain | P2 | N/A | Failed | Fail | API | Medium | Fixed | Deferred | Blocked | Supplier Selection | High | High | Day 3
In Progress | Backend | Filament | Repository |  |  | Reverted | Blocked | UI | Low | Retest |  | Resolved | Document Approval | Critical |  | Day 4
Implemented | API | API | Data |  |  |  | Retest Required | End-to-End |  | Closed |  |  | Work Item |  |  | Day 5
Committed | Database | Firebase | Local DB |  |  |  |  | Regression |  | Won't Fix |  |  | External Service |  |  | Day 6
Pushed | Admin | External Service | Network |  |  |  |  | Manual |  | Deferred |  |  | Data |  |  | Day 7
Testing | Security | Cross Platform | Controller |  |  |  |  | Security |  |  |  |  | Infrastructure |  |  | Day 8
Tested | Payment |  | Service |  |  |  |  | Payment | [7 empty] | Day 9
Reviewed | GPS |  | Model |  |  |  |  | GPS | [7 empty] | Day 10
Completed | Chat |  | Validation |  |  |  |  | Performance | [7 empty] | Day 11
Blocked | Notification |  | Authentication | [12 empty] | Day 12
Cancelled | Testing |  | Authorization | [12 empty] | Day 13
| DevOps |  | Queue | [12 empty] | Day 14
| Documentation |  | Notification | [12 empty] | Day 15
| Bug Fix |  | Schema | [12 empty] | Post-MVP
| Integration |  | Migration | [12 empty] | TBD
| Configuration |  | Query
Index
Seed
Resource
Page
Widget
Action
Policy