CARPOOL MOBILITY PLATFORM

Project Code:  CMP        Brand:  TBD

CMP-PLAN-IMPL-ANALYSIS

Implementation Analysis

What the decomposition of CMP-DOC-01 … CMP-DOC-20 into implementation work found

Version 0.1   ·   Draft   ·   2026-08-19

Classification: Internal

# 0. Document Control

## 0.1 Document Metadata

| Field | Value |
| --- | --- |
| Document ID | CMP-PLAN-IMPL-ANALYSIS |
| Document Name | Implementation Work Breakdown Analysis |
| Project Name | Carpool Mobility Platform |
| Project Code | CMP |
| Version | 0.1 |
| Status | Draft |
| Date | 2026-08-19 |
| Author | Technical Project Management (AI-assisted) |
| Reviewer | [TBD] |
| Approver | Project Owner |
| Classification | Internal |
| Companion artefact | CMP-Implementation-Tracker.xlsx (same directory) |
| Source of truth | Document/ — CMP-DOC-01 … CMP-DOC-20, all v0.1 Draft |

## 0. What this document is, and what it is not

This is a planning artefact, not a specification. It decomposes the approved documentation chain into trackable implementation work items and reports what that decomposition found. It creates no requirement, takes no business decision, and closes no gap.

Five rules governed the decomposition:

1. Nothing was invented. Every work item names the document statement it derives from. No missing business decision was supplied, guessed at, or given a provisional value.

2. A decision is not work. Business decisions, technical decisions, functional gaps, risks and documentation conflicts are not implementation work items and do not appear in the register. They are carried on 09_Decisions, 10_Dependencies and 11_Risks, where they can be tracked without ever being mistaken for something to build.

3. Withheld areas stay withheld. CMP-DOC-04 §9.2 records three functional areas as carrying zero functional requirements. No work item implements any of them, and none is stubbed, prototyped, disabled or marked as forthcoming (ADM-187, ADM-191).

4. The register starts empty of progress. Every row is Not Started or Blocked. Nothing is marked Implemented, Committed, Pushed, Tested, Reviewed or Completed — analysing a requirement is not implementing it.

5. Recommendations are labelled. Engineering tasks not traceable to a numbered statement are marked in the Notes column.

Why rule 2 matters. FRD-RISK-002 is the highest-severity risk in CMP-DOC-04: a developer implements a gap. A gap sitting in a work-item register, with an ID and an assignee column, is an invitation to do exactly that. The register therefore contains implementation work and nothing else.

FACT. At the time of this analysis the repository contained Document/ and nothing else. No Android project, no Laravel project, no MySQL schema, no build configuration. Sections 18 and 19 below are consequences of this, not oversights.

## 1. Total features identified

39 features carrying implementation work, grouped into 13 epics (FEAT-001 … FEAT-039).

Six further feature identifiers — FEAT-040 … FEAT-045 — are reserved, not built. They name the withheld areas (ratings and reviews, wallet and rewards, recurring commute, cancellation/refund/settlement, verification adjudication and account state) and the project-level decision set. None appears in the implementation register. Each is carried where it belongs: on 09_Decisions, 10_Dependencies and 11_Risks.

## 2. Total implementation work items

507 work items. Work IDs were issued across the full analysed set (CMP-IMP-001 … CMP-IMP-562); the 55 IDs belonging to rows that are not implementation work are withdrawn and never reissued, so the register contains 507 rows with 55 vacant identifiers. Section 24 lists every withdrawn ID and where its content now lives.

| Measure | Value |
| --- | --- |
| Work items in the register | 507 |
| Work IDs issued (contiguous, never reused, never renumbered) | 562 |
| Work IDs withdrawn as not-implementation-work | 55 |
| Estimated effort | 3,802 hours |
| Status Not Started | 496 |
| Status Blocked | 11 |
| Status anything else | 0 |
| Distinct source documents cited | 20 |

Every row starts Not Started or Blocked. Nothing is Implemented, Committed, Pushed, Tested, Reviewed or Completed, and nothing in the workbook sets those automatically. Analysis is not progress.

What Blocked means here. A blocked row is buildable implementation work whose value or policy is not yet set — the obligation exists as a numbered statement, only a parameter is missing. Example: FRD-FR-011 requires the platform to stop accepting verification attempts once the limit is reached; the limit itself is unset (FRD-OQ-003). The work item is real; it is blocked on a value.

A blocked row is never a decision, a gap or a conflict. Those are not work.

| The 11 blocked work items | Blocked on |
| --- | --- |
| Declare the supported Android version range | MOB-OQ-001 device range unchosen |
| Cease accepting verification attempts at the limit | FRD-OQ-003 limit and cool-off unset |
| Implement the SMS/OTP provider port and one adapter | Provider unselected |
| Indicate which profile elements are disclosed | BAD-DEC-022 disclosure list |
| Allow a user to take the driver role subject to eligibility | BAD-DEC-005 eligibility criteria |
| Apply disclosure rules at the commitment surface | BAD-DEC-022 location precision |
| Implement the payment provider port and one adapter | BAD-DEP-004 PSP unselected |
| Apply position privacy scoping and retention marking | BAD-DEC-021 retention period |
| Establish accessibility verification as a procedure | MOB-OQ-002 standard unchosen |
| Implement backup and the restore-versus-retention procedure | BAD-DEC-021 retention periods |
| Establish incident response structure and break-glass access | SEC-OQ-07 ownership unanswered |

## 3. P0 work items — MVP critical

433 (85%). Derived from the MVP scope proposed in CMP-DOC-01 §24.2 and from the integrity-critical (‡) statements, which CMP-DOC-04 §3.5 states are not subject to descoping.

## 4. P1 work items — MVP important

70 (14%). Items whose requirement carries MoSCoW S (Should), or which serve a decided behaviour that the core commute loop can complete without.

## 5. P2 work items — post-MVP

4 (1%). Explicitly deferred by a document statement — principally FRD-FR-160 (rich telemetry, Release R2), multi-passenger messaging, and admin bulk operations and export.

Priority was derived from documentation, not assigned. Where CMP-DOC-02 priority was unavailable the item inherits its feature's priority, and where the business priority is genuinely unknown the item is marked Blocked rather than guessed.

## 6. Android work items

86 on platform Android, plus a share of the 84 Cross Platform items that carry client-side obligations.

|  | Value |
| --- | --- |
| Android-platform items | 86 |
| Android effort | 669 h |
| Compose screens specified | 32 (CMP-DOC-12 §4.1 — 31 numbered plus Screen 32) |
| Screens marked Partial by CMP-DOC-12 | 4 (Screens 7, 13, 14, 24) |
| Screens withheld by CMP-DOC-12 §17 | 14 |

## 7. Laravel work items

256 — the largest platform share, 50% of all work items and 1,780 hours.

This is the correct shape. CMP-DOC-07 makes Laravel the business authority; CMP-DOC-08 MOB-010 forbids the client from containing a business rule, a fare computation, a seat calculation or a state-transition rule, and MOB-011 requires that absence to be verified by build-time inspection.

## 8. API work items

46 items of work type API, covering roughly 60 operations across the 13 resource groups of CMP-DOC-10 §11, plus the separate safety surface (§12), the provider callback surface (§13) and configuration delivery (§14).

11 API resources are withheld (CMP-DOC-10 §11.14) — recurring commute, wallet, rewards, refunds, driver-cancellation consequence, disputes, insurance position, referral, fraud reporting, emergency dispatch, and the operator surfaces.

## 9. MySQL work items

35 items, 215 hours, covering the six storage domains of CMP-DOC-11 §4 (op_, led_, ev_, proj_, mch_, cfg_) and roughly 30 tables realising the nine aggregates of CMP-DOC-09 BADR-02.

7 tables are withheld (CMP-DOC-11 §6.11). CMP-DOC-11 states the reason directly: a speculative table acquires foreign keys, then data, then a migration cost — and it encodes a guess about behaviour nobody has decided.

## 10. Filament work items

46 items, 320 hours, across four features: admin foundation and the nine projections, inspection and intervention, payment reconciliation, and safety and support case handling.

5 operator capabilities are withheld (CMP-DOC-17 §15). Two of them are operationally serious and are carried as risks in §17 below.

## 11. Payment work items

34 items across FEAT-015 (fare and initiation), FEAT-016 (verification and reconciliation) and FEAT-017 (ledger) — 276 hours.

CMP-DOC-04 §5.3 states that the payment integrity chain is complete and unblocked: FRD-FR-117, 118, 124–131 and 133 together implement every absolute payment rule and depend on no open business decision. This analysis agrees, and CMP-DOC-04 FR-03 recommends building it first. Two things around it are not buildable: the composition of the amount payable (BAD-DEC-003) and the return of value (BAD-DEC-010).

## 12. GPS / live trip work items

24 items across FEAT-019 (position tracking) and FEAT-020 (estimates and multi-passenger trip) — 221 hours.

CMP-DOC-15 delivers a complete tracking mechanism with no values set: cadence, staleness bound and retention are all configuration, and every one is unset.

## 13. Testing work items

49 items of work type Testing, of which 14 form the verification infrastructure (FEAT-037) and the remainder are per-feature test suites.

| Verification obligation | Source | Count |
| --- | --- | --- |
| Consolidated verification obligations | CMP-DOC-18 §4 | 99 |
| Non-suppressible at gate 4 | TC-021, TC-200 | 25 |
| Structural rules at gate 1 | TC-037 | 13 (8 non-suppressible) |
| Integrity-critical statements across the chain | CMP-DOC-20 §4.3 | 1,412 |
| Integrity-critical mapping (TC-017) | CMP-DOC-18 | Not started |

TC-017 — mapping every integrity-critical statement to an owning obligation — is release readiness criterion 6 and is carried in the register at 24 hours. It is analysis work, it gates gate 4, and no code depends on it.

## 14. DevOps work items

21 items across FEAT-038 (build, pipeline, environments) and FEAT-039 (observability) — 217 hours. Four environments, five deployment units, four gates, 18 measurement points.

None of it can be provisioned. All 21 sizing decisions are open and the hosting provider is unselected. CMP-DOC-19 OPS-014 states this plainly, and CMP-DOC-20 TR-081 records that the sizing class blocks everything downstream of it.

## 15. Estimated 15-day workload

| Measure | Items | Effort |
| --- | --- | --- |
| Allocated to Day 1 – Day 15 | 336 | 2,540 h |
| Deferred to Post-MVP | 161 | 1,184 h |
| Unschedulable (TBD, blocked on a value or a supplier) | 10 | 78 h |
| Total | 507 | 3,802 h |

The day allocation is dependency-ordered, not capacity-fitted. Day n means this work becomes possible on day n given what precedes it, not this work fits in day n.

| Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Items | 7 | 10 | 12 | 17 | 22 | 24 | 26 | 23 | 26 | 32 | 25 | 38 | 30 | 26 | 18 |
| Hours | 39 | 74 | 92 | 147 | 162 | 193 | 192 | 182 | 194 | 232 | 199 | 268 | 235 | 204 | 127 |

2,540 hours over 15 days is approximately 169 hours per day. At 8 productive hours per engineer that implies a team of about 21. No team composition, budget or delivery horizon has been supplied — BAD-CON-017 records their absence and BAD-DEC-002 is the decision that would supply them. The 15-day sprint is therefore a sequence, not a commitment, and should not be reported as one. See §21.

## 16. Major dependencies

Recorded in full on sheet 10_Dependencies (57 entries). The ones that govern everything else:

| # | Dependency | Type | Gates |
| --- | --- | --- | --- |
| 1 | Approval of CMP-DOC-01 … CMP-DOC-20 in chain order | Document approval | Everything. Zero of twenty are approved; every document from CMP-DOC-02 onward was produced from unapproved predecessors and records the conflict (TR-131). |
| 2 | BAD-DEP-009 hosting provider | Supplier | All provisioning, through sizing decision 10 (OPS-014, TR-081) |
| 3 | BAD-DEC-018 KPI and quality targets | Business | 69 quality targets, 11 of 21 sizing decisions, every alert threshold, 5 verification categories |
| 4 | BAD-DEC-021 retention and closure | Business | 8 retention periods, the restore-versus-retention procedure, position history growth |
| 5 | BAD-DEC-006 administrative role set | Business | The admin surface cannot deploy until one role exists (ADM-168) |
| 6 | BAD-DEP-004 payment service provider | Supplier | The payment adapter. The port is buildable; the adapter is not. |
| 7 | Route-overlap algorithm | Technical | FEAT-011, the platform's differentiating capability |
| 8 | Launch scale figures (GAP-016) | Data | Three backend architectural assumptions; index and partitioning strategy; monetary precision |
| 9 | Google Maps Platform / Places / Routes access | External service | Publishing, search, tracking, estimates |
| 10 | Firebase Cloud Messaging | External service | Notification delivery |

Internal build order is a straight line for the first third: database and Laravel foundation → backend authority → evidential log → identity → vehicles → publishing → search → request → booking → payment. Search and matching (FEAT-011) is the only large feature that can be built in parallel with identity, because it depends on publishing data shape rather than on identity behaviour.

## 17. Major risks

Recorded in full on sheet 11_Risks (20 entries, seeded from the risk registers of CMP-DOC-01, CMP-DOC-04 and CMP-DOC-20). The critical ones:

| ID | Risk | Why it is critical |
| --- | --- | --- |
| RISK-002 | A developer implements a gap. Faced with undecided behaviour, someone writes a reasonable-looking flow and business policy is set by default. | The highest-severity risk in CMP-DOC-04 (FRD-RISK-002). The register carries implementation work only, so no gap can be picked up and built by mistake; the 29 functional gaps live on 09_Decisions. |
| RISK-003 | The two live product defects ship. A driver strands passengers; the platform holds money it cannot return. | Both are reachable through specified behaviour. Neither needs engineering to fix. |
| RISK-010 | A structural rule is relaxed under delivery pressure. | The most common severity-20 risk in the chain, recorded independently by six documents (TR-087). |
| RISK-011 | An unresolved decision is resolved by default rather than decided. | The second most common (TR-088), and §16 makes it likely. |
| RISK-013 | The 15-day sprint is read as a capacity commitment. | 2,540 hours in the window; no team size supplied. See §15 and §21. |
| RISK-014 | Nothing can be provisioned. | 21 of 21 sizing decisions open. |
| RISK-016 | A safety responder can close an incident and take no action against the account involved. | ADM-196. A live operational hole, not a missing feature. |
| RISK-019 | Regulatory characterisation is unknown, particularly if the platform sets fares or takes a fee. | BAD-RISK-001. The legal opinion is MVP entry precondition 1 and is not held. |
| RISK-020 | A passing test suite is read as readiness. | TR-121. The largest known risks are undecided, not defective. |

## 18. Existing partially implemented functionality

None. There is no application source code.

The repository contained only Document/ at the time of this analysis. Every one of the 507 work items is therefore Not Started or Blocked; none is Partially Implemented, Implemented, Deprecated or Unknown.

This is consistent with CMP-DOC-20 TR-132: the specification is complete and the platform does not exist.

## 19. Mock / placeholder functionality

None. There is no mock data, no fake API, no simulated GPS, no mock payment, no placeholder authentication, no temporary local storage, no hardcoded value and no demo UI — because there is no code.

There is therefore no mock-to-production migration work in this plan, and none should appear later. Four documented positions make mock substitution actively dangerous here, and they should be treated as build-time constraints from the first commit:

| Constraint | Statement |
| --- | --- |
| A UPI application response is discarded, not trusted | FRD-FR-124, PADR-03 |
| Payment status is never settable through the interface | API-153, DB-066 |
| A position is never presented as current beyond its staleness bound | FRD-FR-150, API-161 |
| Failure-induction hooks are absent from the production artefact, verified by static analysis | OPS-099, TC-155 |

RECOMMENDATION. Because there is no legacy to migrate, the structural checks (FEAT-001, FEAT-002, FEAT-037) should be built in the first three days, before any feature code exists to violate them. They are cheap now and expensive to retrofit.

## 20. Recommended MVP cut line

Classification: RECOMMENDATION. The MVP scope itself is BAD-DEC-020 and is not approved. This is a delivery-sequencing recommendation, not a scope decision.

Build, in this order:

| # | Body of work | Features | Rationale |
| --- | --- | --- | --- |
| 1 | Foundations and structural enforcement | FEAT-001, 002, 003, 037 | The rules are cheap to install and expensive to retrofit. |
| 2 | Backend authority, evidential log, API contract | FEAT-032, 033, 035 | 24 cross-cutting requirements, no open dependency. Every later feature inherits them. |
| 3 | The payment integrity chain | FEAT-016, 017, and the unblocked half of FEAT-015 | CMP-DOC-04 FR-03: complete, unblocked, and the code that prevents financial loss. |
| 4 | Identity, vehicles, publishing | FEAT-004 – 010 | 34 of 48 requirements are unblocked. |
| 5 | Search and route matching | FEAT-011, 012 | 24 requirements, no open dependency, and the platform's differentiator. Route the algorithm decision first. |
| 6 | Safety incident pipeline — without the SOS control | FEAT-025 | 16 requirements, fully specified. FRD-FR-195 keeps the control out, testably. |
| 7 | Notifications, administration | FEAT-023, 027 – 031 | 12 and 28 requirements respectively, no open dependency. |

Do not build, and do not stub, prototype or flag:

| Area | Blocked by |
| --- | --- |
| Ratings and reviews | BAD-DEC-012 — zero functional requirements |
| Wallet and rewards | BAD-DEC-013 — zero functional requirements |
| Recurring commute | BAD-DEC-008 — zero functional requirements |
| Refunds, cancellation consequence, driver settlement | BAD-DEC-009, BAD-DEC-010, BAD-DEC-003, BAD-DEC-004 |
| The SOS control and the safety response protocol | BAD-DEC-011 — and a staffed response capability |
| Verification adjudication; account state change | BAD-DEC-005, BAD-DEC-006 |

ADM-187 and ADM-191 state the rule that matters here: none of these may be presented disabled, hidden behind a role, or marked as forthcoming, and none may be partially built or placed behind a flag.

Cut line for a first release, if one is forced: everything above the trip surface — identity through confirmed, paid booking, plus the administrative surface needed to operate it. Live tracking (FEAT-019, FEAT-020) is the natural cut point, because its retention rule does not exist and every tracked trip accumulates location history that nobody has decided how to remove (FRD-RISK-007).

## 21. Items that cannot realistically fit in 15 days

Most of the plan. Stated precisely:

| Category | Items | Effort | Why |
| --- | --- | --- | --- |
| Allocated to Day 1 – 15 by dependency order | 336 | 2,540 h | Requires ~169 h/day — a team of roughly 21 at 8 h/day. No team size exists. |
| Explicitly deferred to Post-MVP | 161 | 1,184 h | Trips, tracking, messaging, notifications, safety, and the whole administrative surface. |
| Unschedulable | 10 | 78 h | Blocked on an unset value or an unselected supplier. No amount of capacity moves them. |

What a genuinely 15-day-shaped scope looks like, at a plausible small-team capacity of 5 engineers × 8 h × 15 days ≈ 600 hours:

| Included | Features | Effort |
| --- | --- | --- |
| Foundations, structural enforcement, verification infrastructure | FEAT-001, 002, 003, 037 | 510 h |
| Backend authority and API contract | FEAT-032, 035 | 152 h |

That is already over budget — and it delivers no user-visible feature at all. The honest conclusion is that a 15-day window at small-team scale buys the platform skeleton and its structural guarantees, and nothing else. Extending to the first user-visible loop (identity → vehicles → publishing → search) needs roughly 1,300 hours.

This is not a criticism of the plan or of the sprint. It is the consequence of a 3,802-hour body of specified work meeting an unstated capacity. The value of stating it is that the Project Owner can now choose: extend the window, increase the team, or reduce the scope — rather than discover the shortfall on Day 12.

Additionally, and independently of capacity: criteria 7, 8 and 11 of CMP-DOC-20 §10.1 (non-suppressible obligations passing, structural rules enforced, instrumentation live) cannot begin until criteria 2, 3 and 4 are met, because there is nothing to deploy onto (TR-126).

## 22. Decisions required

Recorded in full on sheet 09_Decisions (40 entries). Ordered by how much each unblocks:

| Priority | Decision | Unblocks |
| --- | --- | --- |
| 1 | BAD-DEC-009 cancellation + BAD-DEC-010 refund | The two live product defects. Neither requires engineering. Close before any real passenger books. |
| 2 | BAD-DEC-007 booking model | Three critical gaps — driver acceptance, seat holding, payment timing. The narrow waist of the product. |
| 3 | BAD-DEC-018 KPI and quality targets | 69 quality targets, 11 sizing decisions, every alert threshold |
| 4 | BAD-DEP-009 hosting provider | All provisioning, through the sizing register |
| 5 | BAD-DEC-005 verification policy | Driver eligibility, vehicle capacity evidencing, the entire adjudication capability |
| 6 | BAD-DEC-021 retention and closure | Position history growth today; the restore procedure |
| 7 | BAD-DEC-006 account states and admin roles | The administrative surface cannot deploy without one role |
| 8 | BAD-DEC-003 fare + BAD-DEC-004 settlement | Screen 7 cannot state the amount payable |
| 9 | BAD-DEC-011 safety response protocol | Launch gate. SOS cannot ship. |
| 10 | BAD-DEC-001 legal opinion | MVP entry precondition 1. BAD-DEC-003 must not be taken without it. |
| 11 | BAD-DEC-022 privacy boundaries | Four gaps: disclosure, result precision, messaging availability, trip sharing |
| 12 | BAD-DEC-012 ratings, BAD-DEC-013 rewards, BAD-DEC-008 recurring commute | Three whole functional areas |

Technical decisions raised or carried by this analysis:

| ID | Decision | Owner |
| --- | --- | --- |
| TECH-DEC-01 | The route-overlap algorithm and any minimum overlap threshold | Solution Architect |
| TECH-DEC-02 | Supported Android device range (MOB-OQ-001) | Solution Architect |
| TECH-DEC-03 | Accessibility conformance standard (MOB-OQ-002) | Product Owner |
| TECH-DEC-04 | Monetary precision (DB-032), which needs GAP-016 | Solution Architect |
| TECH-DEC-05 | Verification attempt limits and cool-off (FRD-OQ-003) | Security Analyst |
| TECH-DEC-06 | Who owns incident response (SEC-OQ-07) | Project Owner |
| GAP-013 | Fraud detection and response — unowned through the entire chain | Security Analyst |
| GAP-016 | Launch scale figures | Product Owner |
| GAP-017 | Pickup and drop sequencing on a multi-passenger trip | Product Owner |
| GAP-018 | How user agreement to the rules of participation is recorded | Solution Architect |
| GAP-019 | Whether the evidential record carries the originating element | Solution Architect |
| GAP-020 | Explicit statement of the seat-availability exclusion in search | Backend Lead |

### 22.1 One documentation conflict found during decomposition

DOC-CONFLICT-01 — a ratings interface and table exist for an area with zero requirements.

CMP-DOC-10 §11.9 lists POST /trips/{id}/ratings — rate a counterparty — citing FRD-FR-172, which is in fact a messaging requirement (record every message against the conversation for its ride). CMP-DOC-11 §6.7 and §6.10 list op_trip_ratings among the tables realising the Trip aggregate.

CMP-DOC-04 §1.2 and §9.2 record Ratings & Reviews as carrying zero functional requirements, withheld pending BAD-DEC-012, and CMP-DOC-17 §15 withholds reputation records from the support case surface.

A developer working from CMP-DOC-10 would build a withheld feature. This is recorded on 09_Decisions and as RISK-018. It should be reconciled under change control before construction of the trip feature begins. This analysis does not choose which document is right.

## 23. How the workbook is meant to be used

CMP-Implementation-Tracker.xlsx sits beside this document. Thirteen sheets; one master work-item register; everything on the dashboard and the feature summary is a live formula.

02_Work_Items is implementation work only. If something cannot be built by an engineer it is not in that sheet. What is not there, and where it lives instead:

| Not a work item | Carried on |
| --- | --- |
| Business and technical decisions (40 entries) | 09_Decisions |
| Functional gaps and withheld areas | 09_Decisions, and named in the Notes of the work they block |
| Supplier selections and document approval | 10_Dependencies |
| Risks | 11_Risks |
| The CMP-DOC-10 / CMP-DOC-11 ratings conflict | 09_Decisions (DOC-CONFLICT-01), 11_Risks (RISK-018) |

The six stages are deliberately separate, and nothing collapses them:

Not Started → In Analysis → Ready → In Progress → Implemented → Committed

→ Pushed → Testing → Tested → Reviewed → Completed

Implemented means code exists. Committed means a Git commit exists. Pushed means it reached the remote. Tested means testing completed successfully. Reviewed means the Project Owner or a code review accepted it. Completed means the whole lifecycle was accepted — and nothing in the workbook sets it automatically. A work item may be Blocked at any stage.

TR-121 is the reason the workbook is built this way: a passing test suite is not readiness. Release readiness is assessed against the twelve criteria of CMP-DOC-20 §10.1, of which one is currently met, and any readiness statement must carry the untested-because-undecided set with it (TR-119).

### 23.1 Deviations from the requested workbook specification

Four, all disclosed:

1. 03_Feature_Summary carries one column beyond those requested — Other Statuses (In Analysis, Ready, Cancelled) — so that the status columns reconcile against the total rather than silently under-counting.

2. The effort column is headed Estimated Effort (h) rather than Estimated Effort, so the unit is unambiguous on the sheet.

3. 04_Daily_Progress is pre-seeded with the 336 Day 1 – Day 15 items rather than left empty, so the sheet opens as a usable daily plan. Every owner-maintained column on it is blank.

4. 02_Work_Items has 55 vacant work IDs. Work IDs were issued across the whole analysed set before the not-implementation-work rows were withdrawn, and the ID standard forbids reuse and renumbering. The gaps are deliberate and are itemised in §24.

## 24. Withdrawn work IDs — what was removed from the register, and where it went

Work IDs were issued across the whole analysed set. 55 of them describe things that cannot be built: business decisions, functional gaps, withheld areas and one documentation conflict. They are withdrawn from 02_Work_Items and, per the ID standard, never reissued and never renumbered — the register carries 507 rows and 55 vacant identifiers.

Nothing was lost. Every withdrawn item's content is carried on 09_Decisions, 10_Dependencies or 11_Risks, which is where a project owner acts on it.

| Withdrawn ID | Why it is not work | Subject | Source |
| --- | --- | --- | --- |
| CMP-IMP-139 | Functional gap | Establish the fare on a published ride | FRD-GAP-005 |
| CMP-IMP-140 | Functional gap | Amend a published ride after bookings exist | FRD-GAP-007 |
| CMP-IMP-196 | Functional gap | Determine whether a ride request requires driver acceptance, and the behaviour of that decision | FRD-GAP-009 |
| CMP-IMP-197 | Functional gap | Determine whether requested seats are held pending payment, and for how long | FRD-GAP-010 |
| CMP-IMP-198 | Functional gap | Determine whether payment is taken at booking or on trip completion | FRD-GAP-011 |
| CMP-IMP-234 | Functional gap | Establish the composition of the amount payable | FRD-GAP-013 |
| CMP-IMP-258 | Business or technical decision | Record the unresolved ledger counterparty position | PAY 12.1 |
| CMP-IMP-271 | Functional gap | Define the trip state model and its permitted transitions | FRD-GAP-016 |
| CMP-IMP-272 | Functional gap | Define the consequence of a trip beginning materially early or late, or ending without completing | FRD-GAP-017 |
| CMP-IMP-319 | Functional gap | Determine the point in the journey at which messaging becomes available | FRD-GAP-019 |
| CMP-IMP-368 | Functional gap | Record a user agreement to a version of the rules of participation | GAP-018 |
| CMP-IMP-369 | Functional gap | Build the SOS control and the safety response protocol | FRD-GAP-020 |
| CMP-IMP-370 | Functional gap | Build live trip sharing | FRD-GAP-021 |
| CMP-IMP-371 | Functional gap | Build non-emergency safety reporting | FRD-GAP-022 |
| CMP-IMP-428 | Functional gap | Set KPI targets and alert thresholds for operational reporting | BAD-DEC-018 |
| CMP-IMP-449 | Functional gap | Carry the originating element on every evidential record | GAP-019 |
| CMP-IMP-485 | Functional gap | Own fraud detection and response | GAP-005 |
| CMP-IMP-518 | Functional gap | Select the hosting provider and resolve the twenty-one sizing decisions | BAD-DEP-009 |
| CMP-IMP-526 | Business or technical decision | Set alerting thresholds | OPS 12.4 |
| CMP-IMP-527 | Business or technical decision | Set operational log retention | OPS 12 |
| CMP-IMP-528 | Business or technical decision | Set the availability and maintenance window position | OPS 13 |
| CMP-IMP-529 | Withheld area | Rating, reviewing and reputation behaviour | CMP-DOC-04 9.2 |
| CMP-IMP-530 | Documentation conflict | Resolve the conflict: CMP-DOC-10 and CMP-DOC-11 specify a ratings interface and table that CMP-DOC-04 withholds | API 11.9 |
| CMP-IMP-531 | Withheld area | Wallet balance, ledger view, credits, debits and transaction history | CMP-DOC-04 9.2 |
| CMP-IMP-532 | Withheld area | Reward points, earning, redemption, coupons and history | CMP-DOC-04 9.2 |
| CMP-IMP-533 | Withheld area | Operator adjustment of wallet or reward records | FRD-GAP-026 |
| CMP-IMP-534 | Withheld area | Recurring commute definition, control and generation | CMP-DOC-04 9.2 |
| CMP-IMP-535 | Withheld area | Recurring ride generation as scheduled work | BE-143 |
| CMP-IMP-536 | Withheld area | Driver cancellation of a ride carrying confirmed bookings | FRD-GAP-006 |
| CMP-IMP-537 | Withheld area | Return of value to a passenger | FRD-GAP-014 |
| CMP-IMP-538 | Withheld area | Passenger cancellation, no-show handling and their financial consequences | FRD-GAP-012 |
| CMP-IMP-539 | Withheld area | Recording driver earnings and settling funds to drivers | FRD-GAP-015 |
| CMP-IMP-540 | Withheld area | Financial consequence of an operator intervention or a support resolution | FRD-GAP-027 |
| CMP-IMP-541 | Withheld area | Identity and vehicle verification submission and adjudication | FRD-GAP-023 |
| CMP-IMP-542 | Withheld area | Changing a user account state, and any appeal from it | FRD-GAP-024 |
| CMP-IMP-543 | Withheld area | Moderating reported content | FRD-GAP-025 |
| CMP-IMP-544 | Withheld area | Account closure and the treatment of a closing user data | FRD-GAP-029 |
| CMP-IMP-545 | Withheld area | Data retention: what is held, for how long, and how removal reconciles with durability | FRD-GAP-028 |
| CMP-IMP-546 | Withheld area | Define the administrative role set from the twelve capabilities | ADM-166 |
| CMP-IMP-547 | Project decision or precondition | Approve CMP-DOC-01 through CMP-DOC-20 in chain order | TR 10.1 criterion 1 |
| CMP-IMP-548 | Project decision or precondition | Resolve the four decisions that block the majority of outstanding work | TR 8.4 |
| CMP-IMP-549 | Project decision or precondition | Resolve BAD-DEC-009 cancellation and BAD-DEC-010 refund before any real passenger books | FR-01 |
| CMP-IMP-550 | Project decision or precondition | Resolve BAD-DEC-007 the booking model | FRD-GAP-009 |
| CMP-IMP-551 | Project decision or precondition | Resolve BAD-DEC-003 the fare model and BAD-DEC-004 driver settlement | FRD-GAP-005 |
| CMP-IMP-552 | Project decision or precondition | Resolve BAD-DEC-005 the verification policy | FRD-GAP-002 |
| CMP-IMP-553 | Project decision or precondition | Resolve BAD-DEC-011 the safety response protocol and staff a response capability | FRD-GAP-020 |
| CMP-IMP-554 | Project decision or precondition | Resolve BAD-DEC-022 the privacy boundaries between users | FRD-GAP-001 |
| CMP-IMP-555 | Project decision or precondition | Obtain the qualified legal opinion on the operating model | BAD-DEC-001 |
| CMP-IMP-556 | Project decision or precondition | Select the six unselected suppliers | TR 10.1 criterion 3 |
| CMP-IMP-557 | Project decision or precondition | Supply the launch scale figures | GAP-016 |
| CMP-IMP-558 | Project decision or precondition | Resolve GAP-017 pickup and drop sequencing on a multi-passenger trip | GAP-017 |
| CMP-IMP-559 | Project decision or precondition | Approve or amend the proposed MVP scope | BAD-DEC-020 |
| CMP-IMP-560 | Project decision or precondition | Decide what constitutes a release gate beyond the non-suppressible set | TR-115 |
| CMP-IMP-561 | Project decision or precondition | Route the route-overlap algorithm to CMP-DOC-07 as a named technical decision | FR-06 |
| CMP-IMP-562 | Project decision or precondition | Complete the forward traceability review of the 37 uncited integrity-critical requirements and the 146 remaining | TR 6 |

Summary of withdrawals

| Category | IDs |
| --- | --- |
| Project decisions and preconditions (FEAT-045) | 16 |
| Withheld areas (FEAT-040 … FEAT-044) | 18 |
| Functional gaps embedded in buildable features | 14 |
| Business or technical decisions embedded in buildable features | 6 |
| Documentation conflict | 1 |
| Total | 55 |

The register got smaller and the plan did not. Total estimated effort is unchanged at 3,802 hours, because every withdrawn row carried zero effort — there was never anything to build in them. What changed is that a developer opening 02_Work_Items can no longer pick up a gap and implement it.

End of CMP Implementation Analysis, version 0.1 (Draft).